| Texas Nodal Market Implementation Program - Overview |  |  |  |
| --- | --- | --- | --- |
| Program Director | Jerry Sullivan | Reporting Period | Status at 01/22/2007 |

Confidence in delivery – RAG Status

| Dimension | This week | Trend | Commentary |
| --- | --- | --- | --- |
| Scope/baseline | A | = | Working to close NPRR backlog on all projects to November Protocol version |
| Resources | A |  | Initiated discussions from ERCOT staff for additional personnel. Looking to ramp up committed resources from zonal for nodal projects and transition preparation |
| Costs | A | = | Second reporting cycle initiated. Tracking to budget with some variances. Working with finance to close variances |
| Timescales | R |  | December TPTF commitments met. Working on requirement and CSD approvals with TPTF |
| Critical dependencies | R |  | Critical path work identified major build and release sequence to support EDS trials; working to finalize integrated project schedules to confirm feasibility of build sequence and timescales for downstream projects (integration, Integration testing, and market trials) |
| Vendors | A | = | ERCOT Board of Directors postponed approval of CRR Phase II contract until January 2007. Project team to assess impact during meetings with vendor and determine recovery plan |
| Stakeholders | A |  | Requirements and CSDs approaching approval, and initial Interface documents delivered to TPTF. Working to make MP Sandbox available mid February “Deep dive” review scheduled with ERCOT Executives, business/IT owners and Nodal leadership to improve engagement |

 - Worse,  - Better, =  - Same

- Key Issues for escalation

- IDA

- Working to improve QA, traceability across the program

- NMMS

- Need to correct list of electrical bus names, work in progress with MPs

MER Training

- Towards the end of 2007 training will require dedicated facilities to deliver training.  We are pursuing ERCOT facilities and free MP facilities but there is a very real concern that we will not be able to meet the facility requirement.

- MER & MIS

- CEII security handling strategy has not yet been determined by Security. Need a decision by March 1st, will escalate if none.

- Identity Management is required for MIS go-live, and currently there is continued discussion within ERCOT about how/whether to fund it.

IRT

- Recent efforts on program critical path and facility needs are causing delays in our deliverable creation (related to market trials).

  - Focusing some of the market trials team back on to market trials to slow schedule slippage.

  - IRT expects ongoing maintenance of the critical path to be transitioned to the Nodal PMO by end of January.

- TPTF is focused on Requirements and Conceptual System Designs (CSDs) and has indicated participation in readiness criteria development and market trials will be delayed.

  - Slight delay has been estimated (2 weeks).  Readiness Advisor team has a lower than estimated burn rate to date so expecting no cost impact to the project.

Key achievements and expectations

| Project | Achievements this Period | Outlook for next period |
| --- | --- | --- |
| PMO | - Measures signed off for Nodal balanced scorecard | - Prepare for Nodal Program ‘deep-dive’ - Produce draft prototype for Nodal balanced scorecard |
| IDA | - Preliminary review of EMS RPP CSD - Preliminary review of CRR Use Cases - Review and response to TPTF comments for EMS requirements - QA Operation document approved - 2nd phase SoSA planned - SoSA POC initiated | - Publish the consolidated IDA/EA issues list - Review/update of the artifacts tracking spreadsheet - Review of CRR Use Cases - QA Adoption Training workshop - Initial End-to-End testing workshop with stakeholders - End-to-End plan agreed and publicized |
| NMMS | - NMMS: Develop training documentation - NMT: Now 75% complete with 4,013 Network operations modeling issues. Closed out of the 5,359 identified data issues. The new query (based on the 10/30/2006 to 12/31/2006 period) results brought in 1,082 additional new pending data issues. - NMT: Created development, SIR and MCD to promote measurement weight fix to iTEST. | - NMMS: Prepare training classes. - NMMS: Clarify and document modeling issues. - NMT: Continue to internally resolve the outstanding issues prior to meeting with MPs. - NMT: Conduct work on QSE issues. |
| EMS | - Continued TPTF Review of EMS Requirements Comments & Responses. - Completed EMS/MMS Basic Impact (Y/N) Analysis For NPRR’s Through Jan. 2007 | - Continue Review of TPTF Comments & Responses of EMS Requirements - Commence TPTF Review of OS Requirements Documents - Continue EMS/MMS Phase 2 Baseline Planning & Budgeting Activity - Commence Full Funding SOW Amendment for EMS Phase 2 Vendor - Launch First OS Work Tasks to System Operations Designees |
| MMS | - TPTF Approved All (Five) MMS Requirements Documents | - Complete Full Funding SOW Amendment for MMS Phase 2 Vendor |
| CRR | - Hired Sr. Market Analyst - Reviewed System Level Use Cases with team - Developed initial list of NOIE Generators - Begun McCamey Area map | - BOD vote on budget - Draft Technical Architecture document |
| COMS | - Completed second draft of development guidelines. - Began interface reconciliation with CMM and EMS. - Obtained TPTF approval for all but one COMS CSD - Registration: Review by TPTF on 12/5 and looking for comments by 12/15. Approval is scheduled for 1/9/2007. | - COMS: Conduct architectural workshops (settlements business process) - Continue data model definition - CMM: Complete initial draft Detail - Validate Exposure Calculation Model - Define Test Plan - Standup CMM Sandbox system |
| MER - Training | - Launch of Online testing for ERCOT Nodal 101 the Basics - Delivery of ERCOT Nodal 101 the Basics in Houston. | - Continue development of text for WBT ERCOT Nodal 101 - Continue development of LSE 201, Transitions and Basic Training Courses |
| MER - MIS | - Conceptual System Design has been approved by TPTF. - Security Sign Off has been obtained for Security Audit documents - Technical Architecture Document has been completed and submitted to the EA group. - All Use Cases finalized - Finalized MIS Punchlist. | - Continued content inventory documentation - UI design for notifications entry (will require a CR) - Dashboards analysis, design and wireframes - Site visit to StarTex Power rescheduled. - Submission of final Use Cases. - Compare AsisSiteMap to current Requirements |
| EDW | - EDW Governance document reviewed by stakeholders. - Achieved definitions of 80% of project areas and have begun process of high-level requirements gathering for those identified. | - Receive feedback on EDW engagement process. - Deliver MIS/EDW requirements collaboration presentation to Nodal Leadership team. |
| Infrastructure | - Web Services Sandbox: Server build completed and turned over to the project team. - EDS ½ Environment: Vendor reported successful test of the software targeted for these servers - EA Lab: Progress made and build nearing completion | - Siebel Development environment: complete build - Lodestar development environment: Complete build of blade server - P595 Austin Standup: IBM to complete engineering review. - Credit monitoring development environment: Schedule second round of server builds |
| Enterprise Integration | - Nodal Integration Flow Matrix (D2.3) - MIS External REQ Specs (D4.1) - NMMS-Settlement Test Data & Scripts (D6.4) - Registration-CMM Interface Design Specs (D7.2) - S&B-CMM Interface Requirements Specs (D8.1) - EI Team and MMS/ABB meeting held to discuss working together more effectively. - Initial draft of Mapping EDS/Release/Build Sequences completed. - Stephen Kerr, joined as the ERCOT Project Manager this week. | - Integration Roadmap w/ Phasing by EDS (D1.6) - MMS-MIS Interface Build Iteration (D5.5) - S&B – CMM Interface Design Specs (D8.2) |
| Integration Testing | COMS - Met with CMM team to collaboratively develop test plan - Received use cases from Settlements and Billing for test case writers to provide test case examples Data/E2E/Info - QC-Database POC Testing - POC for QC-Database Performance Testing Tools - Review of Sandbox Test Script Breakdown - Reviewed LMS Test Cases - Organized LMS Requirements in Req Pro and QC - Verified LMS Requirements and finalized scope for latest LMS test cycle Project - Reviewed process for establishing duration estimates for testing - Established metrics for QA Assessment process | COMS - Test case writer to create separate test case documents in standard template from ROME test cases NMMS - Create initial NMMS FAT Test Plan - Create initial estimation for NMMS Test Tools - Update QC to Req Pro Sync and Transfer Ownership from IT to Testing - Review all LMS Test Scripts and submit to business for approval - Review LMS Test environment for completeness and standards Project - Submit request to vendors for additional resources - Complete December budget summary |
| ERCOT Readiness & Transition | - Transition: - Continued discussions with ABB / Areva regarding training curriculum - Two resources assigned to control room desk procedure development - Market Trials: - Continued work on program critical path - Build sequence matrix (v5) and diagram (v2) reviewed with projects - Posted market trials overview presentation for TPTF meeting on 1/25 (addresses market feedback) - TA document for EDS 1 & 2 environments completed, infrastructure ordered - Readiness Advisor: - Conducted second round of discussions with Internal metric owners | - Transition: - Organization structure / sizing discussions with ERCOT Directors - IRT Team organization review with Project Director - Transition Work plan review with Project Director - Training curriculum review - Market Trials - Continue Critical Path refinement - Present response to market comments re: market trials approach - Readiness Advisor - Present to TPTF: Status, candidate metrics, metric sub-group scope and involvement |

Key Milestone Status

| Control Milestone | Baseline | Actual/F’cast | Comment |
| --- | --- | --- | --- |
| Requirements approval | 10/31/2006 | 1/24/2007 | Slippage to key reqts (EMS, MMS & EDW) |
| Key CSD submission | 12/31/2006 | 12/31/2006 | Planned CSDs issued on schedule |
| Key CSD approval | 2/28/2007 | 2/28/2007 | CRR, MIS and most COMS CSDs approved ahead of schedule |
| Vendor SOW BOD approval | 12/10/2006 | 1/16/2006 | CRR vendor approval delayed |
| Interface specs – draft | 12/31/2006 | 12/31/2006 | Deliverable issued to TPTF on schedule |
| Market Operations Sandbox | 1/31/2007 | 2/15/2007 | Initial functionality will be limited and depends on planned January TIBCO release |
| Interface specs – final | 3/31/2007 | 3/31/2007 |  |

Top Risks

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| EDS trials disrupted by inability of upstream projects to deliver product in time to enable proper integration testing sequence | H | H | - Establish build and release strategy for critical path - Establish releases and dependencies - Workshops with PM’s to agree details and ensuring commitments |
| Lack of discipline in managing ongoing changes to protocols impact budget and delivery schedule | H | H | - Address backlog NPRR’s for cost and schedule impact, TPTF and Steering Board approval of changed scope - Periodically synchronize projects to target versions of Protocols - Establish more proactive, timely change control process |
| Delays to the integration project could impact the Nodal critical path | H | H | - Identify and establish integration vendor - Obtain Integration PM resource - Initiate Integration activity to identify issues |