## TPTF Comments & Responses
Document Name: |  |  |  | Texas Nodal Readiness Advisor Metric Framework & Metric Comments
S.No. | Issuing Entity (Name) | Metric Number | Pg, Sec., Req. | Description | Response Type | Reviewer | Reason / Comment
1 | Reliant (F.Trefny) |  |  | Combine the Network Model Management, Market Management, and EMS into one nodal team implementation box. We need to promote we are all in this together from a readiness perspective. Add hand offs from the nodal design team to the ERCOT operations staff. For example, I do not think the nodal Network Model Management is responsible for actual testing. They may be the ones to fix something if it is not correct, but dispatch operations need an organization to house the testing team. | Clarification Provided | J. Dondeti | We have included they subject boxes into 1 box named "Systems" for that purpose, Additional decomposition enables us to aggregate reporting to a second level of detail. We placed them into logical groupings as they cover differing aspects of program development as defined in the Transition Plan.
2 | Reliant (F.Trefny) | D12 |  | Add box to ERCOT internal to cover new facilities construction including control room logistics during start up testing and cut over. | Accepted | J. Dondeti | Metric added "D12 - Verify New Facilities Construction Complete" to metric map pending approval by the TPTF
3 | CNP (V.Emesih) | D14 |  | Add box to ERCOT internal to identify all the operating tasks in the nodal protocols and make operating personnel assignments for all functions in nodal clear to all personnel involved. | Accepted | J. Dondeti | Metric added "D14 - ERCOT Staffed for TN Operations" to the metric map pending approval by the TPTF
4 | Reliant (F.Trefny) | D9 |  | Add box to ERCOT internal to describe process for maintaining data and telemetry in a controlled environment once that data and systems are “approved” by operations | Clarification Provided | J. Dondeti | The Metric "D9 - Validate EDW Access/Accuracy" is intended to address this item
5 | Reliant (F.Trefny) |  |  | Add box to ERCOT internal to cover communications systems infrastructure for new com lines to QSEs, etc | Clarification Provided | J. Dondeti | The communications infrastructure is required before many other tests can be performed. The end products like telemetry and control are only possible when the communications infrastructure is in place.
6 | Reliant (F.Trefny) | MP9 |  | Add boxes to Market Participants to cover support of EDS 3. EDS 3 can not complete until we have all MPs working and good LMPs running. Seems like several steps are needed such as getting interface working, getting offers, etc | Pending | J. Dondeti | Metric "MP9 - Market Trials MP Participation" could be expanded into 4 metrics, one for each EDS.
7 | Reliant (F.Trefny) |  |  | Voltage Support in the EMS box needs to have a green border to match network testing | Accepted | J. Dondeti | Metric Map changed - pending approval by TPTF
8 | Reliant (F.Trefny) | EMS10 |  | Need LFC tuning in EMS; consider have LFC operational as a milestone | Clarification Provided | J. Dondeti | Metric 'EMS10 - QSE Load/Freq/Reg Control' in EDS3 is intended to address this item.
9 | Reliant (F.Trefny) | MMS10 |  | Need to have the Generation subsystem working to start EDS 3 so it can call SCED. | Clarification Provided | J. Dondeti | Metric "MMS10 - 'Verify SCED Functions" in EDS3 is intended to address this item.
10 | Reliant (F.Trefny) |  |  | Add boxes for completion of EDS1, EDS2, EDS3 and EDS4 as moving from one test system to another is a major accomplishment toward readiness | Clarification Provided | J. Dondeti | EDS1, 2, 3 & 4 are currently identified on the Metric Map and their completion will be apparent by the colorized border combined with a colorized background. Completion of the EDS Trials will be reported by the metrics making up the test.
11 | Reliant (F.Trefny) |  |  | Has the Metric Sub-group been formed? Is it attended by all who need to be? Do we need to elevate to TPTF with updates for each meeting week. | Clarification Provided | J. Dondeti | The Metric Sub-Group held the first meeting on Jan 30th, 2007. Those in attendance were: Chris Brewster Trip Doggett Marguerite Wagner Don Blackburn Readiness Advisors
12 | Reliant (F.Trefny) |  |  | Schedule a detail review to vet all with TPTF and ERCOT management before adopting | Accepted | J. Dondeti | A detailed review of the Metric Map and comments received is scheduled for the TPTF on February 6th
13 | Garland Power & Light (Ronnie C. Hoeinghaus) |  |  | The MSG will consist of market participants (ideally 2) from each of the seven market segments and an ERCOT representative Comment: How much involvement is anticipated from these participants over time? What should happen if due to small shop size, one or more segments are not able to have 2 reps? | Clarification Provided | J. Dondeti | Initially we plan to meet every other week until the Metric Framework and Metrics are approved (mid-march). Meetings can be attended in person or via Webex. Time spent outside of the meetings will vary. The MSG will last for the duration of the transition. Our goal is for the entire team to be represented by at least 2 reps per segment. Theoretically, a small organization can be represented by 1 rep.
14 | Garland Power & Light (Ronnie C. Hoeinghaus) |  |  | ERCOT shall chair and provide administrative and technical support to the MSG Comment: Who would ERCOT recommend from their shop to chair this committee? | Clarification Provided | J. Dondeti | It is being suggested that the Readiness Advisor fulfill this role as facilitator - the RA will not be part of the decision making process.
15 | Garland Power & Light (Ronnie C. Hoeinghaus) |  |  | Any declaration of the accomplishment of a metric is at the sole discretion of the Readiness Advisor Team Comment: Should you add to the end of this “with TPTF’s concurence? | Clarification Provided | J. Dondeti | The TPTF will have a major approval role in the definition and verification criteria for each metric, however, the RA will have the responsibility to verify the metric upon submittal - this insures the credibility of the RA to all parties.
16 | Garland Power & Light (Ronnie C. Hoeinghaus) |  |  | Readiness Advisor Team Contacts Comment: Will ERCOT have an employee that will manage this group? | Clarification Provided | J. Dondeti | Yes, however, for the verification phase, the reporting structure has not been defined.
17 | City of Eastland (Chris Brewster) |  |  | Market participants will be very interested in the sharing of market readiness responsibility/authority between the MSG and the RA. I recommend noting in the Metric Fill Legend Box that the first three steps (Metric Definition, Metric Defined, and Metric Approved) will be the responsibility of the MSG/TPTF, and the next four steps or statuses (Metric Late, Metric Received by RA, Metric LTA, Metric Verified) will be the responsibility of the RA. Perhaps this could be accomplished by two sub-boxes within the fill legend box, or brackets with text | Accepted | J. Dondeti | Readiness Advisor concurs. Pending TPTF approval.
18 | City of Eastland (Chris Brewster) |  |  | A point that was raised today that I recommend would be arrows connecting the dependent or linked metrics across the boxes, so long as the resulting linkages do not become so complex as to obscure the rest of the map. In that circumstance, perhaps separate sub-maps would be helpful, and would keep the high-level map cleaner and more easily understood. Today's example was connecting Telemetry Point Validation in the MP box to the same metric in the Network Model Management box. | Accepted | J. Dondeti | Readiness Advisor concurs. Pending TPTF approval. However, other methods may be adopted to show these relationships.
19 | IT Project (John Hall) | D13 |  | In discussion of the metric to define the verification criteria to show a method is in place to identify and continuously manage the Nodal Project Critical Path, it was suggested that this metric be expanded to include at least 2 other aspects of Project Management, specifically a method is in place to manage budget and project resourcing. | Accepted | J. Dondeti | Readiness Advisor concurs. Pending TPTF approval.
20 | Meter Data Management Agent Process (Don Tucker) | MP7 |  | In discussion of the metric to define the Meter Data Management for Market participants it was determined that this function will not change as transition from zonal to nodal occurs. Therefore this shold not be considered a metric issue and the metric removed from the Metric Map. | Accepted | J. Dondeti | Readiness Advisor concurs. Pending TPTF approval.
21 | Patrick Coon / Readiness Advisor | CO2 |  | It is requested that since the preceding metri CO1 is perfomred in EDS4 that the following metric CO2 be changed to show as being done in EDS4 also | Accepted | J. Dondeti | Readiness Advisor concurs. Pending TPTF approval.
22 | Settlements & Billings (Bill Barnes) | CO3 |  | Change name of metric from "Settle a RUC/SASM DAM Market" to "Verify DAM Settlement Statements" | Accepted | J. Dondeti | Readiness Advisor concurs. Pending TPTF approval. Owner - Bill Barnes
23 | Settlements & Billings (Bill Barnes) | CO4 |  | Change name of metric from "Zonal/Nodal Coordinated Settlements" to "Zonal/Nodal Parallel Settlement Operations" | Accepted | J. Dondeti | Readiness Advisor concurs. Pending TPTF approval. Owner - Bill Barnes
24 | Settlements & Billings (Bill Barnes) | NEW |  | Recommend new metric "Verify Inbound Settlement Invoices" | Accepted | J. Dondeti | Readiness Advisor concurs. Pending TPTF approval. Owner - Bill Barnes
25 | Settlements & Billings (Bill Barnes) | NEW |  | Recommend new metric "Verify RT Invoices" | Accepted | J. Dondeti | Readiness Advisor concurs. Pending TPTF approval.Owner - Bill Barnes
26 | Settlements & Billings (Bill Barnes) | NEW |  | Recommend new metric "Verify DAM Invoices" | Accepted | J. Dondeti | Readiness Advisor concurs. Pending TPTF approval. Owner - Bill Barnes
27 | Settlements & Billings (Bill Barnes) | NEW |  | Recommend new metric "Verify CRR Auction Invoices" | Accepted | J. Dondeti | Readiness Advisor concurs. Pending TPTF approval. Owner - Bill Barnes
28 | Settlements & Billings (Bill Barnes) | NEW |  | Recommend new metric "Verify Financial Transfer and Processing" | Accepted | J. Dondeti | Readiness Advisor concurs. Pending TPTF approval. Owner - Cheryl Yager / Bill Barnes
29 | Settlements & Billings (Bill Barnes) | C5 |  | Change name of metric from "Contingency Plan for Settlement Failures" to "Develop Plan for Contingency Failures" | Accepted | J. Dondeti | Readiness Advisor concurs. Pending TPTF approval. Owner - Bill Barnes
30 | CRR (Beth Garza) | CRR3 |  | Change name of metric from "Execute Monthly CRR Market during Trials" to "Execute and Settle Monthly CRR Market during Trials" | Accepted | J. Dondeti | Readiness Advisor concurs. Pending TPTF approval. Owner - Beth Garza
30 | CRR (Beth Garza) | CRR5 |  | Change name of metric from "Execute Seasonal/Annual CRR Market during Trials" to "Execute and Settle Seasonal/Annual CRR Market during Trials" | Accepted | J. Dondeti | Readiness Advisor concurs. Pending TPTF approval. Owner - Beth Garza

## Punch List
Document Name:
Punch List # | Punch List Description | Related TPTF Comment

## Data Entry Lists
Response | Description
Accepted | Comment accepted and requirements document updated as per the comment.
Clarification Provided* | Clarification provided and requirements document updated to clarify
Clarification Provided | Clarification provided and no updates made to the requirements document.
Pending | Issue is not resolved yet. All pending issues will be dispositioned to a punch list and resolved later. These issues need more time and coordination across multiple Nodal projects.
Rejected | Comment rejected as it does not comply with Nodal Protocols.