## Slide 1: Oil and Gas Profile Implementation Plan

## Slide 2: BUSOGFLT Background
02-28-2003 ERCOT received Oil and Gas Profile Segment request
From 02-2003 thru 08-2006 finalizing request, data collection and load research analysis
08-30-2006 ERCOT completed analysis of Oil and Gas load research data and recommended adoption as an ERCOT sponsored Profile with PWG consensus
09-26-2006 COPS unanimously approved concept of Oil and Gas Profile Segment (BUSOGFLT)
10-06-2006 TAC unanimously approved concept of BUSOGFLT Profile Segment
PWG drafted LPGRR017 to make guide changes necessary to implement the BUSOGFLT Profile Segment
ERCOT Impact Analysis indicated minor Lodestar system changes required (O & M dollars)

## Slide 3: BUSOGFLT Future Timeline
Approval LPGRR017, ERCOT Impact Analysis, and this Implementation Plan
  02-13-2007 COPS
  03-13-2007 TAC
  04-17-2007 Board
04-18-2007 Market Notice announcing BUSOGFLT Profile Segment
09-15-2007 150 day notice ends
09-18-2007 Implementation date to avoid weekend
  09-15-2007 ERCOT will begin posting Forecasted Load Profiles
  09-19-2007 ERCOT will begin posting Backcast Load Profiles

## Slide 4: BUSOGFLT Transition
04-18-2007 CR’s eligible to begin sending in documentation to ERCOT requesting BUSOGFLT Profile Segment assignments
04-18-2007 to 09-03-2007 ERCOT will accumulate and validate change requests
  ERCOT will notify submitter of any invalid request
09-04-2007 ERCOT will send files of change requests to TDSPs
09-19-2007 TDSPs will submit 814-20 transactions changing Profile Segment to BUSOGFLT with effective date of a meter reading on or after 09-18-2007

## Slide 5: BUSOGFLT Ongoing process
09-04-2007 CR’s continue sending in documentation to ERCOT requesting BUSOGFLT Profile Segment assignments
09-11-2007 ERCOT begins sending validated change requests to TDSPs
  ERCOT will notify submitter of any invalid request
09-19-2007 After receipt of requests, TDSPs will submit 814-20 transactions on or before the second regularly scheduled meter read date

## Slide 6: BUSOGFLT Ongoing process
(Continued)
January 2008 ERCOT will begin performing quarterly validations of BUSOGFLT Profile Segment assignments
  ERCOT will verify that profile segment assignments for ESIIDs in Lodestar are consistent with documentation submitted
Periodically ERCOT will perform quality control validations of the BUSOGFLT Profile Segment assignments
  Field inspection of a random sample of BUSOGFLT ESIIDs to determine any miss-assignments
  ERCOT will notify CR of record and TDSP of any ESIID found to be invalid
  TDSP will send in 814-20 transaction to assign ESIID to the appropriate default Profile Segment as specified in the Decision Tree

## Slide 7: BUSOGFLT Key Documents
Key Documents available on the ERCOT website at the following links:
  LPGRR017
  http://www.ercot.com/mktrules/issues/lpgrr/000-024/017/keydocs/017LPGRR-02a_PWG_Recommendation_Rep.xls
  http://www.ercot.com/mktrules/issues/lpgrr/000-024/017/keydocs/017LPGRR-02_PWG_Recommendation_Report_122006.doc
  ERCOT Impact Analysis
  http://www.ercot.com/mktrules/issues/lpgrr/000-024/017/keydocs/017LPGRR-03_Impact_Analysis_011907.doc

## Slide 8
New BUSOGFLT Profile Segment
VOTE
PWG requests the following motion:
  That COPS recommend to the TAC and the Board approval of the new BUSOGFLT Profile Segment per the details in this packet, which include this implementation plan and links to LPGRR017 and the ERCOT Impact Analysis.