## Slide 1: PR50121_07 Retail Business Processes (RBP) Project Update
A Sub-project of the Service Oriented Architecture (SOA) Initiative

## Slide 2: Background
Objectives
Goal is to replace current SeeBeyond Retail Components with TIBCO EAI components to deliver a technology and framework improved scalability, reliability, stability & maintainability. RBP is one of 8 SOA Subprojects to replace SeeBeyond.
Drivers
Minimize or reduce operating failures produced from current SeeBeyond Application and Architecture.
Reduce maintenance costs associated with up-keep of SeeBeyond Application and Architecture.
PR50121_07 RBP PPL Source: ERCOT Priority: 1.0 Rank: .08 Budget: $1-3M Program Area: RO

## Slide 3: Project Status
Project Phases
Execution
  Go-Live – Complete 12/10/2006 (within schedule and budget)
  Stabilization effort – Target Completion 03/09/2007 (revised
Closing – Target to complete March 2007
Recent Activities As of 02/12/2007
Began Stabilization Efforts
  Begin Stabilization status meetings
  Began enhancements to HAWK Monitoring Processes
  02/10/2007-Implemented SIRs and Database Maintenance to resolve portion of stabilization issues.
Next Steps
Continue Delta Siebel Data Conversion every weekend until Complete
Continue TIBCO monitoring, enhancements, and training with onsite TIBCO consultant
Resolve all stabilization issues
Compile Overall Project Lessons Learned
PR50121_07 RBP PPL Source: ERCOT Priority: 1.0 Rank: .08 Budget: $1-3M Program Area: RO

## Slide 4: Stabilization Update
Post-Production Issues:
74 Issues relating to RBP have been logged for investigation as of 02/14/2007
  48-Closed
  1-Duplicate
  2-Invalid
  7-Deferred to Future Retail Release (low priority)
  10-Open
  6-Business Analysis/Verification (pending close)
Performance Metrics Update:
Unable to provide true representation of metrics at this time due to the Production Issues/Outages. Will return in May and August to provide detailed metrics after system has stabilized.

## Slide 5: Stabilization Update (Cont’d)
High Priority Issues
01/22/2007 - TIBCO/Siebel Slow Interaction: Noticed degradation in performance.
    Impact: Response transaction delays from normal and management exception processing
    Action: Performed database maintenance during 02/10/2007 Release.
    Status: Pending Close
01/22/2007 – The validity of transactions are periodically evaluated twice. When this occurs the transaction is evaluated as a Duplicate Transaction.
    Impact: Reject transactions produced.
    Action: Database maintenance, oracle upgrade and Siebel release performed during 02/10/2007 Release and problem ceased.
    Status: Pending Close
01/25/2007 - ERCOT experiencing periodic failures of transactions as they process to Siebel, yielding a reject transaction in some cases.
    Impact: Delays in Response Transactions due to reprocessing and Reject Transactions Produced.
    Action: A Log file was disabled on 01/29/2007 and the problem has ceased.
    Status: Pending Close
01/30/2007 – Half Orders being produced in Siebel.
    Impact: Delays in response transactions possible due to Management Exception Handling.
    Action: Database maintenance, oracle upgrade and Siebel release performed during 02/10/2007 Release and problem ceased.
    Status: Pending Close

## Slide 6: Questions / Contact
Adam D. Martinez
Mgr, Market Operations Divisional Projects Organization
ERCOT
(512) 248-3883
amartinez@ercot.com
Hope Parrish
PM, Market Operations Divisional Projects Organization
ERCOT
(512) 248-6522
hparrish@ercot.com