## Slide 1: MarkeTrak Lessons Learned Summary Report Retail Market Subcommittee February 14, 2007 Adam Martinez & Scott Egger Market Operations Division Projects Organization

## Slide 2: Supporting Documents
Please refer to the following documentation for additional MarkeTrak
Lessons Learned feedback not detailed in this Summary Report
  Technical Focus Group notes
    TechMtg_MT_Lessons_Learned.doc (posted with this document) or at web link: http://www.ercot.com/services/comm/projects/current/50007/TechMtg_MT_Lessons_Learned.doc
  Business Focus Group notes
    BusMtg_MT_Lessons_Learned.doc (posted with this document), or at web link: http://www.ercot.com/services/comm/projects/current/50007/BusMtg_MT_Lessons_Learned.doc

## Slide 3: Background
ERCOT, with support from RMS, conducting a Lessons Learned process with the Market that incorporated 3 major steps:
Conduct Focus Groups Sessions – The ERCOT DPO conducted 2 focus group sessions to identify key lessons observed and to help frame discussion topics for the RMS report
  Technical Focus Group Session held on January 9, 2007
  Business Focus Group Session held on January 10, 2007
Analyze Feedback / Identify Improvement Actions – The ERCOT DPO analyzed the Focus Group feedback and summarized / categorized the feedback into seven (7) major improvement areas or “Lessons Learned themes”
  DPO drafted proposed future actions to address each improvement area
  Draft report reviewed with RMS Leadership prior to today’s session
Review Summary Report with RMS / Agree to Next Steps – Review Lessons Learned Report with RMS, allow for final discussion and input from participants, identify/confirm future actions
  RMS Lessons Learned Forum, scheduled for today, February 14, 2007

## Slide 4: MarkeTrak Lessons Learned ~ What Went Well ~

## Slide 5: What Went Well
ERCOT facilitated multiple on-site meetings to gather business requirements
MPs were able to review information gathered at on-site business requirements elicitation meetings
ERCOT’s IT development support was excellent
ERCOT is moving forward with technology. The new tool and API have provided efficiencies for users
The MarkeTrak training was beneficial for users
New tool is a significant improvement over FasTrak
Others?

## Slide 6: MarkeTrak Lessons Learned ~ Improvement Areas ~

## Slide 7: Improvement Area #1: Communications
Theme: Communications between ERCOT and Market Participants were ineffective and did little to achieve agreement and common understanding of project activities, major milestones and deliverables, and project roles and responsibilities
Focus Group Comments:
  ERCOT needs to ensure it interprets MP requirements correctly; no formal “sign off” of requirements, no single body speaking for Market needs
  MPs want more involvement throughout requirements gathering phase; need more opportunities to communicate and validate requirements
  Involve MPs technical resources earlier in the project; lack of communication regarding technical aspects of project OR inappropriate/misdirected technical communications resulted in misunderstandings and rework
Root Cause:
  MPs did not communicate their concerns to ERCOT at appropriate times; timing of first demo resulted in more “requirements” communications instead of reqmts validation
  ERCOT did not proactively validate its communications with MPs to ensure understanding, agreement, or acceptance
  Communications targeted to same MP reps for both business & technical content
Recommended Future Actions:
  RMS to name project-related MP Steering Committee to provide Market leadership and oversight, to issue/review MP communications; to provide Market sign-offs as needed
  ERCOT will target project-related communications to appropriate business and technical contacts designated by MPs and/or MP Steering Committee

## Slide 8: Improvement Area #2: Project Management
Theme: At times ERCOT project management lacked consistency and continuity, which resulted in confusion regarding the project’s scope, schedule, and budget
Focus Group Feedback:
  Incorporate MPs in the process of creating the project schedule
  Incorporate time to allow MPs to complete complementary activities in the schedule
Root Cause:
  ERCOT did not formalize the PM as a Market contact for the project
  ERCOT did not solicit and MPs did not communicate their tasks and associated efforts/durations to the ERCOT PM for incorporation into the schedule
  ERCOT did not consistently solicit MP input to the project schedule
Recommended Future Actions:
  When initiating a Market-facing project, ERCOT will announce the Project Delivery contacts, inclusive of the PM, the Business Analyst, and Technical Contact (as appropriate)
  The project schedule needs to incorporate “project status” milestones where MPs are informed of the project schedule, scope, budget, and risks/issues (not RMS)
  ERCOT’s PM and project leads will meet with MP Steering Committee on a recurring basis to review project “health”
  In addition to the proposed MP Steering Committee, ERCOT will solicit business and technical MP groups to be assigned to the project for detailed reviews

## Slide 9: Improvement Area #3: Business & Technical Requirements
Theme: The requirements gathering process was extended and produced ambiguous results
Focus Group Feedback:
  MPs feel requirements gathering process took too long to complete
  MPs feel some requirements were omitted from the final product
  There was not a clear understanding by MPs of what comprised the final requirements
Root Cause:
  The initial meetings to discuss the business requirements with MPs was done under SCR 732, Enhancements to FasTrak Process (date received: 11/19/06), and the project to deliver the requirements required SCR 738, Enhancements to FasTrak Tools (date received: 8/17/04)
  The MarkeTrak project was initiated in 2005, a year after SCR 732 was complete. This resulting in a gap in time and a loss of continuity with the project schedule
  ERCOT did not require a Market “sign-off” on business and technical requirements
Recommended Future Actions:
  ERCOT will conduct regularly scheduled check point meetings with MP Steering Committee to verify/validate requirements
  ERCOT will seek Market sign-off for Business and Technical Requirements
  ERCOT will share “draft” requirements documents with MP for their review/feedback before final versions are presented for sign-off
  ERCOT and MPs must consider the governance process timeline and intent of SCR process to minimize project impacts

## Slide 10: Improvement Area #4: Vendor/Product Selection
Theme: MPs feel that any ERCOT tools decision that could impact MP operations should allow for MP review and that tool demo should be provided early in a project’s lifecycle
Focus Group Feedback:
  MPs would like to have more involvement in the product selection process
  MPs would prefer to have vendor meet with MPs to validate vendor’s understanding of the requirements
Root Cause:
  ERCOT selected Serena Software’s Team Track tool as the replacement tool for FasTrak. ERCOT did not introduce the solution to MPs until after the requirements were complete and just before development efforts were to begin
Recommended Future Actions:
  ERCOT can provide more product demos earlier in the project process, where feasible, to allow MPs to gain a better understanding of the new product
  Early in the project lifecycle, ERCOT will conduct requirements validation sessions with MPs

## Slide 11: Improvement Area #5: Documentation
Theme: The project’s documentation did not meet the needs of the MP business and technical community
Focus Group Feedback:
  Version control lacking; must have version control of all documents
  Version changes not always easy to identify; any changes to project documents must be highlighted
  ERCOT must provide the proper documents for MPs to develop an API solution; providing ERCOT’s detailed design document is not the same as providing a Market Detailed Design document
Root Cause:
  ERCOT failed to obtain MP approval of templates for Market documents
  MPs did not define documentation requirements well
  ERCOT produced documentation that was not relevant to the MPs, which made MP development and training tasks difficult to complete
Recommended Future Actions:
  Market and ERCOT will agree to all document templates
  ERCOT will leverage a document versioning system to readily identify most recent version and to highlight changes from the previous version
  ERCOT will continue to use a project webpage to make documents available to MPs

## Slide 12: Improvement Area #6: Training
Theme: Training classes need to be timely and hands-on; need to incorporate all functionality of the tool
Focus Group Feedback:
  ERCOT should not conduct training until all testing is complete
  During training all functionality of the tool must be used (i.e. bulk insert)
  Training duration for a new tool needs to be extended and content needs to be more comprehensive
  Some training (i.e., MP administrators) should be mandatory
Root Cause:
  ERCOT was not able to provide hands-on training on all functionality of the tool due to environment and scheduling constraints
Recommended Future Actions:
  ERCOT will attempt to complete all testing prior to training start; milestones will be reflected and tracked via the project schedule
  ERCOT will attempt to ensure all product functionality is available and working for future training classes
  MP Steering Committee should define and implement “readiness” criteria to address minimum training required for MP to use a new tool (or revised tool)

## Slide 13: Improvement Area #7: Testing
Theme: Testing for selected functionality was not comprehensive, therefore, it did not produce desired results
Focus Group Feedback:
  Need better coordination and execution between ERCOT and MPs during development period to address issues prior to Market test
  Sandbox was not available long enough to allow MPs to develop and test their applications
  Would like to see an additional sandbox environment available for MPs to conduct testing and training activities
  Connectivity tests need to mirror NAESB testing process (“integration” test)
  Need better coordination between MPs and ERCOT for Market test script development
Root Cause:
  ERCOT and TTPT did not communicate and ensure understanding of needs for Market Test
  Lack of understanding resulted in changes to testing scope, schedule, and scripts
Recommended Future Actions:
  RMS (or MP Steering Committee) to engage TTPT and ERCOT Test Team in defining test action plan (scope, schedule, scripts), based on project complexity and timeline

## Slide 14: Contacts
Adam D. Martinez
Manager, Market Operations Divisional Projects Organization
ERCOT
(512) 248-3883
amartinez@ercot.com
Scott Egger
Business Analyst, Market Operations Divisional Projects Organization
ERCOT
(512) 248-3162
segger@ercot.com