## Slide 1: Market Coordination Team Update Retail Market Subcommittee February 14, 2007 Susan Munson Retail Market Liaison

## Slide 2: Project Schedule
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 3: Risks / Issues
Issue | Mitigation | Owner
PR50121_07 RBP – Stabilization necessary for successful implementation | Schedule management Milestone completion | ERCOT
ERCOT February Retail Release | Schedule and resource management Milestone completion | ERCOT
PUCT Mandate of 07/01/2007 poses tight timeline | Schedule and resource management Milestone completion | All
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 4
PR40038_01 Status
Status:
  On target for schedule, budget, and scope
Project Phases:
  Initiation – Completed
  Planning – Completed
  Execution – Mandated completion date July 1, 2007; Go-Live 06/24/2007
  Closing – Target completion is post go-live
Recent Activity:
  Complete Exception Handling Requirements (ETS, Reprocessing, ODS, other Tools)
  Began Review of Detail Designs
  Started monthly MCT progress reporting to RMS
  Finalize Core Detail Designs (TIBCO, ODS, Paperfree/NAESB, Siebel, TML)
  Emergency Change Control 2007-704 approved for inclusion in Texas SET 3.0
Next Steps for ERCOT:
  Finalize ETS and Reprocessing Detail Designs
  Complete Test Plans, Scripting, and Data Prep
  Set Up Test Environment
  Complete Core Build
  Migrate to iTEST
Next Steps for MCT:
  Continue to monitor Market issues and progress
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 5: February Status Reporting - CRs
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 6: February Status Reporting - CRs
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 7: February Status Reporting - CRs
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 8: February Status Reporting – ERCOT and TDSPs
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 9: Market Risk Questions
MPs responded to the following questions:
1.) Have you identified any risks that will prevent your company from beginning testing on time (Connectivity Testing for Flight 0407: March 20, 2007)? Please describe any risks.
2.) Have you identified any risks that will prevent your company from implementing on time (June 23, 2007)? Please describe any risks.
All MPs reporting responded ‘NO’ to both questions.

## Slide 10: CRs Not Reporting Progress for February
Ambridge Energy
Current Power and Light LLC
MS Retail Development Corp
NV Power LP
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 11: Texas SET 3.0 “Roadshow”
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO
Suggestion
  from TTPT leadership at January RMS was to hold a ‘change session’ for Texas SET 3.0 and future version releases, similar to what was done for MIMO. Delivery by ERCOT (Market Liaison)
Action Item
  ERCOT took action item to review feasibility with ERCOT management and return to RMS in February with recommendation
ERCOT Analysis
  ERCOT mgmt supported concept, if requested by Market and delivery is appropriate within project timeline and budget constraints
  MCT expressed concerns regarding possible cost to project and value to Market Participants at this stage of the project
  ERCOT estimated possible minimum cost estimate of $16K using following assumptions:
    Hold two one-day sessions in 3 locations: Austin, Dallas, Houston
    Held at ERCOT and MP facilities
    Up to two ERCOT SMEs to develop and deliver sessions

## Slide 12: Texas SET 3.0 “Roadshow”
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO
Recommendation from MCT and ERCOT for Texas SET 3.0
  Do not hold ‘change sessions’ at this time, but ensure Market Participants are made aware of location of necessary information for implementation
Recommendation for future Texas SET version upgrades
  For future Texas SET Releases, MCT and ERCOT will evaluate the necessity of having an Information Session in an open house format. The appropriate time for this event will be after Market Requirements are finalized and Texas SET Redlined Implementation Guides are published

## Slide 13: Emergency Change Control approved for Texas SET 3.0
2007-704 Approved by Texas SET on 2/5/07:
  When updating the 814_03 implementation guide for TX SET 3.0, the PER~IC segment was overlooked. This segment is required if the 814_03 is associated with a Switch (814_01), Drop to AREP (814_10), or Move In (814_16). Since ERCOT will not have customer data to populate in this field for a Mass Transition 814_03, ERCOT will populate the PER~IC with the value of Mass Transition Customer
In Mass Transition 814_03s,
  PER~IC~MASS TRANSITION CUSTOMER

## Slide 14: Changes to Market Requirements – January MCT
B. Mass Transition Detailed Requirements – p.11
“outlined in Protocols Section 15.1.2.9 (Replaced text: 15.2.1.9) Mass Transition”
Ts & Cs Requirement 3: - p. 22
“867_03 cancel and re-bills that happen after Version 3.0 but are for estimated billing periods prior to Version 3.0 will contain the REF~5I segment. TDSPs will send 867_03s Version 3.0 with a REF~5I segment that includes a value of "D10" reason code (Other) in the REF02, an explanation will be populated by the TDSP to prevent TX SET validation errors for this segment and the Estimation counters will be populated with “0” (Replaced text: the reason explanation of "Before V3.0", and Estimation counters of "0“).”
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 15: Changes to Market Requirements since January MCT
Change Control 2007-704
Added #24) to section B. Mass Transition Detailed Requirements
  Currently the PER~IC Name element is a required data field for all 814_03 Enrollment requests, therefore when ERCOT generates the 814_03 Enrollment for a Mass Transition (BGN07=’TS’) this required data element (PER~IC PER02) will be populated with ‘Mass Transition Customer’. Change Control 2007-704 was approved for inclusion by TX SET during an Emergency Change Control Call on February 5, 2007 to fulfill this requirement.
  Transactions Affected: 814_03
  MP Segments Affected: ERCOT and TDSPs (both IOU and MOU/EC)
  Change Control Required? Y/N Y
  Change Control Number: 2007-704
Mass Transition Timelines added as Appendix E
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 16: Reminder: Where are Texas SET 3.0 Key Documents Kept?
  MCT page – ERCOT.com
  http://www.ercot.com/committees/board/tac/rms/mct/index.html
  And what is there?
  Texas SET Version 3.0 Requirements Final Version 1.9
  Texas SET 3.0 - MCT Issues & FAQs Log
  Texas SET Version 3.0 Change Controls
  Texas SET Guides Version 3.0
  Texas SET Version 3.0 Implementation Plan DRAFT
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 17
Meeting Dates and Locations 2007
  February 21 – ERCOT Met Center
  March 28 – ERCOT Met Center
  April 25 – Location TBD
  May 23 – Location TBD
  June 27 – Location TBD or Conference Call
  July 25 – Location TBD
(Note: all meetings are held in conjunction with TX SET meetings)
Future Meetings/Market Communications
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 18: ERCOT Contacts
ERCOT Project Manager ERCOT SR. Business Analyst
Hope Parrish Jennifer Frederick
hparrish@ercot.com jfrederick@ercot.com
512-248-6522 (w) 512-248-6733 (w)
512-771-9582 (c) 512-413-0815 (c)
ERCOT Market Liaison
Susan Munson
smunson@ercot.com
512-248-3881 (w)
512-826-0564 (c)
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 19: Questions?
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO