## Slide 1: ERCOT Outage Evaluation & Resolution Phases I & II PR 60006_01 Project Update Retail Market Subcommittee February 14, 2007 Adam D. Martinez Mgr, Market Operations DPO

## Slide 2: Current Activities
Testing Status as of 02/12/2007
  Successfully tested 147 of 148 Market Participants, 17 of 18 entities
  1 open issue related to 1 entity
    ERCOT is working with MP to resolve the issue
Production Migration Status as of 02/12/2007
  Production migrations started 01/30/2007
    Originally scheduled for 01/08/2007
    Delays due to resource constraints and exacerbated by Jan. ice storm
  Scheduling of MPs for Production Migration continues
    Scheduled for Production: 140 of 148 Market Participants, 12 of 18 entities
  Migration window is scheduled to complete 02/16/2007
  Start of metrics collection against new environment delayed until 02/16/2007
  Old NAESB URL will be disabled, as planned, on 02/28/2007

## Slide 3: Questions / Contact
Adam D. Martinez
Manager, Market Operations Divisional Projects Organization
ERCOT
(512) 248-3883
amartinez@ercot.com