## RMR
Document Name: | Texas Nodal Model Management System CSD
Issuing Entity | Name | Page Number | Description | Accepted / Rejected | Reviewer | Reason
TXU | David Bogen | 15 | I have experienced performance problems using Citrix. If there is a way of providing a solution that does not include Citrix I believe the product will perform better and have improved usability. If Citrix | Response | John Moseley | . Item added to the IDA punchlist
TXU | David Bogen | 21 | This is no where in this section that it defines the testing environment for a project that the MP can use for validation proposes before submitting a project. | Clarification | John Moseley | Operational Phase one validation may be done prior to submission. Additionally, the project will not submit unless it passes phase one validation. Subsequent validation requires a full model implementation, and internal ERCOT testing. There is a market test period that occurs after ERCOT internal validation as defined in the protocols. ERCOT is planning to provide the models to MPs under the given protocol timeperiods for MPs to test on their systems.
TXU | David Bogen | 34 | Should include MPs as a user. (Of the Siemens Operational Test System) | Rejected | John Moseley | The NMMS is not scaled for this level operational testing, nor can the AREVA model be loaded and viewed externally. This item is outside the scope of the NMMS project.
TXU | David Bogen | 31 | Need the capability to attach a file the is the narrative describing how the scheme operates. | Clarification | John Moseley | This is the description of the SPS manager used to store the EMS SPS/RAP definitions. The narrative used to model these are in the SAMR submittal and can be attachements to the SAMR submittal. This will be elaborated in more detail in the detailed design
TXU | David Bogen | 13 | Each data flow path should show a two tier submission process for the Market Participants. First tier would be data entry and validation of changes by the Market Participant. The second tier is the actual submission of the verified changes by the Market Participant. | Clarification | John Moseley | This is the currently described process. MP will submit data, ERCOT will validate and post to the MIS website for the market test. The next tier if for internal ERCOT testing of the model changes
TXU | David Bogen | 10 | Each Market Participant should also be allowed access to a suite of applications for verify the validity of the data that is being submitted. This should be true for both Planning and Operations changes. | Response | John Moseley | Operational Phase one validation may be done prior to submission. Additionally, the project will not submit unless it passes phase one validation. Subsequent validation requires a full model implementation, and internal ERCOT testing. There is a market test period that occurs after ERCOT internal validation as defined in the protocols. ERCOT is planning to provide the models to MPs under the given protocol timeperiods for MPs to test on their systems.
TXU | David Bogen | 8 | The project tracker also need to provide for the attachments of files that contain drawings other documents that might be required for the project. The PTC must also provide a feature to update information already submitted and to update service and completion data for each project. | Rejected | John Moseley | The Project Tracker is the module that tracks the NOMCRs, the changes described here can be viewed at the Project Tracking Level, but the changes need to be made at the NOMCR level. Additional tools will be available (as they are today in MOTE) to review data submitted and ask for additional testing. ERCOT is not planning to make available the network analysis toolset. In a submission of a NOMCR you can attach files that further describe the NOMCR. Additional clarifications will be provided in the detailed design
TXU |  | General | The CSD does not state NMMS will produce topology only, not complete load flow models. This may cause confusion on the part of others who review this document. | Clarification | John Moseley | The NMMS system will be able to produce "snap shot" load flow models using the information from the approved SSWG base cases. Additionally, a SAMR can be submitted with any additional data that MPs would like ERCOT to review. The functionality of the NMMS will produce topology and load flow models depending on the subset of applications within NMMS.
TXU |  | General | The CSD seems to imply PMCRs are the same as IDEVs. Is this correct? If not, the wording should be changed. The contents of the PMCR are not well defined. Where and when will the definition be provided? We like the proposal to permit the use of IDEVs, Python, GUI or RAWDs to create PMCRs, but are unsure how this will work since the PMCRs appear to contain information that is not part of the load flow data input supported by IDEVs, Python and RAWDs. | Clarification | John Moseley | An IDEV is one of several formats of information that may be attached to a PMCR. Further definitions of the submission lay layout will be provided in the detailed design
TXU |  | General | The test bed/sand box to be used by TSPs to validate PMCRs is not well defined. This is an important feature from the TSP planner’s perspective. | Clarification | John Moseley | NMMS detailed design will seek to explain that functionality in more detail
TXU |  | General | The requirement to upload the completed DSA cases is not described. The process for turning these cases into the monthly CRR cases with the appropriate topology, bus load, voltage tuning and generation is not described. | Clarification | John Moseley | The DSA case will not be uploaded to the NMMS. The results from the DSA will be unloaded, i.e. load/generation pattern, settings, snap shot.
TXU |  | General | The requirement for NMMS to possibly produce the TPIT report is not described in the CSD. Can the requirement be included before the details for inputting the information and producing TPIT are developed? Further comments on this proposal will be provided in response to Doug’s e-mail. | Accepted | John Moseley | The inclusion of TPIT information in the submission process will be moved to IDA punchlist and followed up at Detail design
TXU |  | General | The decision on what projects go into the base cases rests with ROS, not ERCOT Planning. The rules for producing the 14 base cases that include the five Annual Planning Model cases are in the SSWG Procedures. The SSWG Procedures are approved by ROS because SSWG is a ROS working group. If ERCOT Planning wants a modified set of cases, NMMS might be able to produce these modified cases if it is designed to do so. This will probably require uploading all 14 SSWG cases into NMMS so the modified cases will have bus load, voltage tuning and generation. There may be problems with this if projects that affect bus load or generation are ones ERCOT Planning wants to delete. | Clarification | John Moseley | This CSD deals more with the functional role, rather that the regulatory one. ERCOT planners will build cases under the same criteria as they currently do today. Additional details on the business process will be provided in detailed design
TXU |  | General | The dashboards shown appear to be functional, but the true test will come when TSPs and ERCOT have hands on trials in December and January. Some specific comments are embedded in the pages that show the dashboards. | Accepted | John Moseley | ERCOT welcomes member input into the design of the dashboards. Since this functionality will be new, ERCOT will work with MPs to develop a design that will work best with MPs.
TXU |  | General | No one has discussed the TAC approved resolution calling for the full development of NMMS and the deferral of using it to produce cases beyond 2.5 years into the future. ERCOT shall proceed with the conceptual design development of an NMMS as described in the NMMS Business Requirements document subject to modification of the operational and planning functions developed through detailed design discussions between ERCOT and the Market Participants. ERCOT will schedule and conduct these discussions to accommodate the nodal market implementation timeline. ERCOT shall plan for an NMMS implementation to accommodate both a NMMS implementation that accommodates the timing needs of the CRR auctions (approximately 2.5 yrs) followed by an implementation over a 5 yr transmission planning horizon. This resolution probably should not be in the documentation, but it affects the deployment of NMMS and other activities associated with base case development and the production of TPIT by NMMS. | Accepted | John Moseley | NMMS is scaled to handle what ever business process is required. Whether its 2.5 or 5 the setup of NMMS is the same
TXU |  | General | The proposal for the ERCOT staff to check PMCRs is problematic. During the creation of the 14 SSWG base cases, hundreds of new or modified PMCRs will be created over a short period of time. This deluge of PMCRs will very likely overwhelm the ERCOT staff and could lead to delays in creation of these cases. | Accepted | John Moseley | More planning staff may be required to review. Business procedure will need developed to help mitigate this possibility. ERCOT will be evaluating the business need and will respond appropriately
TXU |  | General | The existing e-mail system has failed both the ERCOT staff and the TSPs. Relying on it to successfully communicate NMMS messages is risky. Will a more reliable system be used by NMMS? | Accepted | John Moseley | ERCOT will also use a messaging system via web services and a notification service on the dashboard to alert MPs about issues
TXU | Mike Juricek |  | Presently, the DSA and DSB base cases and submitted IDEVs are posted on the Operations and Planning website that requires an ERCOT assigned logon ID and password. NMMS and the PMCRs and NOMCRs should be stored on a similar website. The users of NMMS and the load flow data should not be required to pay for digital certificates or some other security system to gain access to the load flow data. This data is made available to any legitimate requestor, so the security for the load flow data should be consistent with access provided to this data. | Accepted | John Moseley | ERCOT System Planning is currently designing a site to accommodate the posting of PMCRs. NOMCRs are to be posted per the Protocols.
TXU | Mike Juricek |  | How will NMMS be upgraded to match changes to PSS/E and other software it supports? We currently have upgrade issues with our internal database system caused by annual changes to PSS/E and the RAWD file. NMMS will be subject to these same issues since it relies on the structure of IDEVs and the RAWD file. | Clarification | John Moseley | Our vendor for the MOD is PTI, they will upgrade thru a service contract. ERCOT planning will move forward together.
TXU | Mike Juricek |  | Will NMMS be stored at both ERCOT and a remote site for disaster recovery? This is not a big issue today because the TSPs have copies of the DSA and DSB cases and can repopulate the ERCOT load flow database should ERCOT lose all of its computers due to a disaster. We will not have a copy of NMMS. | Accepted | John Moseley | Yes, we will have the same level of availability as the EMS
TXU | Mike Juricek |  | The current SSWG load flow base case update process involves TSPs providing ERCOT with IDEVs to modify the existing cases or RAWDs to totally replace a TSP’s system in the existing cases. This occurs in several passes for DSA and DSB. SSWG then meets to review the cases and makes additional changes using IDEVs. In some instances, the TSPs perform another in-house review after the SSWG meeting. If NMMS is used to create these cases, it appears all of the IDEV work be replaced by PMCRs. Can NMMS quickly process all of these PMCRs and quickly import and export the cases with load and generation? The SSWG meetings may be held in Taylor, the Met Center or another location. Can NMMS be accessed from remote sites? | Clarification | John Moseley | An IDEV is one of several formats of information that may be attached to a PMCR. MPs will be able to access NMMS through the internet explorer.
TXU | Mike Juricek |  | You could add a definitions subsection in Section #1 to define NOMCR, PMCR and SAMR instead of covering the definition in other subsections. I believe the only models described in the Nodal Protocols are Network Operations Model, Annual Planning Model and CRR Auction Model. These terms should be defined in Section #1 and always be used when referring to these models. The others models created by NMMS such as EMS/OTS model and planning models also should be defined in Section #1. This would help the reviewers understand the different models that are needed. The drafters of the Nodal Protocols apparently were unaware of the entire set of network models needed to meet all of the requirements. | Accepted | John Moseley | Such a table will be added in the next release to explain that all methods of changes to the model are NOMCRs and the subsets are PMCRs, SAMR, and Real time changes
TXU | Mike Juricek |  | I believe the model names used in the Nodal Protocols were not consistently used in the CSD and the use cases. Some members of TPTF could react negatively to this when they review the documents. | Accepted | John Moseley | We will be consistent with the Nodal protocols and elaborate the definitions in the detailed designs
CPS | Gurrala, Sharmila |  | On page 16 of the CSD document it states "With each S/W delivery, appropriate H/W will need to be setup and configured at ERCOT so that maximum usage of the S/W can be achieved." We are not sure what S/W and H/W stands for, it would be helpful if you include Acronyms in the document. There is one more comment which I included in the Document on page 17th. We are still going through Use Cases. I will mail you if we have any comments. | Accepted | John Moseley | Such a table will be added in the next release. S/W is software H/W is hardware
LCRA | Brad Woods |  | 1) When does ERCOT plan to provide LCRA Planning an Operations case in the PSSE format from NMMS to use to developed the IDEV needed to convert the LCRA Operations case to an LCRA Planning case (I couldn't tell from your Delivery Schedule)? I assume the operations case from NMMS will have all substations condensed down to one node and the conversion tool will need to add/remove buses as needed for planning. | Clarification | John Moseley | ERCOT should have this in by June, the topology processing will be based on the needs of the individual planning organizations.
LCRA | Brad Woods |  | 2) Will the conversion tool need to also add the correct bus number or will NMMS use the data dictionary to spit out an operations case with the planning bus numbers? | Clarification | John Moseley | We will have an internal data dictionary for this function with the initial content reviewed by Market Participant members.
LCRA | Brad Woods |  | I would like to see a different form for submitting PMCR's. I think it would be easier for everyone to keep track of their projects and would be less work if the TPIT information and the information for PMCR's could be combined. If a new project is to be submitted, then it could be submitted in the TPIT format. It would be added as a new listing for the TPIT and contain the information needed for the PMCR. The TPIT could have a PMCR column that has the possible options of "Submitted for Approval", "Approved", etc. This will help everyone keep track of which projects have been submitted for PMCR approval. This way we have one form to fill out and maintain for all projects. If the PMCR's and TPIT information is not together, then you have to fill out the information for each new project twice and you have no way of determining if a PMCR has been submitted for the project by lo! oking at the TPIT. If the project changes (scope, energize date), the TPIT and the PMCR information will need to be changed. NMMS is being developed because we couldn't keep the same information for the same projects in different locations consistent. | Clarification | John Moseley | NMMS is currently looking into the incorporation of the TPIT information and will provide more definition of this process in the detailed design
CPS | James A. Boston |  | Can we link the Traceability to Requirements (found in the Functional Specification section) to the actual requirements in PR50142 by listing the requirement numbers it affects? I don’t know if this would be too time consuming or even helpful to all. | Accepted | John Moseley | This will be included in the detailed design
CNP | Ebby John |  | When ERCOT was in Houston we provided comments that NMMS needed some way to group NOMCRs that are related to a single NOMCR. If this was not done, then all the NOMCRs related to a single PMCR would have to be submitted at the same time to avoid downstream data errors. For example, if first of multiple NOMCR is submitted and the appropriate PMCR is referenced, then either the PMCR is converted and archived or remains active. Either way there is a data integrity problem. The usecase language has “The PMCR stays in the project list unless the MC confirms that the PMCR conversion is complete or the PMCR in-service date is at or beyond the deadline for project submission of a NOMCR”. How is this done? For incomplete PMCRs, both the PMCR and NOMCR exist at the same time. Is the incomplete set of related NOMCRs somehow on “hold” and not used to build models. I just want to ensure this concept is captured in the design. Submitting all related NOMCRs at the same time is burdensome and unacceptable and also increases our NOMCR submittal timelines for long projects. | Accepted | John Moseley | We revised the CSD to include the concept of a project which can contain one or more NOMCRs and the project will be referenced to the PMCR. The project will be marked as complete when all the NOMCRs have been submitted, and the PMCR at that point will be archived.
CNP | Ebby John |  | It seems what is required is in addition to the “Original PMCR” selection in the NOMCR form, there also needs to be a “PMCR complete” check box. Until a PMCR is complete, all related NOMCRs that are linked to this PMCR id should be in an “inactive state” until the final NOMCR marks the PMCR complete. Once the PMCR is complete, it can be officially converted and archived. | Accepted | John Moseley | We revised the CSD to include the concept of a project which can contain one or more NOMCRs and the project will be referenced to the PMCR. The project will be marked as complete when all the NOMCRs have been submitted, and the PMCR at that point will be archived.
TXU |  |  | COMMENT: Will MOD have the same features as SHIMM for validation, audit trail, report generation and automatic display generation?} | Clarification | John Moseley | Not the same features, but PTC and MOD will have some validation capability
TXU |  |  | {COMMENT: If this is the feature that converts the node-branch operations model to the bus-branch planning model should the description be expanded to describe this conversion?} | Accepted | John Moseley | Moved to IDA punchlist and followed up at Detail design
TXU |  |  | {COMMENT: Should the test bed or sand box be described here ?} In the Market Participant Interface | Clarification | John Moseley | The functionality incorporated into the test bed will be based on currently available features of the core NMMS software
TXU |  |  | {COMMENT: At the Forum meeting, ERCOT discussed uploading the completed and tuned DSA base cases into NMMS to be used to create the monthly CRR cases with bus loads and generation. If this is the plan, should the data flow diagram show a flow from System Planning to NMMS?} | Clarification | John Moseley | The DSA case will not be uploaded to the NMMS. The results from the DSA will be unloaded, i.e. load/generation pattern, settings, snap shot.
TXU |  |  | {COMMENT: How is the PMCR description to be evaluated without a model of the PMCR to test with? What is done during the evaluation?} | Clarification | John Moseley | The ERCOT Planner will incorporate the change into a model and solve a power flow
TXU |  |  | {COMMENT: How will ERCOT address TSPs’ concerns about performance issues related to using Citrix?} | Clarification | John Moseley | See Above
TXU |  |  | {COMMENT: Will PTC handle RAWD’s that contain data for a whole Area?} | Clarification | John Moseley | In theory, not a recommended course but NMMS should be able to handle such an upload. Business procedures at a local level may need reviewed to determine the ramifications of this action
TXU |  |  | Concerning the PTC GUI {COMMENT: The title of the PMCRs, NOMCRs and SAMRs should be more descriptive so the user can more easily identify them.} | Accepted | John Moseley | Moved to IDA punchlist and followed up at Detail design
TXU |  |  | {COMMENT: Will search capability be provided?} | Accepted | John Moseley | Moved to IDA punchlist and followed up at Detail design
TXU |  |  | {COMMENT: The project types do not match the text description of a SAMR in an earlier section.} | Accepted | John Moseley | Moved to IDA punchlist and followed up at Detail design
TXU |  |  | {COMMENT: The user should be able to select PMCRs using a date range in addition to manual selection. I do not see this capability on figure.} | Accepted | John Moseley | Moved to IDA punchlist and followed up at Detail design
TXU |  |  | {COMMENT: Where is the control for the test bed/sand box?} | Clarification | John Moseley | The functionality incorporated into the test bed will be based on currently available features of the core NMMS software
TXU |  |  | {COMMENT: Will the other users of NMMS be able to generate reports? These reports could be helpful in checking NOMCRs and PMCRs.} | Clarification | John Moseley | Currently all report generation will be done internally by ERCOT staff and reviewed before release to outside market participants
CNP |  | General | CIM Issues: Assignment of Master Record ID (MRID) for Electrical network elements: Suggested proposal may have problems. Asset owners should have first right to assign such IDs and register the IDs for ERCOT’s and MP use. See comments below. The concept as described should be further refined. | Accepted | John Moseley | ERCOT has no issue with the proposed change, acceptance of other TSPs to have ERCOT basically dictate IDs will be necessary. This is a business process and is not an intergrated part of the CSD. ER OT will clarify on the detailed design
CNP |  | General | CIM Issues: Assignment of Master Record ID (MRID) for Electrical network elements: Suggested proposal may have problems. Asset owners should have first right to assign such IDs and register the IDs for ERCOT’s and MP use. See comments below. The concept as described should be further refined. There are several references to various sections of IEC 61970 standard, and other references that point to inadequacies in the standard. There were no details on the model extensions needed to fully support NMMS requirements. As a MP should I assume that model extensions will only affect ERCOT internal systems? | Clarification | John Moseley | If the MP chooses to submit CIM XML files generated by their system that are different from the NMMS design, there will be a functional and business impact on the Market Participant and ERCOT. The model extensions will affect the ERCOT system but are required for proper data submittal.
CNP |  | General | CIM Issues: There are several references to various sections of IEC 61970 standard, and other references that point to inadequacies in the standard. There were no details on the model extensions needed to fully support NMMS requirements. As a MP should I assume that model extensions will only affect ERCOT internal systems? | Clarification | John Moseley | It will only affect ERCOT if you choose not to use the CIM/XML files for model changes and updates - If the MP chooses to submit CIM XML files to ERCOT or to download and use CIM XML files from ERCOT and those files contain changes that must use the CIM extensions, they there will be an impact to the MP.
|  |  | PMCR & and how to meet model consistency requirement between Operations and Planning models:Implementation, as described in CSD may be a source of unforeseen errors in the model if PMCRs , NOMCRs, and SAMRs are not adequately managed. It may be practical to allow the co-existence of a given change in both NOMCR and PMCRs but restrict the use of PMCRs to Planning Models outside of the protocol defined data submittal window. | Accepted | John Moseley | Agreed, they will be adequately managed. PMCR that are dated for implementation within the appropriate NOMCR period will be either converted, changed (the implementation date) or removed from the system. If is not practical to allow the co-existence of a PMCR change within the 90-day implementation period.
CNP |  | General | CRR model and Planning Models appear be used interchangeably. Although CRR models are exchanged as PSS/E files, Planning models have a precise meaning in ERCOT. E.g.. In figure 1 of the NMMS CSD the box referred to as “Planning Model Manager” is really a CRR Model manager. Planning Models are managed directly by SSWG. | Clarification | John Moseley | No, it is not a CRR Model Manager. This is a Planning Model Manager that is used to create Planning Models for the CRR group or the Planning departments (ERCOT or MPs). If an MP does not want to use this facility to generate their planning models, they do not have to; however, the ERCOT planning group does plan to use this facility to generate some Planning Models – or at least they will have the option to do this. Planning Models will continue to be managed by SSWG, the information will be stored in NMMS
CNP |  | General | Use of Web Services to submit NOMCR, PMCR, SAMR: Since ERCOT has settled on using IEC 61968 message structures, there is no reason not to create a suit of web services that can exchange Model change payloads/status messages directly to/from NMMS, rather than via a web client login. There are several benefits to both ERCOT and Market Participants | Rejected | John Moseley | The NMMS team is working with the ERCOT internal integration team to look at the possibility of using a Web Service as one of the submission methods. Since the 61968 standard has not developed a message for this type of submission, the 61968 standard probably will not be used to accomplish this. However, we believe we can leverage the “message structures” defined in this standard. In our discussions with the integration team they have clarified their use of the 61968 standard as follows: “No vendors are going to produce 61968 messages. Any message definitions or APIs from these vendors for this project [that we have seen] so far are NOT CIM compliant in any way, shape or form (with the exception of RDF of course). If any vendor does define a message or an API that uses CIM for payload definitions we can readily use it.Internally, we are looking at using the IEC 61968 message structure. [We] even want to use this for the external web services we are working on now. Where we can, we will try to use CIM classes in payload definitions. The things from the CIM that we will certainly leverage in our messages are curves and schedules. If there is more we can leverage, we will try it where appropriate.”
CNP |  | General | NMMS’ outage scheduler interface should be limited to providing valid equipment list to the outage scheduler database. Section 2.10 of the CSD appears to suggest a complicated requirement. The nuances of incorporating outage schedule to a any model should be left to end user application or systems (e.g., Power flow /SE on EMS, Planning applications, CRR etc.) Outage scheduling validation should be left to the outage scheduler application. | Clarification | John Moseley | The NMMS passes a list of equipment and current projects to the outage scheduler, the OS passes a list of submitted outages to the NMMS case builder to allow the Model builder to incorporate outages into the model. Interfacing between the 2 systems will be clarified in the detailed design
CNP |  | General | Differentiation between ERCOT’s implementation choice and dictates of the Nodal protocol. See suggested changes in the last paragraph of the Overview Section of the NMMS CSD. | Rejected | John Moseley | ERCOT plan forward have been communicated with MPs through the stakeholder process and ERCOT will change its position if the Nodal protocols are changed. However at this time the current methodology is what ERCOT is planning to develop going forward
CNP |  |  | Due to differences in informational content, the Network Model Change Request (NMCR) is divided into three separate data submission. First, is the Network Operations Change Request (NOMCR) which is used to submit changes to the Network Operations Model. Second is the Planning Model Change Request (PMCR) which is used to submit changes for use in the ERCOT planning models. Finally, there is the Special Action Model Request (SAMR) which is used to submit operational information including contingency definitions, special protection schemes, line rating methodologies, etc. All three of these modeling requests are subsets of the proposed implementations “Management Activities for ERCOT System” as described in the ERCOT nodal protocol | Accepted | John Moseley | We agree that all three are subsets of the NOMCR process as described in the protocols. In the detailed design ERCOT will clarify the definitions of the PMCR, SAMR, and real time operational model for clarity and reference back tot eh protocols
CNP |  |  | COPS.P01.ModelManageData_UCConvertPMCR2NOMCR_V0.9.doc – Use Case to Convert a PMCR to a NOMCR (PMCR management within operational model is still and issues. ERCOT’s implementation here will create management issues in dealing with the contents of NOMCR versus PMCR. The role of PMCR in non-planning areas of operation is still not clear) | Clarification | John Moseley | PMCRs have functionality in the CRR process and planning process. The inconsistant data issue is due to business processes and not the software functionalty, and should probally be addressed as such.
|  |  | COWM.P05.ConductCRRMarkets_UC_CreateCRRSettlementFile_V04.doc – Use Case to Create a CRR Settlement File that corresponds to the Planning Model for the CRR System (This appears to be an SSWG task) | Rejected | John Moseley | No, the SSWG will not be creating the Settlement File. NMMS will create the data needed by settlements through the interface design and build
CNP |  |  | CPPS.P01.PlanFutureBaseCase_L4_CreatePMCR_V0.3_accepted.vsd – L4 Swim Lane Diagram that graphically defines the Create PMCR process (This is supposed to be a baseline model sent to TSP planning departments. Other than the time interval, and the number of project packets, is this process any different from creating any other planning model?) | Clarification | John Moseley | The difference is the part of data submission, and possibility a more robust reporting process
CNP |  |  | Figure 1 - NMMS Conceptual System Design Should “Planning Model Manager” be CRR Model Manager?” | Clarification | John Moseley | No, these could be distiactly different roles.
CNP |  |  | NOMCR details in the PTC database include information such as the project classification, project statuses (e.g. submitted, approved, completed, rejected, in-progress (part of a string of NOMCRs), online, energized, etc.), and project summaries. This information supports project tracking and coordination functions and operational model changes. | Rejected | John Moseley | The changes suggested do not follow Protocol requirements and thus the functionality described in the NMMS solution
CNP |  |  | ERCOT need to review this functionality against SSWG’s current practice. Our understanding is that NMMS simply provides a common starting point (based on the operational model) for the TSP Planning departments. SSWG then expends significant effort in creating the annual/seasonal models used by ERCOT’s transmission planning and other market participants. Additionally, the short circuit and dynamic models are handled separately. | Clarification | John Moseley | Currently only steady state model data necessary to support planning will be housed in the planning section of NMMS
CNP |  |  | It is assumed that the generated PSSE file is a steady-state power flow model? | Accepted | John Moseley | Correct
CNP |  | General Model Building Comment | These models are limited by the data submittal windows? | Clarification | John Moseley | You can create a model for any point in time based on the data submitted. As newer data is submitted, the model will change.
CNP |  |  | Market Participant interface should include web service or other programmatic methods that would allow the submittal of NOMCR, PMCR, SAMR etc. This will minimize duplicate entry of changes in MP systems and ERCOT’s NMMS. ERCOT’s API group appears to be settled on using IEC 61968 message structure as standard mechanism for system to system message exchange. Web services can be defined to allow this exchange to happen. The good side is that it would allow a MP submit batch changes to ERCOT and minimize load on the thin client interface. | Clarification | John Moseley | The NMMS team is working with the ERCOT internal integration team to look at the possibility of using a Web Service as one of the submission methods. Since the 61968 standard has not developed a message for this type of submission, the 61968 standard probably will not be used to accomplish this. However, we believe we can leverage the "message structures" defined in this standard. In our discussions with the integration team they have clarified their use of the 61968 standard as follows: "No vendors are going to produce 61968 messages. Any message definitions or APIs from these vendors for this project [that we have seen] so far are NOT CIM compliant in any way, shape or form (with the exception of RDF of course). If any vendor does define a message or an API that uses CIM for payload definitions we can readily use it.Internally, we are looking at using the IEC 61968 message structure. [We] even want to use this for the external web services we are working on now. Where we can, we will try to use CIM classes in payload definitions. The things from the CIM that we will certainly leverage in our messages are curves and schedules. If there is more we can leverage, we will try it where appropriate.”
CNP |  | 2.3.2 | The Planning Model Manager produces the planning models used by the Congestion Revenue Rights (CRR) system, Annual Planning Models, and the planning models used by ERCOT staff planners, as well as any other planning models required by SSWG. Verify this is accurate) | Clarification | John Moseley | The plan is that the SSWG and the ERCOT planners will begin with the Operational model contained within NMMS.
CNP |  | pg 25 in ref to PTC | What actions can be performed on the artifacts on this display (modify, insert, cancel, query?) Are there other drill down capability available on this display? | Clarification | John Moseley | Moved to IDA punchlist and followed up at Detail design
CNP |  | pg 26 in ref to PTC | How was this record selected from this display. How would you review another record? Is record copy allowed? | Clarification | John Moseley | Moved to IDA punchlist and followed up at Detail design
CNP |  | 2.10.2 | NMMS’ outage scheduler interface should be limited to providing valid equipment list to the outage scheduler database. The nuances of incorporating outage schedule to a any model should be left to end user application or systems (e.g., Power flow /SE on EMS, Planning applications, CRR etc) | Clarification | John Moseley | Per the receiving system requirements, the NMMS must be able to apply the outages selected by the operator to the model during model generation