## CBA_Dtl
Project Cost / Benefit Analysis Detail Worksheet
Project Information | [6 empty] | ß |  |  | Market: Enter source document for request (PRR or SCR)
PRR / SCR / PR / "New": | PRR707 | [8 empty] | ERCOT: Enter "New" if requesting a new ER number
Project Title: | Prioritization and Timing of Transactions Based Upon PRR672 Collaborative Analysis and Retry Process for 814_20s
Sponsor's Name: | ERCOT | Estimator: | Mansour/RMS | Estimate Date: | 2007-02-14
Senate Bill 7 Requirements
Indicate percentage that this project supports SB7 requirements:
Pct
| Access to transmission and distribution systems |  |  | 0%
| Reliability and adequacy of electrical network |  |  | 0%
| Customer choice of REP |  |  | 100%
| Accounting accuracy |  |  | 0%
|  | Total (Maximum 100%) |  | 100%
ERCOT Corporate Goals
Indicate percentage that this project supports each ERCOT corporate goal:
Pct
| 1 - Reliability and Congestion Management |  |  | 0%
| 2 - Retail Transaction Processing Success |  |  | 100%
| 3 - Wholesale Access, Settlement and Billing |  |  | 0%
| 4 - Management Systems and Business Practices |  |  | 0%
| 5 - Financial Management and Cost Effectiveness |  |  | 0%
| 6 - External and Stakeholder Affairs |  |  | 0%
| 7 - Organizational Readiness |  |  | 0%
|  | Total (Maximum 100%) |  | 100%
Assumptions
Assumptions Relevant to the Cost / Benefit Analysis of this Proposed Project
1 | This CBA addresses Prioritization and Timing of Transactions Based Upon PRR672 Collaborative Analysis and Retry Process for 814_20s. | [5 empty] | ß |  |  | Prioritize these by putting the most important at the top
2 | Ongoing support likely cannot be absorbed by current ERCOT staff. However, the FTEs described in ERCOT’s PRR672 Phase 3 Impact Analysis [Retail Customer Choice (2 FTEs)] could also perform the work requirements for this PRR. | [8 empty] | The top 4 will be displayed on the summary page
3 | PR- 50121_07 Retail Business Processes: Changes to the Retail Transactions applications in support of the TIBCO framework are currently in progress. Risk is high that resolution for testing and stability issues related to RBP will impact design and development work on this PRR.
4 | PRR672 Phase 1 resulted in a scope change to PR-40038 Tx SET 3.0 to include the prioritization of the processing of 814_16 Move-In Requests containing a priority code of anything other than null or 01. PRR672 Phase 2 Collaborative Analysis was managed as an O&M effort. PRR672 Phase 3 included Level 1 Priority Move Ins - to be processed within 1 retail business hour; Level 2 - Standard Move-ins and Move outs – to be processed within 2 retail business hours. PRR672 Phase 3 will be executed in a separate project, PR-60008 Terms and Conditions requirements, not limited to Texas SET changes. PRR707 is also to be managed under Project No. 60008_01.
5 | PRR672 Phase 1 CBA, posted on 08/09/2006, listed Total Cost of $1.5M and Total Benefits of $6.5M for a Benefit Cost Ratio of 4.3. PRR672 Phase 3 CBA, posted on 12/06/2006, listed Total Cost of $1M. PRR707 CBA lists Total Cost of $75K. Input from Market Participants indicates that the Phase 1 Market Benefits also apply to PRR672 Phase 3 and to PRR707. As a result, the combined PRR672 Phase 1, PRR672 Phase 3, and PRR707 Benefit Cost Ratio is positive, approximately 2.5.
6
7
8
ERCOT Cost / Benefit Detail
ERCOT Internal Cost |  | Year 1 | Year 2 | Year 3 | Year 4 |  |  |  |  | OPTIONAL WORKSHEET FOR CALCULATING COSTS - STAFFING
Implementation Cost | Cost to Implement: | 75000 | 0 | 0 | 0 |  |  | NPV = | 0
[10 empty] | Task / Item | FTE Cost ($/hour) | Expected Cost in FTE Hours Per Workday | Total FTE Hours Per Year | Estimated Cost = Total FTE Hours * FTE Cost | Workdays Per Year
Ongoing Cost (O&M) | Staffing: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Hardware: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Software: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Infrastructure | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Total ERCOT Implementation Cost: | 75000 | [10 empty] | Total | 0
| Present Value of ERCOT O&M Cost: | 0
OPTIONAL WORKSHEET FOR CALCULATING BENEFITS - STAFFING
ERCOT Internal Benefit |  | Year 1 | Year 2 | Year 3 | Year 4 |  |  |  |  | Task / Item | FTE Cost ($/hour) | Expected Reduction in FTE Hours Per Workday | Total FTE Hours Per Year | Estimated Benefit = Total FTE Hours * FTE Cost | Workdays Per Year
[11 empty] | 0 | 0 | 0 | 0 | 240
Direct Cost Savings | Staffing: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Hardware: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Software: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Infrastructure: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0
Productivity Increases | Time Savings: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  |  |  | Total | 0
| Other Increased Efficiencies: | 0 | 0 | 0 | 0 |  |  | NPV = | 0
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 | OPTIONAL WORKSHEET FOR CALCULATING BENEFITS - OTHER
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  |  |  |  | 0
Other Benefits | Cost Avoidance: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  |  |  |  | 0
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  |  |  |  | 0
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  |  |  |  | 0
| Present Value of Internal ERCOT Benefit: | 0
Market Cost / Benefit Detail
Market Cost |  | Estimated Market Cost | Market Segment | Number Impacted | Market Implementation Complexity
Implementation Cost |  | 0 | QSE | 100 | No Impact |  | ß |  |  | ERCOT Implementation Cost * Number Impacted * Complexity
(Based on ERCOT cost) |  | 0 | CR | 100 | No Impact
|  | 0 | TDSP | 6 | No Impact
|  | 0 | Resource | 175 | No Impact
| Market Implementation Cost: | 0
Ongoing Cost |  | Year 1 | Year 2 | Year 3 | Year 4
| QSE | 0 | 0 | 0 | 0 |  |  | NPV = | 0
| CR | 0 | 0 | 0 | 0 |  |  | NPV = | 0
| TDSP | 0 | 0 | 0 | 0 |  |  | NPV = | 0
| Resource | 0 | 0 | 0 | 0 |  |  | NPV = | 0
| Present Value of Ongoing Market Cost: | 0
OPTIONAL WORKSHEET FOR CALCULATING BENEFITS - STAFFING
Market Benefit | Impacted Market Segments | Direct Cost Savings - Per MP | Elimination of Manual Effort - Per MP | Other:(Per MP) | Other:(Per MP) |  |  |  |  | Task / Item | FTE Cost ($/hour) | Expected Reduction in FTE Hours Per Workday | Total FTE Hours Per Year | Estimated Cost Savings = Total FTE Hours * FTE Cost | Workdays Per Year
[11 empty] | 0 | 0 | 0 | 0 | 240
Benefits Quantified | QSE | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 240
by Participant | CR | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 240
| TDSP | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 240
| Resource | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 240
[11 empty] | 0 | 0 | 0 | 0 | 240
|  | Year 1 | Year 2 | Year 3 | Year 4 | [5 empty] | 0 | 0 | 0 | 0 | 240
| Direct Cost Savings: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Elimination of Manual Effort: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Present Value of Individual MP Benefit: | 0 | [10 empty] | Total | 0
Benefits for Market |  | Year 1 | Year 2 | Year 3 | Year 4 |  |  |  |  | OPTIONAL WORKSHEET FOR CALCULATING BENEFITS - OTHER
| Reduced Congestion Cost: | 0 | 0 | 0 | 0 |  |  | NPV = | 0
| Consumer Savings: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 | Item | Comment |  |  | Amount
| Transaction Cost: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  |  |  |  | 0
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  |  |  |  | 0
| Other: | 0 | 0 | 0 | 0 |  |  | NPV = | 0 |  |  |  |  | 0
0
| Present Value of Market Benefit: | 0
| Total Present Value of Market Benefit: | 0
Total Cost | 75000 |  | Net (Cost) - Benefit ($) |  | -75000
Total Benefit | 0 | Total Benefit / Total Cost (Ratio) |  |  | 0
Summary values are rounded to 2 significant digits.
Objectives Detail
Score
IMPLEMENTATION REQUIREMENT: Is the project required to support a PUCT rulemaking or government requirement? Is the project required by an ERCOT committee? |  |  | 2 - Does not have a defined implementation date |  |  |  | ß | 2 |  | Select from dropdowns for each category
RELIABILITY: Does the project improve ERCOT's reliability performance? Is there a significant operational need for the project? |  |  | 2 - Addresses existing, low impact issue |  |  |  | ß | 2 |  | Select from dropdowns for each category
SECURITY: Does the project improve ERCOT's security? Is there a physical security, cyber security or safety issue that is addressed by this effort? |  |  | 0 - No impact on security |  |  |  | ß | 0 |  | Select from dropdowns for each category
DATA MANAGEMENT: Does this improve the accuracy, timeliness and transparency of transactions/settlements related to date received from, managed and delivered to the market? |  |  | 3 - Addresses existing, moderate level issue |  |  |  | ß | 3 |  | Select from dropdowns for each category
EFFICIENCY: Does the project improve the efficiency/effectiveness of ERCOT? Does the project automate, improve and/or streamline a necessary function? |  |  | 3 - Spans multiple areas and partially addresses the function |  |  |  | ß | 3 |  | Select from dropdowns for each category
REQUIREMENTS: Are the high level requirements clearly defined? How complex are the potential solutions? Can the project be broken down into smaller sections or delivered in stages to reduce risk? |  |  | 0 - Requirements are extremely complex, cannot be broken into phases and there is only one deployment recommendation |  |  |  | ß | 0 |  | Select from dropdowns for each category
INVESTMENT OR BASELINE: Is this project an investment in new capability or does it support the baseline architecture that delivers current services? |  |  | 0 - Investment |  |  |  | ß | 0 |  | Select from dropdowns for each category
RISK REDUCTION: Refer to Risk Reduction Section below |  |  | 0 - No significant risk reduction identified |  |  |  | ß | 0 |  | Select from dropdowns for each category
TOTAL SCORE |  |  | Maximum Score = 30 |  |  | 10
[5 empty] | Regulatory Requirement |  |  | Q1 | 0 - No regulatory requirement
1 - Nice to have but not a necessity
2 - Does not have a defined implementation date
3 - Upon system implementation
4 - Has a defined implementation date
[5 empty] | Reliability |  |  | Q2 | 0 - No impact on reliability
1 - Nice to have but not a necessity
2 - Addresses existing, low impact issue
3 - Addresses existing, moderate level issue
4 - Addresses existing, high level issue
[5 empty] | Security |  |  | Q3 | 0 - No impact on security
1 - Nice to have but not a necessity
2 - Upon review of audit results, a breach was not discovered but suggestions were made to improve current policies/procedures
3 - Upon review of audit results, issues were discovered and recommendations were made to improve security/safety issues that required response prior to the next audit
4 - Without immediate attention, data privacy/integrity would be jeopardized that could have widespread market impacts
[5 empty] | Data Management |  |  | Q4 | 0 - No impact on this dimension
1 - Nice to have but not a necessity
2 - Addresses existing, low impact issue
3 - Addresses existing, moderate level issue
4 - Addresses existing, high level issue
[5 empty] | Efficiency |  |  | Q5 | 0 - No impact on this dimension
1 - Contained within one area and partially addresses the function
2 - Contained within one area and addresses the function 100%
3 - Spans multiple areas and partially addresses the function
4 - Spans multiple areas and addresses the function 100%
[5 empty] | Requirements |  |  | Q6 | 0 - Requirements are extremely complex, cannot be broken into phases and there is only one deployment recommendation
1 - Requirements are relatively easy but cannot be broken into phases and there is only one deployment recommendation
2 - Requirements are complex but clearly defined, potential to deploy in phases to mitigate risk
3 - Requirements are relatively easy and clearly defined, potential to deploy in phases to mitigate risk
[5 empty] | Investment/Baseline |  |  | Q7 | 0 - Investment
4 - Baseline
[5 empty] | Risk Reduction |  |  | Q8 | 0 - No significant risk reduction identified
1 - Nominal risk reduction
2 - Some risk reduction
3 - Significant risk reduction
Non-quantifiable Impacts
| Area | Comments (include reason why benefit cannot be quantified)
1 | CR | Reduced number of Customer complaints. Will allow CRs to provide Customers with a more accurate estimate for completion of services. Allow CRs to better manage which requests need to priority and which could be standard. |  |  |  |  | ß |  |  | Prioritize these by putting the most important at the top
2 | TDSP | Provides the TDSP with as much time as possible to more accurately schedule and manage daily workload. | [7 empty] | The top 4 will be displayed on the summary page
3 | Customer | Will allow Customers to get their services completed as quickly as possible.
4 | ERCOT | Potentially reduced number of requests and MarkeTrak issues. Will allow ERCOT to expedite the processing of orders as prioritized by the Market.
5 | PUCT | Reduce number of Customer complaints.
6
7
8
9
10
11
12
Risk Reduction
| Risk Description | Mitigation Percentage (degree of reduction of risk) | Probability of Risk Condition happening (in a year) | Approximate cost of risk during risk period | Expected risk-cost/year = Probability of risk * Cost of risk * Mitigation %
1 |  | 0% | 0% | 0 | 0 |  | ß |  |  | Prioritize these by putting the most important at the top
2 |  | 0% | 0% | 0 | 0 |  |  |  |  | The top 4 will be displayed on the summary page
3 |  | 0% | 0% | 0 | 0
4 |  | 0% | 0% | 0 | 0
5 |  | 0% | 0% | 0 | 0
6 |  | 0% | 0% | 0 | 0
7 |  | 0% | 0% | 0 | 0
8 |  | 0% | 0% | 0 | 0
Alternatives | [6 empty] | ß |  |  | Document costs and other impacts of not executing the project
[7 empty] | ß |  |  | Document other alternatives considered
Alternatives (Cost of Not Doing Project, Manual Workaround Options, etc.)
1
2
3
4

## CBA_Sum
Project Cost / Benefit Analysis Summary
Project Information
PRR / SCR / PR / "New": | PRR707
Project Title: | Prioritization and Timing of Transactions Based Upon PRR672 Collaborative Analysis and Retry Process for 814_20s |  |  | Sponsor's Name: |  | ERCOT
Estimator's Name: | Mansour/RMS |  |  | Estimate Date: |  | 2007-02-14
ERCOT Corporate Goals |  |  |  | Senate Bill 7 Requirements |  |  |  | ß | Market: SB7 required; ERCOT Goals optional
Indicate percentage that this project supports each corporate goal: |  |  |  | Indicate percentage that this project supports SB7 requirements: |  |  |  |  | ERCOT: Both ERCOT Goals and SB7 required
|  | Pct |  |  |  |  | Pct
Goal 1 - Reliability & Congestion Management |  | 0% |  | Access to transmission & dist systems |  |  | 0%
Goal 2 - Retail Transaction Processing Success |  | 100% |  | Reliability & adequacy of electrical network |  |  | 0%
Goal 3 - Wholesale Access, Settlement & Billing |  | 0% |  | Customer choice of REP |  |  | 100%
Goal 4 - Management Systems & Business Practices |  | 0% |  | Accounting accuracy |  |  | 0%
Goal 5 - Financial Management and Cost Effectiveness |  | 0%
Goal 6 - External & Stakeholder Affairs |  | 0%
Goal 7 - Organizational Readiness |  | 0%
Total (Maximum of 100%) |  | 100% |  | Total (Maximum of 100%) |  |  | 100%
Cost / Benefit Summary
Project Cost | ERCOT Implementation Cost | 75000
| Market Implementation Cost | 0
| Total Implementation Cost |  | 75000
| ERCOT O&M Cost | 0
| Market Ongoing Cost | 0
| Total Ongoing Cost |  | 0
[5 empty] | 75000 |  | Total Cost
Project Benefit | ERCOT Benefit | 0
| Market Benefit | 0
[5 empty] | 0 |  | Total Benefit
|  | Net (Cost) - Benefit |  |  | -75000
Objectives Summary
Prioritization and Timing of Transactions Based Upon PRR672 Collaborative Analysis and Retry Process for 814_20s | [6 empty] | Score
IMPLEMENTATION REQUIREMENT | [6 empty] | 2
RELIABILITY | [6 empty] | 2
SECURITY | [6 empty] | 0
DATA MANAGEMENT | [6 empty] | 3
EFFICIENCY | [6 empty] | 3
REQUIREMENTS | [6 empty] | 0
INVESTMENT OR BASELINE | [6 empty] | 0
RISK REDUCTION | [6 empty] | 0
TOTAL SCORE |  |  | Maximum Score = 30 |  |  |  | 10
Non-quantifiable Impacts
| Area | Comments
1 | CR | Reduced number of Customer complaints. Will allow CRs to provide Customers with a more accurate estimate for completion of services. Allow CRs to better manage which requests need to priority and which could be standard.
2 | TDSP | Provides the TDSP with as much time as possible to more accurately schedule and manage daily workload.
3 | Customer | Will allow Customers to get their services completed as quickly as possible.
4 | ERCOT | Potentially reduced number of requests and MarkeTrak issues. Will allow ERCOT to expedite the processing of orders as prioritized by the Market.
Risk Reduction Summary
| Risk Description | [5 empty] | Risk/Year
1 | [6 empty] | 0
2 | [6 empty] | 0
3 | [6 empty] | 0
4 | [6 empty] | 0
Assumptions Summary
Assumptions
1 | This CBA addresses Prioritization and Timing of Transactions Based Upon PRR672 Collaborative Analysis and Retry Process for 814_20s.
2 | Ongoing support likely cannot be absorbed by current ERCOT staff. However, the FTEs described in ERCOT’s PRR672 Phase 3 Impact Analysis [Retail Customer Choice (2 FTEs)] could also perform the work requirements for this PRR.
3 | PR- 50121_07 Retail Business Processes: Changes to the Retail Transactions applications in support of the TIBCO framework are currently in progress. Risk is high that resolution for testing and stability issues related to RBP will impact design and development work on this PRR.
4 | PRR672 Phase 1 resulted in a scope change to PR-40038 Tx SET 3.0 to include the prioritization of the processing of 814_16 Move-In Requests containing a priority code of anything other than null or 01. PRR672 Phase 2 Collaborative Analysis was managed as an O&M effort. PRR672 Phase 3 included Level 1 Priority Move Ins - to be processed within 1 retail business hour; Level 2 - Standard Move-ins and Move outs – to be processed within 2 retail business hours. PRR672 Phase 3 will be executed in a separate project, PR-60008 Terms and Conditions requirements, not limited to Texas SET changes. PRR707 is also to be managed under Project No. 60008_01.
Calculation Parameters
Market Cost | Impacted Number of QSEs |  |  | 100
| Impacted Number of CRs |  |  | 100
| Impacted Number of TDSPs |  |  | 6
| Impacted Number of Resources |  |  | 175
Present Value Interest Rate: |  |  |  | 6%
Changing this parameter is not recommended
It is used to calculate present value of future cash flows

## Instructions
Cost / Benefit Analysis Worksheet Instructions
General Information
Fields highlighted in yellow are to be entered by the person completing the CBA
Fields highlighted in turquoise are section headings or important subtotals
All data entry takes place on the "CBA_Dtl" tab
"CBA_Sum" provides a 2 page summary of the 5 page detail section
"CBA_Dtl" contains several optional worksheets to the right of the main CBA sections
These optional worksheets are not included in the default print range
CBA_Dtl Tabl
Project Information
|  | PRR / SCR / PR / "New" |  | Enter the source document number for this project - if none exists,
enter "New"
|  | Project Title |  | Name of project
|  | Sponsor's Title |  | Project sponsor
|  | Estimator |  | Person completing the CBA
|  | Estimate Date |  | Date the CBA is completed
| Senate Bill 7 Requirements |  |  | Enter percent of each SB7 requirement the project supports
Total should not exceed 100%
| ERCOT Corporate Goals |  |  | Enter percent of each ERCOT corporate goal the project supports
Total should not exceed 100%
Assumptions
|  | Assumptions |  | Document assumptions that are made in the evaluation of the project
ERCOT Internal Cost
Implementation Cost
|  |  | Cost to Implement | For a project requested by ERCOT this number comes from the Time and Cost Estimate worksheet
For a project requested by the market, this number is the mid-point of the Impact Analysis cost range
All project costs are to be included in this value
Ongoing Cost (O&M)
|  |  | Staffing | ERCOT staffing increases due to the implementation of this project
|  |  | Hardware | Hardware additions required after project implementation
|  |  | Software | Software costs required after implementation (ex: yearly licensing)
|  |  | Infrastructure | Other costs relating to the physical or computing infrastructure
|  |  | Other | Use these 2 fields to capture other cost categories
|  |  | Other | Change the "Other" headings to the name of the new cost categories
ERCOT Internal Benefit
Direct Cost Savings
|  |  | Staffing | ERCOT staffing savings due to project
|  |  | Hardware | Hardware savings due to project
|  |  | Software | Software savings due to project
|  |  | Infrastructure | Infrastructure savings due to project
|  |  | Other | Use these 2 fields to capture other savings categories
|  |  | Other | Change the "Other" headings to the name of the savings categories
Productivity Increases
|  |  | Time Savings | Value of hours saved due to project deliverables
|  |  | Other Increased Efficiencies | Value of hours saved due to project deliverables
|  |  | Other | Use these 2 fields to capture other savings categories
|  |  | Other | Change the "Other" headings to the name of the savings categories
Other Benefits
|  |  | Cost Avoidance | Costs avoided due to implementation of project
|  |  | Other | Use these 2 fields to capture other savings categories
|  |  | Other | Change the "Other" headings to the name of the savings categories
Market Cost
|  | Implementation Cost |  | Market implementation cost is derived from ERCOT implementation cost
|  |  | Estimated Market Cost | Calculated by multiplying ERCOT implementation cost by the selected market impact percentage (from the Parameters section) and the number of impacted market participants (from the Parameters section)
|  |  | Impacted Market Segments | These fields allow the requester to customize the cost/benefit
calculations by declaring the number of market participants are
impacted by segment - this is used in both the Market Cost and
Market Benefit sections
|  |  | Market Implementation Complexity | "High/Medium/Low/No Impact" - indicates the impact percentage for a market segment
|  | Ongoing Cost |  | Ongoing costs required of market participants upon implementation of project (totals by market segment)
Market Benefit
Benefits by Participant
|  |  | Direct Cost Savings | Direct savings per market participant in each market segment
|  |  | Elimination of Manual Effort | Elimination of manual effort per market participant in each market segment
|  |  | Other | Use these 2 fields to capture other savings categories
|  |  | Other | Change the "Other" headings to the name of the savings categories
Benefits for Market
|  |  | Reduced Congestion Cost | Expected congestion cost savings in market
|  |  | Consumer Savings | Expected savings that are likely to benefit consumers - be sure not to double count savings to market participants that are likely to pass through to consumers
|  |  | Transaction Cost | Expected reductions in transaction costs due to project
|  |  | Other | Use these 2 fields to capture other savings categories
|  |  | Other | Change the "Other" headings to the name of the savings categories
Project Objectives Detail
|  | Implementation Requirement |  | Project score indicating implementation timing requirements and/or governing body requirements (PUCT, market committee, etc.)
|  | Reliability |  | Project score indicating impact on overall ERCOT system reliability (all systems to be considered)
|  | Security |  | Project score indicating impact on physical or cyber security
|  | Data Management |  | Project score indicating the impact on data accuracy, timeliness and/or transparency
|  | Efficiency |  | Project score indicating efficiency gains that would be realized
|  | Requirements |  | Project score indicating the completeness of the requirements and the likelihood that delivery risk can be reduced by breaking the project into smaller deliverables
|  | Investment or Baseline |  | Project score indicating whether the project provides additional functionality (investment) or supports the existing system architecture
|  | Risk Reduction |  | Project score indicating overall risk reduction that can be achieved at implementation
Intangible Benefits
|  | Area / Comments |  | Document benefits here that cannot be quantified but should be considered in the overall prioritization of the project
Risk Reduction
|  | Risk Description |  | Description of risk item
|  | Mitigation Percentage |  | Percent of the risk that the project would eliminate if implemented
|  | Probability of Risk Occurring |  | Probably of the risk occurring in a given year
|  | Approximate Cost of Risk |  | Estimated cost if the risk occurred
|  | Expected Risk Cost/Year |  | Risk probability * Approximate Cost of Risk * Mitigation Percentage
Alternatives
|  | Alternatives |  | Document alternatives that were considered or are available
Ex: comments about manual workarounds (amount of effort and cost) or other implementation options that were considered
CBA_Sum Tab
| Cost / Benefit Summary |  |  | Summary from CBA_Dtl tab
| Objectives Summary |  |  | Summary from CBA_Dtl tab
| Intangible Benefit Summary |  |  | Summary from CBA_Dtl tab
| Risk Reduction Summary |  |  | Summary from CBA_Dtl tab
| Assumptions Summary |  |  | Summary from CBA_Dtl tab
Calculation Parameters
Market Cost
|  |  | Impacted # of QSEs | Source for this data is in the Market Cost section of CBA_Dtl
|  |  | Impacted # of CRs | Source for this data is in the Market Cost section of CBA_Dtl
|  |  | Impacted # of TDSPs | Source for this data is in the Market Cost section of CBA_Dtl
|  |  | Impacted # of Resources | Source for this data is in the Market Cost section of CBA_Dtl
|  | Present Value Interest Rate |  | Percentage used to value future cash flows in the CBA
This value was suggested by the ERCOT Accounting Dept.; it should not be changed