## Sheet1
No. | PWG 2007 Goals | Target Date | % Complete
1 | Implement new Version 2 ERCOT Profiles. | 2007-05-07 | 80%
2 | LRS sample selection round two. | 2007-03-01 | 80%
3 | New Oil & Gas Profile - BUSOGFLT | 2007-09-07 | 80%
4 | 2007 Annual Validation. | 2007-11-07 | 5%
5 | Evaluate the methodology for profile scaling factors (per UFETF Nov. 16) | 2007-06-07 | 5%
6 | Review 2004, 2005 & 2006 UFE Analysis. | 2007-08-07 | 5%
7 | Examine ways to accommodate extreme events in Settlement process. | 2007-10-07 | 5%
8 | Establish Long Term Strategy of Load Profiles including refresh timeline | 2007-05-07 | 5%
9 | IDR Analysis – 2 issues outstanding from original analysis. | 2007-12-07 | 5%
10 | Review if having more weather stations adds accuracy | 2007-07-07 | 5%
11 | Review if the weighting of weather stations is appropriate | 2007-07-07 | 5%
12 | Review IDR installation procedure language to ensure compliance | 2007-08-07 | 5%
13 | Does having 2 decimals on load profiles significantly affect settlement | 2007-06-07 | 5%
14 | Review LPG language on list based profiles and universality | 2007-08-07 | 5%
15 | PUCT Docket responses to demand response or AMR rule, etc. | 2007-12-07 | 5%
16 | Set up area on PWG web page for key documents | 2007-05-07 | 5%
17 | Annual Review of load profiles as specified in market language | 2007-12-07 | 5%
18 | Analysis to identify new profiles as specified in market language | 2007-12-07 | 5%
19 | Update the TOU procedures on the Load Profiling web site | 2007-05-07 | 5%
20 | Investigate ways to improve Business Profile ID assignments | 2007-05-07 | 5%
21 | Review analysis of DLC demonstration programs | 2007-09-07 | 5%
22 | Review Protocol and LPG language for appropriateness for large Opt-in Entity | 2007-08-07 | 5%