## Goals for 2007
DSWG Goals for 2007 Update
Item # | DSWG Goal | Deliverable | Target Date | Primary Owner | Additional Team Members | Status
1 | Nodal Training for Load Participation | ERCOT sponsored training class | End of 4th Quarter | Paul Wattles | Mark Patterson, Mary Anne B, Floyd T, Scott W | Not Started
2 | Notice of Nodal LMP & Load Zone Prices | Document to post on DSWG web site | End of 4th Quarter | Mary Anne Brelinsky | Jay Z, Floyd T, Nelson N | Not Started
3 | RUC Capacity Short Charge—How do you insulate price responsive loads from these charges | Overview at DSWG Meeting in April | End of 4th Quarter | Nelson Nease |  | Wait until we get more guidance from the PUCT and look at TXU Response 33416
4 | Priority Pricing—Long term BUL Commitment | Conceptual Design |  | Jay Zarnikau | Shmuel Oren | Not Started
5 | Develop Improvements to LaaR Performance | PRR supported by WMS and submitted to PRS | End of 2nd Quarter | Mary Anne Brelinsky |  | Not Started
6 | Revisit DLC and Energy Aggregation—What’s working and what’s not | Presentation at DSWG Meeting and Summary Document | End of 4th Quarter | Bob Boyle | Steve I, | Not Started
7 | Load participation in RPRS and BES | Training and PRR Sponsorship if necessary | End of 3rd Quarter | Randa Stephenson | Mark P | Not Started
8 | CLR for Dummies | Documents for posting on DSWG web site | End of 3rd Quarter | Scott Wardle | Mark P | Not Started
9 | Price Responsiveness Survey | Report and Presentation to the DSWG | End of 2nd Quarter | Paul Wattles | Randa Stephenson | Not Started
10 | Review Load Bidding/Dispatchability as related to PRR 667 (RPRS) | Review at April DSWG Meeting | End of 1st Quarter | Scott Wardle |  | Not Started
11 | Review Infrastructure (settlement procedures) Requirements (metering and Load Profiles) to Support DLC and other Mass Market Programs | Presentation at DSWG | End of 3rd Quarter | Steve Isser |  | Not Started
12 | Finalize the Load for Dummies in the Nodal Market | Document to post on DSWG web site | End of 2nd Quarter | Floyd Trefny | Mary Anne B, Jay Z, Mark P | In Progress

## Goals for 2006
DSWG Goals for 2006 Update
Item # | DSWG Goal | Deliverable | Target Date | Primary Owner | Team Members | Status
1 | Identify a permanent solution for negative LaaR bidding | List of solution alternatives identified, comparative analysis completed, and PRR's introduced | End of 2nd Quarter | Mary Anne Brelinsky | Special Task Force
2 | Develop a description of demand side opportunities for the Nodal Market Design | HTML document that has been peer reviewed and posted to the ERCOT website | End of 4th Quarter | All | Jay Zarnikau | PUC to initiate procedures
3 | Develop a Price Responsive Load Participation Program for all customer segments | Program concept & preliminary analysis completed. Present to WMS for feedback on next steps | End of 4rd Quarter | Malcolm Smith | Jay Zarnikau, Dan Austin, George Arnold | In Progress
4 | Review comments from an Ad Hoc Group on Proposed Rules for Resource Adequacy and Automated Metering | Comments to Proposed Rules filed with the PUCT | End of 1st Quarter | Jay Zarnikau | Malcolm Smith
5 | Compare demand response resource programs being run in other ISO markets | Report Completed and Posted to ERCOT Website | End of 3rd Quarter | Steve Isser | Steve Krein
6 | Identify by market segment: a. customer ability to respond to prices b. barriers to participation c. proposed solutions to remove those barriers | Assessment and basis for ERCOT's reporting requirements under the PUCT Demand Response Project #32853 | End of 4th Quarter | Steve Krein | All
7 | Identify demand side program opportunities to solve a once in ten year loss of load type event | Present analysis and recommendations to WMS | End of 1st Quarter | Steve Krein | All
8 | Update description of demand side opportunities on ERCOT website and include status of Replacement Reserve | HTML document that has been peer reviewed and posted to the ERCOT website | End of 2nd Quarter | Mary Anne Brelinsky | Steve Krein