## NMMS
Number | Issuing Entity | Name | Page Number | Description | Accept / Reject / Response | Reviewer | Comments/Reasons | Document that initiated punch list item | Document that in the end incoroporated punchlist item | Date Originally added to Punch list | Assigned Owner | STATUS (closed, open) | Notes
| NMF 2/28/2007 |  |  | Moving NOMCR interim update back to the PMCR for planning base cases etc |  |  | Added at NMF 2/28/2007
| NMF 2/28/2007 |  |  | Equipment values depencency --- use new NOMCR, please describe the process |  |  | Added at NMF 2/28/2007
| NMF 2/28/2007 |  |  | PMCR process to NOMCR and showing the methodology and example |  |  | Added at NMF 2/28/2007
| NMF 2/28/2007 |  |  | Can we have READ ONLY mode for IMM ? |  |  | Added at NMF 2/28/2007
| NMF 2/28/2007 |  |  | Send Rose model to MPs (selected) ? Selected MPs should send their interest to ERCOT |  |  | Added at NMF 2/28/2007
| NMF 2/28/2007 |  |  | Finalize naming convension RDFID and discuss with MPs |  |  | Added at NMF 2/28/2007
| NMF 2/28/2007 |  |  | Load data loaded into profiles in MOD. Especially if the format is non-PSSE, need meeting and methodology -- Doug Evans lead from ERCOT |  |  | Added at NMF 2/28/2007
| NMF 2/28/2007 |  |  | How to pick pick ratings for JOU items in planning ? What should be the methodology. Need SSWG to weigh in on decision |  |  | Added at NMF 2/28/2007
| NMF 2/28/2007 |  |  | Send the list of parking lot items from NMF to NMF list |  |  | Added at NMF 2/28/2007
| NMF 2/28/2007 |  |  | Send presentations from 2/28/2007 to NMF |  |  | Added at NMF 2/28/2007
| NMF 2/28/2007 |  |  | Dates for future NMF meeting. Please send those out in the next two weeks |  |  | Added at NMF 2/28/2007
| NMF 2/28/2007 |  |  | Please add zone names to zone numbers in MOD |  |  | Added at NMF 2/28/2007
| NMF 2/28/2007 |  |  | Instead of columns that say "yes/no" for required fields highlight the ones that would be required it would be much easier in IMM |  |  | Added at NMF 2/28/2007
| NMF 2/28/2007 |  |  | What is the way to bring PMCR data over to NOMCR data. Pleas eprovide more details on the CIM export process from MOD and the import to Operations |  |  | Added at NMF 2/28/2007
| NMF 2/28/2007 |  |  | Need to keep PMCR available for viewing inside the 90 days operations window |  |  | Added at NMF 2/28/2007
6 | CenterPoint Energy |  |  | Just as a requirement is stated for the AOGM to provide for the automatic conversion of existing one-line diagrams the requirement should also exist for the automatic conversion of existing Outage Schedule and Project (i.e., TPIT) in the current zonal model. Hence, a description of the current TPIT system and corresponding data is also needed in the document. | Related to Detail Design |  | Outage Scheduler is expected to be a separate Nodal requirement document. The Outage Scheduler requirements will need to address Outage issue. The functionality of TIPT will need to be maintained, but the reports defined in the requirements document are intended to meet this requirement. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date. |  | This was not covered in the CSD but, if this functionality is provided in the NMMS, it will be described in the Detailed Design Specification. The TPIT functionality is currently under discussion and if the TSPs decide they wish to provide this information to NMMS, we will provide the functionality to implement this requirement. |  |  | Open
7 | CenterPoint Energy |  |  | With respect to Figure 4 : Transition from Planned to Operations Project, a definition of what constitutes each would be helpful; also, it’s not clear why a TDSP has to provide additional data and what forms the basis for accuracy under “project review for accuracy”. Ideally, this information is entered accurately into the data base and no updates or verifications are necessary. Cross-checks are good but they need to be clearly defined. | Related to Detail Design |  | In general a Planning Project will be bus-oriented. When the transition to Operations is required, additional breaker-to-breaker model data will be required to update the Project. For instance, switching devices will need added as well as the 15 min rating for a line Planning-to-Operations transition. The only additional data added in the Nodal environment as compared to the current environment would be what is required by Nodal Protocols or Business Processes to ensure Nodal Protocol coverage. In many cases the additional data provided would be minimal and actually less than currently required (with the noted exception of additional Nodal requirements). The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date. |  | A very high level approach for this conversion is presented in the CSD. The Detailed Design Specification will provide a full description of this process and who will be responsible for providing the data and when. Also provided will be a full description of the PMCR-to-NOMCR conversion process and how these will be kept in synch. |  |  | Open
10 | CenterPoint Energy |  |  | Inherent to the database design and as illustrated in Figure 11, Timeline Database Process, is the idea that any model will be “grown” or created from one database. It’s been pointed out that this has never been done before so why would ERCOT want to be the first? Is this really needed? Do annual planning cases or monthly CRR cases need detail down to the breaker level? Won’t this create unintended consequences dealing with model size and performance. This idea needs to be re-visited with significant input from the ROS working groups to see if this would really work or if it’s really needed. | May require Nodal Protocol change |  | Yes, It is the requirements documents intent that the Model Database will be the repository for Model data needed for Annual Planning, CRR Network, and Network Operations Model. The single database concept is ERCOT's proposal to meet the consistency requirements defined in the Nodal Protocols. ERCOT staff believes that failure to design a central repository lead to major amounts of effort to verify and rectify differences and fail to meet the consistancy requirements. Nodal Protocol Annual Planning Models do not specifically require breakers, nor do these requirements require breakers for planning cases. The Nodal Protocols require Annual Planning Models to be provided in a CIM compliant manner. ( See 3.10.2 (3)) ERCOT has requested in this document the ability to provide PSSE and IEEE Common format dumps of the model data; however, these formats are currently not a Nodal Protocol requirement. There are specific rules associated with the CRR Network Model and its association or derivation from the Network Operations Model (See Nodal protocol 7.5). NMMS is designed to meet those Nodal requirements. Model size and performance does not currently cause an issue with today's software. |  | No Change to Requirements will be made. The Comments/Reasons block provides the clarification to the issue. The Requirements and CSD describe the use of a single Model and this approach/philosophy will be propagated through the Detail Design as well. |  |  | Open
12 | CenterPoint Energy |  |  | The NMMS requirements list dynamics data as being provided and used. Note that each generator in the system needs dozens of pieces of data to adequately model its dynamic behavior. The introduction of a single piece of errant data amongst the thousands of pieces of dynamics data contained in the database sometimes causes a completely useless simulation. It takes time to find and tune the dynamics data so that useful results can be obtained. The Dynamics Working Group (DWG), for the most part, contains the handful of people in ERCOT who can accomplish this task and a very valid and real concern is that the NMMS software may require DWG members to spend lots of time trying to make the software work that would be better spent on more valuable exercises. Add to that, it is unclear as to what dynamic analysis will be accomplished by this software. Is the application a daily analysis? The maintenance to obtain meaningful results for such an application would be enormous? | Related to Detail Design |  | Noted. Our intent is that NMMS will be a repository for the Dynamics data and will provide the base data for a dynamics case. Conceptually, dynamics data would be provided and reviewed by Market Participants for inclusion in NMMS. ERCOT is currently executing dynamic studies in operations which require this data. It seems to ERCOT staff that it is an appropriate solution to the business process to include this required data in the central repository. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date. |  | No detail or mention of this issue was made in the CSD. This issue will be addressed in the detailed design specification. |  |  | Open
15 | CenterPoint Energy |  |  | Other pertinent planning parameters are missing from the requirements documents. Where are the specifications for load, dc-tie, and block load transfer, etc. inputs? | Related to Detail Design |  | The NMMS shall include the current Transmission Element types. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date. |  | All model data will be contained in the Data Dictionary. This will be provided to the Market Participants for review. In addition, the NMMS will allow the addition of any data required and the database schema will be modified as needed. The process/method to add an element to the NMMS schema will be defined in the Detailed Design Specification. |  |  | Open
16 | CenterPoint Energy |  |  | How will new devices not currently modeled in operations, such dynamic reactive or potential electric storage devices, be incorporated into the planning model? | Related to Detail Design |  | Business processes for maintaining the device types will have to be developed. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date. |  | All model data will be contained in the Data Dictionary - including the device types. This will be provided to the Market Participants for review. In addition, the NMMS will allow the addition of any data type and the database schema will be modified as needed. The process/method to add a device type to the NMMS schema will be defined in the Detailed Design Specification. |  |  | Open
17 | CenterPoint Energy |  |  | As a preliminary general statement, CenterPoint Energy believes that there are a number of unanswered questions about the Network Model Management System (NMMS). In the limited time that has been allowed for the proposal to be reviewed, CenterPoint has heard different views of exactly how this NMMS proposal would be implemented. Building, maintaining, tuning, refining, and testing transmission system modeling databases is a complex and resource-intensive process. The NMMS proposal, as CenterPoint Energy understands it, would unnecessarily complicate this process further by requiring transmission planners to use operational modeling databases to model transmission planning data. | Related to Detail Design |  | The NMMS design proposes that the basic building block for the Annual Planning Model will be data within the Network Operations Model. This is to ensure the consistency between the models as required by the Nodal protocols. This document is not intended to document all process changes that will be required in implementing a nodal market The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date. |  | The NMMS process to build operational and planning models has been defined at a high level in the CSD. The Detailed Design Specification will further describe this process. Per the current plan, the NMMS will not require TSP or ERCOT Planners to use Operational Models to model transmission planning. The Operational model will be the base from which a planning model will be created for use by the ERCOT planners. |  |  | Open
18 | CenterPoint Energy |  |  | Burdening transmission planners with new modeling chores to support a system designed in a vacuum sets up an unrealistic expectation that may not be met throughout ERCOT. Certainly, there are issues of data consistency in any transmission system throughout the country, and it requires hard work by transmission modeling experts to resolve those issues. However, the NMMS modeling proposal is not a panacea that magically resolves those issues, and has not undergone the necessary technical review by ROS working groups to assess whether the concept would help or hurt. | Related to Detail Design |  | There are no panaceas to the difficulties of developing and operating transmission network models; and it is not our intention to suggest that there are. ERCOT has been charged with developing a processes and tools to meet specific protocol requirements. This requirements document is one part of these tools. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
19 | CenterPoint Energy |  |  | It is worth noting that the NMMS proposal is not a necessary pre-requisite to implementation of the nodal market. In fact, no where in the Nodal Protocols is the requirement for the planning model to use operational model data as a starting point. The Nodal Protocols assumes that the operational and planning models will be inherently different and therefore requires that they have a certain degree of consistency in terms of load flow results. CenterPoint Energy has discussed this matter with other TSPs and believes it is a general consensus that the NMMS proposal, as presently structured, will likely create unneeded modeling burdens and new data accuracy problems and possibly fail completely. It would benefit no one if, after by-passing normal technical and budgetary review processes and committing to NMMS expenditures and staff additions on a modeling project objective that may have been ill-conceived from the outset, the resulting database becomes cumbersome, if not impossible, to use for all the intended applications. | Related to Detail Design |  | a) While a construct called "NMMS project" is not a pre-requisite to implemenation of the nodal market; some toolset must be defined to provide the deliverables required by the nodal protocols. Under the direction of the nodal transition plan, ERCOT is charged with proposing systems to the TPTF to meet the nodal requirments. b) ERCOT staff does not beleive we have bypassed the technical and budgetary review process, but is following it in making this proposal to TPTF. c) Nodal protocols make it clear that ERCOT is to produce CIM models which are related to the Annual Planning models. ERCOT believes that the comment is objecting to a Nodal Protocol requirement, reference Nodal Protocol section 7.5 which reads" (5) ERCOT shall make available to TSPs and/or DSPs and all appropriate Market Participants, consistent with applicable policies regarding release of Critical Energy Infrastructure Information (CEII), the CRR Network Model. ERCOT shall provide model information through the use of the Electric Power Research Institute (EPRI) and NERC-sponsored “Common Information Model” and web based XML communications" and 3.10.8.4 (2) ERCOT shall provide a system to implement Dynamic Ratings and obtaining monthly expected ambient air temperatures to be applied to rating tables for the Annual Planning Models and the CRR Network Models. Transmission Elements that have Dynamic Ratings implemented in the Network Operations Model must have Dynamic Ratings in the Annual Planning Models and CRR Network Models. ERCOT cannot revise this Nodal Protocol requirement
20 | CenterPoint Energy |  |  | If an idea such as the NMMS “breaker” planning model made sense for managing data consistency, then CenterPoint Energy and other TDSPs could have and would have implemented it. Some regions and some TDSPs have some limited elements similar to NMMS, but CenterPoint Energy is not aware of any TSP or region successfully carrying a centralized, operational-model-based central database management concept as far as the NMMS proposal aspires to go. Of particular relevance, CenterPoint Energy is not aware of NMMS being used in other regions that have nodal market designs. | Related to Detail Design |  | There is nothing in the requirements document that ERCOT staff is aware of that requires planning to use a breaker planning model.
21 | CenterPoint Energy |  |  | Given that the NMMS database proposal is not a pre-requisite to nodal market implementation and is not required by the proposed nodal protocols, CenterPoint Energy advises against bootstrapping this proposal to nodal market implementation in an effort to bypass normal technical and budgetary review processes. In the event, however, that ERCOT decides to go down the NMMS path without meaningful support or input from TDSPs and ERCOT stakeholders, CenterPoint Energy offers additional comments as outlined below. | May require Nodal Protocol change |  | ERCOT hopes that all TSPs will actively participate in the implementation of NMMS. Nodal protocols make it clear that ERCOT is to produce CIM cases which are related to the Annual Planning models. ERCOT believes that the comment is objecting to a Nodal Protocol requirement, reference Nodal Protocol section 7.5 which reads" [(5) ERCOT shall make available to TSPs and/or DSPs and all appropriate Market Participants, consistent with applicable policies regarding release of Critical Energy Infrastructure Information (CEII), the CRR Network Model. ERCOT shall provide model information through the use of the Electric Power Research Institute (EPRI) and NERC-sponsored “Common Information Model” and web based XML communications"] and 3.10.8.4 (2) ["ERCOT shall provide a system to implement Dynamic Ratings and obtaining monthly expected ambient air temperatures to be applied to rating tables for the Annual Planning Models and the CRR Network Models. Transmission Elements that have Dynamic Ratings implemented in the Network Operations Model must have Dynamic Ratings in the Annual Planning Models and CRR Network Models."] ERCOT cannot revise this Nodal Protocol requirement
5 | TXUED_NWG |  |  | Within the Vision section of the document pertaining to Annual Planning Model(s) the following comment was inserted: During the clarification questions asked by ERCOT staff a consecion was given in that planning could still retain bus that are in the model that do not belong to any physical facilities. How will these buses be retained if this is the building block for future planning models? | Related to Detail Design |  | Consistency definition must be defined. It is understood that there are possible differences due to current modeling needs. Some differences need solutions while others may still remain but will be bound by the consistency requirements. G38
6 | TXUED_NWG |  |  | Within the Vision section of the document, bullet item 3 originally read: "Due to the size of ISO modeled systems, the number of network changes is larger than most vertically integrated utilities; and due to the problem listed above, timeliness is more critical"; however, the recommended language submitted reads as follows: "Due to the size of ISO modeled systems, the number of network changes is larger than most vertically integrated utilities; and due to the problem listed above" (removed "timeliness is more critical."). What does timeliness have to do with the size of the model. | Related to Detail Design |  | Timeliness references the economic impact and idea that data is derived from external sources. The number of model changes submitted is a concern.
20 | TXUED_NWG |  | NMMSREQ_88(b4) | How does the annual ADLR fits into this process? What provided for the base load model that all applications will use for there annual update? | Comment received -- no change to document |  | The ALDR (annual load data request) will have to be adapted to provide the load data that is required for NMMS. This will have to be further discussed with TSP and defined in the Detailed Design. |  | This is Requirement #91 (a3) in the current version of the NMMS Requirements document. No change was made to the document for this comment. Additional definition concerning the Loads to be used for the NMMS will be provided in the Detailed Design Specificaiton. |  |  | Open
1 | TXUED_TGP |  |  | No one -- not TPTF, ERCOT, or anyone else -- can know whether/what requirements exist today that have not been identified, or what additional requirements may arise in the future. Since this is true, the system should be designed with all possible flexibility to address those future needs whenever the cost of this flexibility is relatively low. This recognition and intent warrants a mention in the Vision section, and may warrant the specific addition or expansion of capabilities listed as requirements in the detail sections. If it is easy to hedge against costly problems on the back-end of the process by adding relatively cheap flexibility on the front-end, that seems to be a very prudent business practice. | Related to Detail Design |  | ERCOT staff agrees with these comments, but has not identified any change to be made to document to address them.
3 | TXUED_TGP |  |  | During the TPTF meeting on 2/20/2006, it was stated the Transmission Project Information Tracking (TPIT) Report could be produced from the data in NMMS. The current version of TPIT includes information that is not identified as part of NMMS in this requirements document. | Related to Detail Design |  | Additional data fields may be required for NMMS but it may also be noted that TPIT may change. G59
4 | TXUED_TGP |  |  | The Operations Model and the Annual Planning Model are produced by processing an extremely large amount of data to create network models that are significantly different in nature. The Operations Model is a node oriented model that discretely reflects all series components that make up a transmission line or transformer installation. This level of model detail is required in Operations to reflect the status of the components and to manage the real-time operation of the transmission system. The Annual Planning Model is a bus oriented model that does not discretely model all of the components of a transmission line or transformer because that level of detail is not needed to model, analyze or plan the transmission system, and would be confusing to most users. The effect of these components on the rating of lines and transformers is captured in the Planning Model. Also, the modeling capability of the Operations software and the Planning software is different because the modeling needs are different. In order to meet the different modeling requirements, NMMS will be a very complicated software product. Attempts by reputable vendors to develop such products in the past have not been successful. There is a high degree of risk that a properly functioning NMMS can be developed in time to support the Nodal Market, particularly with no evidence that a working version of a software product with the proposed capabilities of NMMS exists today. The lack of a detailed requirements document for the request for proposals will also complicate getting a good cost estimate and timetable from the candidate vendors. | Related to Detail Design |  | Until this document is presented to vendors ERCOT staff does not feel it is qualified to say that this project is beyond present technology. ERCOT is not aware of reputable vendors attempting to develop a product similar to NMMS and failing. ERCOT is aware of other ISO's and market driven organizations attempting similar modeling efforts. Approval of the initial requirements document is a necessary step to involving vendors in the process.
5 | TXUED_TGP |  |  | A number of the TSPs have developed fairly sophisticated in-house data management systems to produce their part of the Annual Planning Model. These systems and the ability to test the model in-house before it is submitted to ERCOT and the Steady-State Working Group (SSWG) results in models with very few initial errors. These data management systems replaced the historical approach to planning model development that employed the use of IDEVs to insert projects into the model. The submission of model changes through IDEVs proved to be an error prone and resource intensive approach. The process proposed in NMMS is similar to the historical, error prone, resource intensive approach with even more complications. NMMS proposes submitting IDEVs, or something like an IDEV, to add hundreds of planning projects to an ever- changing Operating Model. The TSPs will apparently not be able to fully test the IDEVs in-house because they will not have direct access to the NMMS data base. There is nothing in the requirements document to address these issues. | Related to Detail Design |  | ERCOT staff understands that there is a long history of planning projects pre-existing. We are also aware that the regulatory environment surrounding approval of projects has rapidly changed in the past years. We think that the nodal protocols, if passed by the PUCT, will institute another change in regulatory environment that requires proposed projects be captured by ERCOT in a market in which the network model is central. If approved by the PUCT, ERCOT staff thinks a process for implementing planning projects into the market is inevitable. The NMMS requirements embody our vision of how this process can take place. We welcome constructive advise on improving this process.
6 | TXUED_TGP |  |  | One of the stated goals of NMMS is the reduction of time consuming activities. While the proposed system might reduce time spent maintaining the Operations Model, it appears likely to increase the total time spent on developing the Annual Planning Model. The submission of system changes as individual projects to ERCOT for their implementation in 14 base cases by using NMMS is much more time consuming, and may also be more error-prone than the current methods used by SSWG and the TSPs. | Related to Detail Design |  | ERCOT staff understands that there is a long history of planning projects pre-existing. We are also aware that the regulatory environment surrounding approval of projects has rapidly changed in the past years. We think that the nodal protocols, if passed by the PUCT, will institute another change in regulatory environment that requires proposed projects be captured by ERCOT in a market in which the network model is central. If approved by the PUCT, ERCOT staff thinks a process for implementing planning projects into the market is inevitable. The NMMS requirements embody our vision of how this process can take place. We welcome constructive advise on improving this process.
11 | TXUED_TGP |  | NMMSREQ_60 | The different PTI software products, e.g., PSS/E, MUST, have different abilities to run contingencies that involve removing multiple line sections from service. How will NMMS create contingency files that match the capability of the different software products? | Proposed change to document -- accepted |  | Sub-classifications of contingencies will need further scrutiny in the detailed design phase of NMMS. Req 61 in 3.6.2 now reads :Req 61. Contingencies shall be able to be extracted for use in other applications including, but not limited to: a PTI/PSSE. BP, SR b Power World. BP, SR c Real Time Contingency Analysis The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date. |  | Modified PR50142 NMMS Network Model Management System Requirements. (new requirement # is 63). Additional Details will be provided in the Detailed Design - a full Contingency Editor/Builder will be provided as part of the NMMS sub-system. |  |  | Open
14 | TXUED_TGP |  | NMMSREQ_74(d) | The document does not describe what is meant by Dynamic Simulation Model. Is this the raw electrical and mechanical data for generators, etc., or is it the completed model such as a governor model used by a dynamic program? Some of the dynamic programs required models to be developed that are unique to that program. How will NMMS handle those models? How will proprietary models be handled? Will NMMS produce the load model for the dynamic base case? There is a considerable amount of work required to create a dynamic base case that will flat start using the DYRE file. How will NMMS create a base case that will flat start? | Related to Detail Design |  | The programs that are unique or proprietary to a dynamic program will be handled separately just as they are today by DWG. They will not be handled in NMMS. NMMS will produce a base case that is comparable to what is created by SSWG today. DWG will not see a reduced workload for flat starting. |  | The handling of Dynamic Models will be fully described in the Detailed Design Specification |  |  | Open
18 | TXUED_TGP |  | NMMSREQ_88(b4) | Will the forecasts of new substations and substation load from the Annual Load Data Request (ALDR) be used to develop the bus loads in the Annual Planning Model as it is today? How will the reactive losses through the substation transformers be calculated to create a transmission side load for the buses? Will NMMS develop the bus loads for the individual TSPs using their peak load forecasts and their substation load forecasts or will it try to combine all of the TSPs into one group and then develop the loads? If it does not treat the TSPs and their substations individually, the quality of the bus loads will not be as good as it is in the existing Annual Planning Model. | Related to Detail Design |  | The ALDR (annual load data request) will have to be adapted to provide the load data that is required for NMMS. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date. |  | This is Requirement #91 (a3) in the current version of the NMMS Requirements document. No change was made to the document for this comment. Additional definition concerning the Loads to be used for the NMMS will be provided in the Detailed Design Specificaiton. |  |  | Open
26 | TXUED_TGP |  |  | Section 3.13.1: This requirement states the Study Case will be built using Operation Projects and Planning Projects. The Planning Project data will not be as extensive as the Operations Project data because all of the individual components of the future projects such as switch and circuit breaker data is not available for the future projects, nor is it needed to model the future projects. How will the Study Case Builder create a case using the different project descriptions? | Related to Detail Design |  | It is ERCOT staffs vision that Planning Projects involving lines not fully modeled with breakers shall appear as bus-to-bus lines in studies.
28 | TXUED_TGP |  |  | Section 3.15.1: The Annual Planning Model consists of 14 different system models that represent different years and load levels. NMMS must be able to produce these models using different bus load levels, generation dispatches (MW and MVAR), voltage profiles, and shunt capacitor and shunt reactor switching status for each of the 14 system models. The requirements document does not address these and other modeling issues unique to the Annual Planning Model. | Related to Detail Design |  | It is not the intent of ERCOT to completely replace the planning process with a modeling database. This comment requires detail on either business process, or conceptual design which ERCOT has not yet developed. ERCOT intends to keep this question and provide the TPTF with a conceptual design which will address this issue before subsequent design proceeds.
31 | TXUED_TGP |  | NMMSREQ_137 | The same questions and comments developed for 3.7.2 Req 88 (b) (4) apply here. | Related to Detail Design |  | The ALDR (annual load data request) will have to be adapted to provide the load data that is required for NMMS. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date. |  | This is Requirement #143 in the current version of the NMMS Requirements document. No change was made to the document for this comment. Additional definition concerning the Loads to be used for the NMMS will be provided in the Detailed Design Specificaiton. |  |  | Open
1 | AEPSC |  |  | ERCOT staff and the TOs have barely learned to crawl in as far as modeling the existing as-built network. The approach endeavored by the proposed NMMS Requirements suggests that ERCOT is ready to jump to light-speed, and attempts to accomplish much more than can reasonably be attempted in a single step. AEP recommends that a phased approach be considered, which would allow ERCOT and its participants to learn from our mistakes before proceeding into a system that might never get off the ground under its own weight. The efforts necessary get the settlements system functional should not be forgotten. | Related to Detail Design |  | ERCOT staff is agreeable to a phased approach if that is also agreeable to the TPTF. ERCOT staff understands that there is a long history of planning projects pre-existing. We are also aware that the regulatory environment surrounding approval of projects has rapidly changed in the past years. We think that the nodal protocols, if passed by the PUCT, will institute another change in regulatory environment that requires proposed projects be captured by ERCOT in a market in which the network model is central. If approved by the PUCT, ERCOT staff thinks a process for implementing planning projects into the market is inevitable. The NMMS requirements embody our vision of how this process can take place. We welcome constructive advise on improving this process.
4 | AEPSC |  |  | If the product of the NMMS is to be the tool used by the market to anticipate LMP, then not only does the forward looking models need to be valid, but the substantial number of control techniques currently used avoid congestion need to be captured. Constraints relieved by operator action, or logical controllers, or reactive control systems may cause constraints that have measurable impact on pricing to be eliminated 99.9% of the time. These actions require highly sophisticated logic to be built into modeling tools used by both ERCOT and those interested in anticipating nodal prices. As more and more inefficiencies in market transactions are exposed, then even more complicated schemes will evolve only aggravating the need for capturing such complex logic into the modeling tools. Why even develop NMMS if the end product produces the bad information? | Comment received -- no change to document |  | There are no panaceas to the difficulties of developing and operating transmission network models; and it is not our intention to suggest that there are. ERCOT has been charged with developing a processes and tools to meet specific protocol requirements. This requirements document is one part of these tools. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
5 | AEPSC |  |  | While there are realistic steps that can and should be taken toward implementation of LMP, without preparing the proper foundational steps or soliciting the expertise necessary to do so, the implementation of NMMS may fail. | Comment received -- no change to document |  | There are no panaceas to the difficulties of developing and operating transmission network models; and it is not our intention to suggest that there are. ERCOT has been charged with developing a processes and tools to meet specific protocol requirements. This requirements document is one part of these tools. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
32 | Reliant |  | NMMSREQ_5 | The NMMS shall operate on a fully redundant platform with a service level agreement equal to the ERCOT EMMS?? What is ERCOT EMMS?. BP, SR Why do we need redundant hardware for this? | Comment received -- no change to document |  | ERCOT wants to be clear that this system availability and performance should meet or exceed the availability and performance of an EMS (ERCOT calls this the EMMS) The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
34 | Reliant |  | NMMSREQ_8 | [ Seems like the GUI should be separately specified and all applications should meet its requirements Do not repeat here.] | Comment received -- no change to document |  | ERCOT wants to be clear that this system availability and performance should meet or exceed the availability and performance of an EMS (ERCOT calls this the EMMS) The details shall be further refined in the Conceptual Design and Detailed design to be provided
37 | Reliant |  |  | Comment to Section 3.5.1: Need to be clear of the scope of data coming in from QSEs and TDUs through this process versus Registration, SCADA, and other potential system needs for example a Resources Parameters i.e., Minimum run time, start-up cost ….] | Related to Detail Design |  | Refer to 3.10.1 (1) and Reliant comments to 3.5.1 of document The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
48 | Reliant |  | NMMSREQ_40(l) | [seems like it would be better to list each type of Transmission Element, i.e., Transmission line, Transformer, breaker, generator and what data must be submitted to NMMS or is this detail specified somewhere else Do we need to see sample GUI layouts to assure we have captured all?] | Related to Detail Design |  | Minimal requirements are listed in Protocol 3.10.7. More requirements are needed to fully address modeling needs. Current devices (as they are called today versus Transmission Elements) basic templates will be provided. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
52 | Reliant |  |  | Comment to Section 3.6.1: [Not sure SE test facility, LMP has anything to do with NMMS] | Related to Detail Design |  | Comment may be correct, but NMMS may have its own Test Facility to test model fidelity. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
54 | Reliant |  | NMMSREQ_46(b1) | Added the word "Model" | Related to Detail Design |  | ERCOT staff believes that we need to detail difference between Model and Case. The use of the word model has a different connotation than case. The model contains all the necessary data to build a skeleton default base case. SCADA or other inputs may be added to the model to produce a case. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
55 | Reliant |  | NMMSREQ_46(b2) | Inserted question marks after verbiage | Related to Detail Design |  | Need to detail difference between Model and Case
56 | Reliant |  | NMMSREQ_46(b3) | Added the word "Model" | Related to Detail Design |  | Need to detail difference between Model and Case
57 | Reliant |  | NMMSREQ_46(b4) | Added "Network Model " | Related to Detail Design |  | Need to detail difference between Model and Case
73 | Reliant |  | NMMSREQ_68(g) | Inserted question marks after verbiage | Comment received -- no change to document |  | Hub Busses Protocol 3.10.3 (3)(a
77 | Reliant |  | NMMSREQ_73('c) | Inserted question marks after verbiage | Comment received -- no change to document |  | see definition. Used in Dynamic Model?
88 | Reliant |  | NMMSREQ_80 | Inserted question marks after FACTS and replaced the word "device" with "Transmission Element" | Comment received -- no change to document |  | We need models for "Flexible AC Transmission System" elements
99 | Reliant |  | NMMSREQ_85('c) | [a HUB is a attribute of a Electrical Bus definition] | Comment received -- no change to document |  | No change. System needs to have a database attribute to assign Electrical Bus and other bus types as defined in Hub definition. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
112 | Reliant |  | NMMSREQ_97 | Inserted question marks after verbiage | Comment received -- no change to document |  | ERCOT staff considers the ability to back out a change an important feature. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
119 | Reliant |  |  | Comment to section 3.11.1: [ the intent of the protocols is that there is one and only one Network Operations model that all these systems uses; This implies there may be a difference. The specifications of the SE, OS and NSA should require that they all start from the same data ] | Comment received -- no change to document |  | The intent of this entire document is that all network models come from the same database. The use of CIM databases however, implies that there can be time dependent changes in the model used at any given time.
133 | Reliant |  | NMMSREQ_146 | TWO COMMENTS: (1) This is an EMS function not a NMMS function (2) [what is the requirement to repeat protocol language here? Should we include all the applicable protocols as an Appendix to facilitate the reader and make the protocols part of the requirements documents for Vendors to provide systems that meet those requirements. ERCOT should not be the go between when it is possible to include protocol language in the business requirement] | Comment received -- no change to document |  | Q1 This may be an NMMS function. since the data path for dynamic rating changes may be through the NMMS. Q2A copy of the Nodal Protocols will be furnished to the vendor. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
1 | LCRA |  |  | In the Nodal World, do we still have the ability to copy the Real Time Solved State Estimator solution to a Study Case on the ERCOT EMS and do any studies/analyses on the study case including performing line inages/outages in the Study Case and rerunning Contingency analysis. Will Market Participants have something similar to the MOTE access that we currently have? | Comment received -- no change to document |  | A MOTE-like environment seems to be appropriate although explicitly not called for. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
3 | LCRA |  |  | How are the planning cases built? Is it from the CIM schema? | Comment received -- no change to document |  | The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
| TXU |  | CSD - General | The test bed/sand box to be used by TSPs to validate PMCRs is not well defined. This is an important feature from the TSP planner’s perspective. | Clarification | John Moseley | NMMS detailed design will seek to incorporate that functionality
| TXU |  | CSD - General | The requirement for NMMS to possibly produce the TPIT report is not described in the CSD. Can the requirement be included before the details for inputting the information and producing TPIT are developed? Further comments on this proposal will be provided in response to Doug’s e-mail. | Accepted | John Moseley | The inclusion of TPIT information in the submission process will be moved to IDA punchlist and followed up at Detail design
| TXU |  | CSD - General | {COMMENT: If this is the feature that converts the node-branch operations model to the bus-branch planning model should the description be expanded to describe this conversion?} | Accepted | John Moseley | Moved to IDA punchlist to be followed up during Detail design
| TXU |  | CSD - page 15 | I have experienced performance problems using Citrix. If there is a way of providing a solution that does not include Citrix I believe the product will perform better and have improved usability. If Citrix | Response | John Moseley | Fair criticism, Citrix solution will need to be verified as a workable one.
| ERCOT |  | No Document reference | Contingency Builder/Editor and User Process - Contingency List creation validation, exchange and modification | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | PMCR-to-NOMCR Conversion Process | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | NMMS Initial Load Process | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | Define Process to input Load and Generation Patterns - how do we create, modify, validate,and exchange - where do these come from, etc. | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | Generation data - how do we create, modify, validate,and exchange? | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | Process to define JOU and how to implement protocols to allow split generation parameters to be entered | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | EPS Meter sighting | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | Hub requirements | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | Settlement points requirements | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | Dynamic rating Adder | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | Dynamic ratings in general - Issues relating to Dynamic ratings -Updates/ web feeding? | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | LMP place holder measurements | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
1 | CenterPoint Energy |  |  | The Model database needs more detail. It should describe a CIM database that ERCOT can use to create the various different models. On the input side, it should detail what information is required from TDSPs (i.e., what level of detail from a SCADA, Outage | Related to Detail Design |  | PTI/PSSE RAWD format and IEEE Common Format added to requirement document. The only Nodal Protocol requirement is CIM. The timelines for all data are defined in Nodal Protocols. The type of data required was defined by Nodal Protocols but extensive add |  | This level of detail is provided in the Data Dictionary that will be completed and ready for distribution no later than the first week of February, 2007. That Data Dictionary will be distributed to all Market Participants. Any updates will be distributed |  |  | Open
2 | CenterPoint Energy |  |  | The Timeline Database Builder appears to simply meet the letters of the TNT protocol requirement. Does ERCOT use the CIM/XML data generated by this process in any way that would assure its fidelity? CIM/XML should play a more central role in the modeli | Related to Detail Design |  | ERCOT shall build Models and provide Models to Market Participants per the Nodal Protocol requirements. Our intent is to provide comparisons of data between time periods; measured against proposed Projects falling within the time periods for fidelity. |  | The Case Builder is currently in design but the current direction of that design is to use CIM XML to the fullest extent possible. The NMMS will accept, validate and produce CIM XML files for the entire ERCOT Network model in accordance with the protocol |  |  | Open
3 | CenterPoint Energy |  |  | Outage Scheduler: method of update and data extraction not clearly defined. Some programmatic method for update and data extraction is necessary to meet the increased outage scheduling requirements of TNT. | Related to Detail Design/Outside of scope of NMMS project |  | Upgrade to Outage Scheduler effort is another Nodal project. To be integrated with Outage Schedule update. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date. |  | A full description of the NMMS-to-Outage Scheduler interface will be provided in the NMMS Detailed Design Specification. The interface of the NMMS to the Outage Scheduler is limited to a list of equipment with limited (tier 1-2) topology provided by the |  |  | Open
5 | CenterPoint Energy |  |  | The interfaces between the various different models need more explanation regarding which functions are manual or automated in nature. For example is the case builder a manual or automated function or a combination. Similar comments hold for the Compariso | Related to Detail Design |  | Determination of case type is manual but retrieval is automatic. In some cases, sub-classifications of Projects may need filtered to provide meaningful or requested results. The details shall be further refined in the Conceptual Design and Detailed desig |  | This is partially described in the CSD and will be fully described in the Detailed Design Specification. All input and output interfaces to the NMMS are Man-Machine interfaces; however, the functional tasks for input validation or model generation using |  |  | Open
14 | CenterPoint Energy |  |  | The system needs failsafe back up. In the event that a case or model cannot be created because of an element bottleneck (example: a breaker or switch element is correctly modeled but the corresponding line does not show up or vice versa) there should be a | Related to Detail Design |  | There is the ability to back projects out of the system. Also, there will be sequence of Project submittal checks that will prevent the scenario listed. |  | This is addressed in the CSD and will be more fully described in the Detail Design Specification. The Level 1 Validation that occurs just prior to submission will validate that all devices and connectivity are available to implement the change. The abil |  |  | Open
13 | TXUED_NWG |  | NMMSREQ_42 | Does this include the capability to merge MP's annual model updates using PSS/E format into NMMS to reflect future years planning model? | Comment received -- no change to document |  | PSS/E format is specified as a requirement in 3.6.1. If the question is intended to ask if we will somehow take future PSSE planning cases and generate projects, the answer is no. The vision ERCOT holds is that approved projects would be entered into NM
15 | TXUED_NWG |  | NMMSREQ_46(f4) | This does not make sense. There are many devices that have only a single network connection, Shunt device, ground switches, and transmission switches installed to allow for future flexibility. All of these devices should be included in the ERCOT model. | Related to Detail Design |  | The intent is that all devices provided by Market Participants will be modeled and validation rules to detect errors will be defined. Perhaps a better wording would be "All two ended devices which are left one-ended without a specific approval of such a c |  | This is Requirement #49 (f4) in the current version of the NMMS Requirements document. No change was made to this document. The improved wording provided in the comments along with a full description of the validation process and rules will be defined i |  |  | Open
16 | TXUED_NWG |  | NMMSREQ_47 | This is not a good idea and can introduce error. Planning data submission should never be used to create a network model that is to be used by operations unless the planning data is provided in switch/branch format. The capability to reference an operatio | Related to Detail Design |  | This is proposed to minimize the impact to existing planning processes and support the defined Nodal Protocol consistency requirement. It is intended that the design prevent a Planning Project from being introduced into the Network Operations Model. |  | This is Requirement #50 in the current version of the NMMS Requirements document. No change was made to the document for this comment. Additional definition concerning the conversion of PMCRs to NOMCRs will be provided in the Detailed Design Specificait |  |  | Open
7 | TXUED_TGP |  | NMMSREQ_34(d) | The sub-classifications need to be revised because the meaning of the classification is not clear. For example, what is a TSP Budgeted Project? The ERCOT Staff and TSPs should develop the sub-classifications to ensure the list meets everyone’s requireme | Related to Detail Design |  | "Other" is listed as an option. Definitions of the sub-classifications will be provided and additional sub-classifications will be added if required. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF
17 | TXUED_TGP |  | NMMSREQ_82 | Without knowing the “current existing fields”, it is difficult to determine if all of the information needed for the Annual Planning Model is included in this requirements document. For example, there is no mention of base kV, area number, or Planning bu | Related to Detail Design |  | This comment requires detail on either business process, or conceptual design which ERCOT has not yet developed. ERCOT intends to keep this question and provide the TPTF with a conceptual design which will address this issue before subsequent design proc |  | This is Requirement #85 in the current version of the NMMS Requirements document. No change was made to the document for this comment. All fields in the database will be fully defined in the Data Dictionary and in the Detail Design Specification. |  |  | Open
27 | TXUED_TGP |  | NMMSREQ_125 | Removed "or Planning" from the original requirement verbiage | Related to Detail Design |  | Network Operations Model data "may" be submitted up to one year in advance (per Nodal Protocol 3.10.1). The minimum data submittal timeframe is 90 days and in some parts of the year 180 days. Therefore, it may be necessary to use Planning Projects to co |  | No change was made to the Requirements. The exact use of the Operations and Planning changes was explained in the CSD and will be further described in the Detail Design |  |  | Open
29 | TXUED_TGP |  | NMMSREQ_131 | Removed "or Annual Planning" from the original requirement verbiage | Related to Detail Design |  | Network Operations Model data "may" be submitted up to one year in advance (per Nodal Protocol 3.10.1). The minimum data submittal timeframe is 90 days and in some parts of the year 180 days. Therefore, it may be necessary to use Planning Projects to co |  | No change was made to the Requirements (currently this is number 137). The exact use of the Operations and Planning changes was explained in the CSD and will be further described in the Detail Design |  |  | Open
8 | Reliant |  |  | Comment to the definition of "Generation System" as follows: [Not all data for generators will come through NMMS as this implies. Some will come through registration.] | Related to Detail Design |  | Business Practice. TBD The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
30 | Reliant |  | NMMSREQ_3(b) | [ Reliant assumes the only actions allowed is to use a “project package” or not use a package. Not to modify a package or use part of one] | Related to Detail Design |  | Updates to Projects can occur beyond the Timeline mentioned in 3.10.1. For instance, if a model update is submitted a year in advance and updates occur prior to the required minimum timeframe set in 3.10.1, the capturing of the data would be critical to
51 | Reliant |  | NMMSREQ_44 | [Protocols did not envision the “project” process and thus there is no current requirement to post status of projects status. Do we need to add something similar to that used for Outage Scheduler?] | Related to Detail Design |  | Status is required to track. Refer to 3.10 (8) The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
75 | Reliant |  | NMMSREQ_72 | [Does the AOGM link to the Real Time system operators one-lines and SCADA points?] | Comment received -- no change to document |  | yes |  | This will be further discussed in the Detailed Design document. The answer given in the comments may need to change due to new information available based on vendors selected for the NMMS project.
79 | Reliant |  | NMMSREQ_75 | is this conforming to the “naming convention”] | Comment received -- no change to document |  | NO This is a unique software pointer. If the name is used for this pointer then a name change generally requires deletion of the transmission element and re-entry under a new name. |  | Will be further defined and documented in the Detailed Design phase.
80 | Reliant |  | NMMSREQ_75(a) | Create?? [Why is one not entered by the provider?] a unique identifier (e.g. Transmission Element) for each new Transmission Element within the Project. | Comment received -- no change to document |  | The TEID is unique and provided by the software. |  | Will be further defined and documented in the Detailed Design phase.
87 | Reliant |  | NMMSREQ_79 | [this sounds like a Outage Scheduler requirement not a NMMS requirement] | Comment received -- no change to document |  | Definitive design question. Requires NMMS link. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
91 | Reliant |  | NMMSREQ_82('c) | needs to be part of naming convention | Proposed change to document -- accepted |  | added " u. Transmission Element Name" The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
92 | Reliant |  | NMMSREQ_82(e) | Deleted "Congestion Management Zones" and inserted questions marks | Proposed change to document -- accepted |  | Should change this - did not get done in the issued document
98 | Reliant |  | NMMSREQ_84(d) | Seems like we should list all; this document should be more specific than protocols ] | Comment received -- no change to document |  | Req 1. Definitions shall be provided for Transmission Elements and generation related equipment including , but not limited to:...The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
103 | Reliant |  | NMMSREQ_91(f) | do not understand TEXT file as a protocol requirement] | Proposed change to document -- accepted
108 | Reliant |  |  | Section 3.8.1 Comment: Protocols Section 6 uses a term “Updated Network Model” . Is that what is being described here? Protocols Section 6 uses a term “Updated Network Model” . Is that what is being described here? [These statements can be confused w | Comment received -- no change to document |  | No this describes the process to move approved changes into the Network Operations Model
113 | Reliant |  | NMMSREQ_99('c) | We should consider not implementing this. Operators should always control | Comment received -- no change to document |  | ERCOT agrees. Operator will always control
117 | Reliant |  |  | Comment to section 3.10.1: [ use of this is not envisioned in the nodal protocols; what is it for; can be very dangerous to Market Participants who are not expecting this] | Comment received -- no change to document |  | ERCOT staff envisions a tool required for changes such as, participant name changes, and all associated equipment names must be revised. I
122 | Reliant |  |  | Comment to section 3.13.1: [ Do not think you mean Outage Scheduler here; suggest you use Study Power Flow for Outage Screening or something like that]. | Comment received -- no change to document |  | ERCOT staff thinks there is an interaction of study case builder and outage scheduler. The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
127 | Reliant |  | NMMSREQ_127 | [ do not think this can work automatically without engineering review] | Comment received -- no change to document |  | Definitive design question The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
129 | Reliant |  |  | Comment to 3.15.1: Same comments as before with CRRs . Please change to Annual Planning Model requirements applicable for a specified time such as the year it is applicable to] | Comment received -- no change to document |  | See req 132
131 | Reliant |  |  | Comment to 3.16.1: [there should not be a separate system for posting of NMMS but a generalized system that uses data from NMMS] [Protocols have hard requirements on how to post data in section 12. Menus to obtain posted Data must be in Protocol order | Comment received -- no change to document |  | It may be true that a separate system will be designed for posting all protocol required data; but until that system is conceptually designed, ERCOT staff feels that requirement should remain. The Timeline Database Process provides an accurate CIM model f
2 | LCRA |  |  | Is ERCOT planning to define the specifications of the CIM schema. Is this the standard CIM ? (because in the NMMS document it is referenced as “CIM/XML format as defined by ERCOT”) Example – We need to understand what is needed on our side if we wanted t | Comment received -- no change to document |  | The details shall be further refined in the Conceptual Design and Detailed design to be provided to TPTF at a future date.
5 | LCRA |  |  | Based on what I have heard at the TPTF, if there is a change in the energization schedule for a project, that change will get reflected in the Real Time Case/ Day Ahead case as soon as the information becomes available to ERCOT . Is that correct? How soon | Comment received -- no change to document |  | The scheduled energization date for a Project is a part of the Project definition. When this date is changed by the TSP the Project will be updated by ERCOT as soon as the process permits. I would anticipate this to be within one working day of receipt
| TXU |  | CSD - General | Concerning the PTC GUI {COMMENT: The title of the PMCRs, NOMCRs and SAMRs should be more descriptive so the user can more easily identify them.} | Accepted | John Moseley | Moved to IDA punchlist to be followed up during Detail design
| TXU |  | CSD - General | {COMMENT: Will search capability be provided?} | Accepted | John Moseley | Moved to IDA punchlist to be followed up during Detail design
| TXU |  | CSD - General | {COMMENT: The project types do not match the text description of a SAMR in an earlier section.} | Accepted | John Moseley | Moved to IDA punchlist to be followed up during Detail design
| TXU |  | CSD - General | {COMMENT: The user should be able to select PMCRs using a date range in addition to manual selection. I do not see this capability on figure.} | Accepted | John Moseley | Moved to IDA punchlist to be followed up during Detail design
| CNP |  | CSD - pg 25 in ref to PTC | What actions can be performed on the artifacts on this display (modify, insert, cancel, query?) Are there other drill down capability available on this display? | Clarification | John Moseley | Moved to IDA punchlist to be followed up during Detail design
| CNP |  | CSD - pg 26 in ref to PTC | How was this record selected from this display. How would you review another record? Is record copy allowed? | Clarification | John Moseley | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | SPS/RAP/RAPC/MAP/Reactive Switching Plans/etc Process and Interface description | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | Settlement Points file contents and format (for Settlement&Billing, Data Aggregation, LodeStar, MMS, CRR, etc.) | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | ICCP Data Processing and Integration (Measurement Mapping) | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | Interface with Outage Scheduler & Outage Evaluation - What is the necessary data exchange with Outage scheduler/Eval Group | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | Interface with Lodestar and/or Siebel/Registration (data feed to NMMS) | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | Describe each Interface to and from NMMS | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | Define MIS interface and list all postings that will be completed by NMMS | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design
| ERCOT |  | No Document reference | section 3.3 reference to outages | Accepted | Margaret Goodrich | Moved to IDA punchlist to be followed up during Detail design