## Slide 1: Managing Project Funding Changes
David Troxtell
Program Management Office
March 14, 2007

## Slide 2
Managing Project Funding Changes
Process for Managing Changes in Project Funding
  Individual CARTs have authority to make project budget changes <$100k
    They must still manage within their allocated CART budget
  Project budget changes >=$100k go to the ERCOT Strategic Review Team (directors) for review and approval
    CARTs bring forward proposals for reallocation of funds (including the CART which released the funds)
  Project budget changes >=$500k go to the ERCOT Executive Committee (EC) for review and approval
    SRT recommendation is provided
  Project budget changes >=$1M go to the ERCOT Board of Directors for review and approval

## Slide 3
Important Considerations
  Critical projects emerge between yearly prioritization cycles that need to be addressed on a near-term basis
  Every effort is made to AVOID negatively impacting PUCT and market projects. These include:
    Projects expected by the market in the current year
    Projects immediately below the cutline
  Market input is derived from project ranking on PPLs and input from appropriate CARTs (RO, MO, SO)
  Reallocating funds between CARTs is preferred over requesting additional project funding from the BoD
    This is especially the case early in the calendar year
  Communication of decisions occurs through usual channels
    Market Subcommittee reports (PRS, RMS, etc.)
    Board reports
Managing Project Funding Changes

## Slide 4
Texas SET 3.0 Funding Transfer
  Texas SET 3.0 was estimated at $1.63M going into Execution
    PPL budget was $3.75M
    $2.1M variance was reported to SRT by RO CART
      Reasons: Project consolidation, reduced external labor, hardware not needed
    RO presented a proposal to use some of the funds within RO
    CO presented a proposal to use the funds for facilities needs
      Build out unfinished TCC2 space, reconfigure cubicles to increase cube count, construct 12,000 sq. ft. annex/warehouse
    The SRT and Executive Committee decided the best course of action was to reallocate the funds to CO
      No impact to planned RO market projects to be started in 2007; possible, but small, impact to delivery in 2007
    These decisions occurred very quickly due to timing constraints relating to the February Board of Directors meeting
    Reported to RMS on 2/14
    Board reviewed proposal on 2/20 (see next slide)
Managing Project Funding Changes

## Slide 5
At February Board meeting a portion of the proposed CO facilities project was approved (PR-60099_01)
  Approved (used $600k of $2.1M reallocated funds)
    Reconfigure TCC2 cubicles from 6 packs to 8 packs (+216 seats)
    Build out unfinished TCC2 space (+136 seats)
    Configure TCC2 space for Nodal market trials
    Reconfigure conference rooms as vendor/team rooms
    Parking lot expansion (+130 spaces)
    Off-site storage (+5,000 sq ft leased space)
  Not Approved
    12,000 sq ft annex/warehouse
  CO will bring forward a proposal for remaining needs at an upcoming Board meeting
  Reallocated funds remain with CO until final decisions are made on facilities needs ($1.5M not yet committed to a project)
  If additional effort is not approved, funds will be returned to SRT for reallocation consideration
Managing Project Funding Changes

## Slide 6: Additional Slides

## Slide 7
Examples of Workspaces in Taylor