## Slide 1: Market Coordination Team Update Retail Market Subcommittee March 14, 2007 Adam Martinez Market Operations Division Projects Organization

## Slide 2: Risks / Issues
Issue | Mitigation | Owner
PR50121_07 RBP – Stabilization necessary for successful implementation | Schedule management Milestone completion | ERCOT
ERCOT February Retail Release | Schedule and resource management Milestone completion | ERCOT
PUCT Mandate of 07/01/2007 poses tight timeline | Schedule and resource management Milestone completion | All
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 3: Project Schedule
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 4: March Status Reporting - CRs
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 5: March Status Reporting - CRs
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 6: March Status Reporting - CRs
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 7
PR40038_01 Status
Status:
  On target for schedule, budget, and scope
Project Phases:
  Initiation – Completed
  Planning – Completed
  Execution – Mandated completion date July 1, 2007; Go-Live 06/24/2007
  Closing – Target completion is post go-live
Recent Activity as of March 5, 2007:
  Complete Test Plans, Scripting and Data Prep for ITEST
  Complete Core Build TIBCO, Siebel, Paperfree, TML, NAESB, EIS)
  Migrate Core Build to iTEST (TIBCO, Siebel, Paperfree, TML, NAESB, EIS)
  Begin UAT on 03/05/2007
Next Steps for ERCOT as of March 5, 2007:
  Finalize Build ETS and Reprocessing
  Complete Market Test Plans, Scripting, and Data Prep
  Set Up Market Test Environment
  Migrate to Market Test Environment
Next Steps for MCT:
  Continue to monitor Market issues and progress
  Continue work on Production Implementation and Contingency Plan
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 8: March Status Reporting – ERCOT and TDSPs
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 9: Market Risk Questions
MPs responded to the following questions:
1.) Have you identified any risks that will prevent your company from beginning testing on time (Connectivity Testing for Flight 0407: March 20, 2007)? Please describe any risks.
2.) Have you identified any risks that will prevent your company from implementing on time (June 23, 2007)? Please describe any risks.
All MPs responded “No” to the two questions.
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 10: CRs Not Reporting Progress for March
Ambridge Energy
Spark Energy LP
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 11: Changes to Market Requirements – February MCT
Sending Customer Billing Contact Information to Gaining CR – p.8
Upon receipt of the Customer billing contact information from the
exiting CR during a mass transition event, ERCOT shall provide each
gaining CR with available Customer billing contact information for the
ESI IDs they will be receiving through the mass transition event.
ERCOT will transmit files in a pipe-delimited file format via NAESB using file type ‘FF’ (flat file).
File 2 – Record Layout for the MTCRCustomerInformationERCOTResponse file (ERCOT to submitting CR) – Appendix B
Modified following language to replace ‘csv’ with ‘flat file’:
“Header record – First row of flat file…”
Appendix E: Mass Transition Timelines
Modified following language in second box on both timelines to include ‘and TDSPs’:
“ESI ID lists for POLRs and TDSPs generated”
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 12: Information on PR 40038
POLR Customer Class
  Evaluated and assigned monthly in ERCOT systems
  Defaulted to Premise Type when 814_20 add received by ERCOT
  Viewable through TML Find ESI ID functionality and PiApp
  Will be added to the TDSP ESI ID Report
    3/19/07 – User Guide Posted
    5/8/07 – DDL change will go live and field will be null in May and June postings
    7/3/07 – PCC will be populated beginning with this posting
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 13: Information on PR 40038
Mass Transition Indicator
  Siebel Service Order Updated to reflect whether a transaction is associated with a Mass Transition.
  3/19/07 – User Guide posted
  5/8/07 – DDL change will go live and field will be null in May and June postings
  6/25/07 – Mass Transition Indicator will be populated beginning with this posting
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 14: Information on PR 40038
MWh and ESI ID Reporting Information
  During April of every even year ERCOT will provide information on Total MWh and Total ESI IDs served in each TDSP territory for inclusion in REP Reports.
  Information will be posted in April evaluating the time period from April 1st of odd year through March 31st of even year.
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 15: Information on PR 40038
867_03 Processing
  867_03 is being modified to include an ’05’ purpose code to indicate that the usage is a replacement of a previous 867_03.
    The ’05’ Replacement code is in addition to the ’00’ (Original) and ’01’ (Cancel) purpose codes already present in the 867_03
  Going forward, the daily load of 867_03s at ERCOT will include the following:
    867_03 for 3 AM – 3 AM which contain an ’00’ or ’01’ and
    867_03s for the previous day 3 AM – 3 AM which contain an ’05’
  ’05’ will be mapped as ’00’ for usage loading business rules in Lodestar
    ’05’ will be reported as ’00’ in the 867_03 Activity Report
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 16: Reminder: Where are Texas SET 3.0 Key Documents Kept?
  MCT page – ERCOT.com
  http://www.ercot.com/committees/board/tac/rms/mct/index.html
  And what is there?
  Texas SET Version 3.0 Requirements Final Version 1.9
  Texas SET 3.0 - MCT Issues & FAQs Log
  Texas SET Version 3.0 Change Controls
  Texas SET Guides Version 3.0
  Texas SET Version 3.0 Implementation Plan DRAFT
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 17
Meeting Dates and Locations 2007
  March 29 – ERCOT Met Center
  April 25 – ERCOT Met Center
  May 23 – ERCOT Met Center
  June 27 – ERCOT Met Center or Conference Call
  July 25 – Location TBD
  August 29 – Location TBD
(Note: all meetings are held in conjunction with TX SET meetings)
Future Meetings/Market Communications
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 18: ERCOT Contacts
ERCOT Project Manager ERCOT SR. Business Analyst
Hope Parrish Jennifer Frederick
hparrish@ercot.com jfrederick@ercot.com
512-248-6522 (w) 512-248-6733 (w)
512-771-9582 (c) 512-413-0815 (c)
ERCOT Market Liaison
Susan Munson
smunson@ercot.com
512-248-3881 (w)
512-826-0564 (c)
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 19: Questions?
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO