|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Technical Advisory Committee Reliability and Operations Subcommittee for February 2007 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | ERCOT is currently tracking 160 active generation interconnection requests totaling over 71,000 MW. This includes over 22,000 MW of Wind Generation. |  |  |  |  |  |  |  |
| 2. | Transmission Services has updated the Transmission Information Tracking System (TPIT) workbook which highlights both completed and future transmission improvements to the ERCOT grid and the related costs. |  |  |  |  |  |  |  |
| 3. | Regional Planning is currently reviewing proposed transmission improvements with a total cost of approximately $190 to $250 M. |  |  |  |  |  |  |  |
| 4. | Local Congestion costs continue on a downward trend from 2004 and 2005, possibly due to lower MCPEs in 2006 and lower fuel costs than in 2005. |  |  |  |  |  |  |  |

1.0	Status of Active Generation Interconnection Requests

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” data folder posted in the “Operations and System Planning” data area on the ERCOT website.

## New Generation Beginning Commercial Operations

Mesquite Wind 1 (200 MW) went into commercial operation.

## Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Currently tracking 160 active generation interconnection or change requests |  |  |  |  |  |
|  |  | North | South | West | Total |
| Security Screening Study |  | 3 | 4 | 11 | 18 |
| SSS Completed |  | 10 | 10 | 19 | 39 |
| Full Interconnect Study |  | 12 | 21 | 44 | 77 |
| FIS Completed |  | 1 | 0 | 2 | 3 |
| Interconnect Agreement Completed |  | 6 | 4 | 13 | 23 |
| Capacity for Grid, MW |  | 24,079 | 28,337 | 19,225 | 71,641 |
| Wind MW (under development) |  | 932 | 4,328 | 17,352 | 22.612 |

| Fuel | Public | Non-public | Total |
| --- | --- | --- | --- |
| Natural gas | 2.850 | 10,900 | 13,750 |
| Nuclear | 0 | 25,186 | 25,186 |
| Coal | 4,971 | 4,052 | 9,023 |
| Wind | 2,900 | 19,712 | 22,612 |
| Other | 0 | 1,070 | 1,070 |
| Totals | 10,721 | 60,920 | 71,641 |

## Potential Future Generation Interconnections

The table below summarizes the publicly known potential future generation projects for the ERCOT region.  (IA=Interconnect Agreement, PL=Public Letter)

| FUTURE GENERATION INTERCONNECTIONS (PUBLIC PROJECTS) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR # | Site Name | Status | County | Region | Fuel | In Service Date | MW into Grid | Change from Last Report |
| 06INR0016 | Dow 9 | IA | Brazoria | South | Gas | Mar-07 | 0 |  |
| 06INR0037 | Cirello 1 | IA | Taylor | West | Wind | Mar-07 | 233 |  |
| 06INR0035 | Colorado Bend 1 | IA | Wharton | South | Gas | Apr-07 | 275 |  |
| 06INR0036 | Quail Run 1 | IA | Ector | West | Gas | Apr-07 | 275 |  |
| 06INR0038 | Scurry County 1 | IA | Scurry | West | Wind | May-08 | 130 |  |
| 03INR0030 | Wild Horse 1 | IA | Cottle | West | Wind | Jun-07 | 126 |  |
| 07INR0003 | Whirlwind 1 | IA | Floyd | West | Wind | Sep-07 | 60 |  |
| 06INR0021 | Barton Chapel | IA | Jack | North | Wind | Oct-07 | 120 |  |
| 04INR0011 | Mesquite Wind 2 | IA | Shackelford | West | Wind | Dec-07 | 200 |  |
| 04INR0017 | Ocotillo Wind Farm 1 | IA | Howard | West | Wind | Dec-07 | 59 |  |
| 04INR0020 | Project Snyder | IA | Scurry | West | Wind | Dec-07 | 63 |  |
| 07INR0045 | Roscoe 1 | IA | Scurry | West | Wind | Dec-07 | 209 |  |
| 07INR0010 | Stanton Wind 1 | IA | Martin | West | Wind | Dec-07 | 101 |  |
| 03INR0034 | Silver Star 1 | IA | Erath | North | Wind | Dec-07 | 60 | Change in in-service date |
| 07INR0023 | Sweetwater Wind 4 | IA | Nolan | West | Wind | Dec-07 | 300 | Signed IA |
| 06INR0035 | Colorado Bend 2 | IA | Wharton | South | Gas | May-08 | 275 |  |
| 06INR0036 | Quail Run 2 | IA | Ector | West | Gas | May-08 | 275 |  |
| 03INR0030 | Wild Horse 2 | IA | Cottle | West | Wind | Aug-08 | 39 |  |
| 05INR0015 | Gulf Wind 1 | PL | Kenedy | South | Wind | Sep-08 | 400 |  |
| 09INR0006 | Oak Grove 1 | IA | Robertson | North | Coal | Apr-09 | 855 |  |
| 09INR0006 | Greenville | PL | Hunt | North | Gas | May-09 | 1750 |  |
| 08INR0003 | Sandow 5 | IA | Milam | North | Coal | Jul-09 | 581 | Signed IA |
| 05INR0015 | Gulf Wind 2 | PL | Kenedy | South | Wind | Sep-09 | 400 |  |
| 09INR0006 | Oak Grove 2 | IA | Robertson | North | Coal | Oct-09 | 855 |  |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | Coal | Jun-10 | 750 |  |
| 05INR0015 | Gulf Wind 3 | PL | Kenedy | South | Wind | Sep-10 | 400 |  |
| 10INR0002 | Hugo | PL | Choctaw, OK | North | Coal | Feb-11 | 500 |  |
| 11INR0001 | Twin Oaks 3 | PL | Robertson | North | Coal | Jun-11 | 630 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Coal | Sep-11 | 800 |  |
|  |  |  |  |  |  | Total | 10,721 |  |

- Transmission Services Activities

# Dynamic Analysis and Modeling

  - Finalized 2006 study report and responses to TXU comments.

  - Study results presented to ROS/RPG.

  - Continuing to support PTI in the development of combined cycle power plant stability models.

  - Reviewed and provided comments on Generator Interconnection Procedure 2/22/07.

  - Performed preliminary review of TXU study

  - Review of study scopes and/or dynamic studies produced by TO’s associated with generation interconnection projects into ERCOT.

  - Supporting System Operations (Shun-Hsien Huang) in the analysis and enforcement of real time voltage stability limits and transient stability limits.

  - Continuing participation on dynamic load model development.  Review of latest report from EPRI.

  - Supporting ongoing DWG activities including efforts to develop a transient voltage recovery criteria, revision of high-set underfrequency load shedding schemes and draft requirements for field testing of NERC generator performance standards (PRC-019, PRC-024, MOD-026, MOD-027).

  - Compiled LaaR models in psse format and provided to DWG 2/15/07.

  - Continue supporting the System Operation project – PR-30084 CSC Thermal and Voltage Calculation and Postings with bug fixing and testing.

# Resource Adequacy/CDR

  - Most Notice of Probabilities of Return for moth-balled units have been returned by generating companies.

  - Notices of capacity for private network units have been sent by Client Relations.  Some have been completed and submitted.

# Load Forecasting

## Modeling

  - ERCOT Staff:

  - Updated and refined the Load Shape and Energy forecasting models used for the 2006 forecast for the development of the 2007 long-term peak and energy demand forecast. These updated models were used to obtain a tentative long-term forecast for the 2007 cycle.

  - Tested the new models using extreme weather profiles to determine the effects on the summer peak demand forecast.

# Data Activities

## Case Building

  - Completed February TPIT update of Steady State WG 2007 Data Set A cases

  - Delayed by one week the February TPIT update of Steady State WG 2007 Data Set B cases due to uncertainty in new coal plant statuses

## Studies underway or planned within System Planning Division

  - System Planning will be updating the generating units Pmax data in the base cases with the latest seasonal Net Dependable Capability test data in March

## Other

  - Submitted PRR 713 to improve resource outage information.

# TPIT

  - TPIT graph formulas was re-formatted from 2006 to 2007

  - Compiled all updated TPIT data for 1st quarter TPIT report.  A lot of old project duplicates on Completed projects tab was sorted out and many changes were updated regarding joint projects. Once TPIT report was updated, all correspondence on Future projects was sorted by projected in-service date and Completed projects were sorted by actual in-service date.  This process allows for another sorting to configure yearly sums of CONFIDENTIAL Total Project Estimated Cost column,  Trans Circuit Miles New, Rebuilt or Reconductored column and Transformer Capacity (MVA) column.  These sums were logged to the Improvement Cost Summary Graph by Service Level kv per year.

  - Assigned new project numbers to new projects

  - Prepare Service Level Kv data past 2013

# Maps/Graphics

  - Maintained and updated AutoCAD Transmission Network System map.

  - Completed the updating AutoCAD Transmission map to match Power World map, one-line diagram information and Data dictionary.

  - Created area maps for reports (PDF, JPEG, DXF or WMF format) as requested.

  - Plotted Transmission, Zone, area maps for mailing and internal use and plotting oversized documents for others.

# Upcoming Events/Deadlines

## March

  - March 1 ALDR data due to ERCOT

  - Summer Assessment due to NERC Mar 30

  - Long-Term Reliability Assessment due to NERC Mar 30

  - TPIT Report with No Cost completed 03/01/07 and posted to ERCOT website

  - TPIT Cost Summary Report completed 03/01/07

  - Prepare Service Level Kv data past 2013

## April

  - April 1 ALDR data due to SSWG

  - TPIT Report with No Cost to be Posted to ERCOT Website

  - TPIT Cost Summary Report to be posted by March 11

  - April 20 NOIE dispatch data due to ERCOT

## May

  - Siemens – PTI user group meetings for PSSE, MUST, ODMS

  - ATTENDING ERCOT Operations Training Seminar at MET

# Other Issues

  - System  Planning and Operations Map Access Approval

  - Process of receiving ALDR data.  Logging completed data received to ALDR check off list spreadsheet.  Contacting ALDR contact person with any issues.

3.0	Regional Planning Activities

The following summarizes numerous significant activities associated with regional planning issues.

# Coal Unit Integration Study

  - Have begun initial analysis associated with this study.  This study will evaluate what sets of transmission projects are economic to integrate the various units planned for the eastern part of Texas in the 2009-2012 timeframe.  Different sets of economic projects will be identified for reasonable combinations of these units.  Transmission projects identified in the study will be presented for Board endorsement when the combination of units which justify those projects have signed interconnection agreements and air permits

# CREZ Study (SB20).

  - Responded to numerous questions from parties in PUCT Docket 32672 through two technical conferences

# Regional Planning Group Project Reviews.

  - TXUED TNP One – East Bell County 345kV Double Circuit Project has been submitted. This is a $63 million project in north central Texas driven primarily by the proposed addition of new coal generation in the area.  Comments have been received from stakeholders, which TXUED has addressed, and the ERCOT Independent Review of this project is underway.

  - TXUED Anna-Collin-NW Carrollton has been submitted and the ERCOT Independent Review is nearing completion and will be presented to TAC and the Board in March.

  - TXU Able Springs has been submitted.  It is a $12.8 million project primarily to serve a customer in Kaufman County.  It is currently in ‘Study Mode’ while TXU addressed comments made by the RPG.

  - CNP Houston Area Constraint Mitigation Phase II Project has been submitted.  It is a $37.9 million project to increase the North to Houston import capability.  It has completed the comment phase with no comments requiring CNP resolution and is currently in ERCOT Independent Review.

  - TXUED has submitted the Jewett to West Fairfield 138 kV line rebuild project.  This is a $17.9 M dollar project in Leon and Freestone counties.  This project is currently in the comment phase.

  - LCRA has submitted the Evant to Lampasas 138 kV line rebuild project.  This is the first project to be submitted by a transmission operator that originated from the ERCOT 2006 Five Year Plan.  This is a $7.8 M dollar project in Lampasas County that is currently in the comment phase.

  - LCRA has submitted the Paleface to Miller 138 kV line rebuild project. This is a $9.4 M dollar project in Travis and Blanco counties.  This project is currently in the comment phase.

  - TXUED has submitted the Parkdale Dynamic Reactive Project.  This is a $45-$98 M dollar project to add a dynamic reactive device in the DFW area.  This project is currently in the comment phase.

# Other Projects/Studies

    - Regulatory support related to Entergy Integration study and CREZ study.

4.0	Congestion Management Activities

# CSC Congestion Charges Collected from QSEs

  - Less dollars collected from QSEs in 2006 compared to 2005.

| $Million | E_N | N_H | S_H | S_N | W_N | N_W | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2006 total | 7.5 | 8.4 | 31.4 | 1.5 | 0.2 | 3.0 | 52.0 |
| 2005 total | 0 | 25.7 | 39.2 | 8.9 | ~0 | 5.3 | 79.0 |

Number of Interval where constraints were binding.

Last quarter of 2006 had a higher number f the binding intervals in the S_H zone due to the Hillje construction project but still less congestion dollars overall for this zone were collected in 2006.

|  | E_N | N_H | S_H | S_N | W_N | N_W |
| --- | --- | --- | --- | --- | --- | --- |
| 2006 total | 198 | 504 | 2192 | 588 | 47 | 361 |
| 2005 total | 0 | 884 | 1516 | 1135 | 11 | 328 |

Local Congestion Costs in Millions for 2004-2006

Lower local congestion costs in 2006 possibly due to lower MCPEs in 2006 as well.

|  | 2004 |  | 2005 |  | 2006 |
| --- | --- | --- | --- | --- | --- |
| OOMC | $78.9 |  | $83.9 |  | $62.4 |
| Unit Specific – Up | 19.0 |  | 32.8 |  | 23.1 |
| Unit Specific – Down | 55.4 |  | 46.6 |  | 30.6 |
| RMR | 125.7 |  | 103.4 |  | 62.6 |
| RPRS | _____ |  | _____ |  | 43.2 |
| TOTAL | $279.0 |  | $266.7 |  | $221.9 |

MCPE 2004-2006

Fuel Index Price 2004-2006