## Sheet1
MCT Issue Log and FAQs for Texas SET 3.0
Issue # | Issue Type | Affected Txn | Change Control Affected | Issue Statement | Issue Status | Date added | Date of Status Change | Source
1.1 | Implementation Guide Gray Box | 814_04 | Emergency CC 2006_703 | Clarification required that 'SNP' shall only be used by the TDSP when 814_03 is for Mass Transition and a Safety Net Request is pending for the ESI ID. Update REF~7G 'SNP' gray box | Closed | 2006-08-23 | Adopted 8/24/2006
1.2 | Implementation Guide Gray Box | 814_08 | Emergency CC 2006_703 | Correct 'MTC' Mass Transition Cancel gray box to restrict use to 'ERCOT Use Only' in the REF~1P (Status Reason) | Closed | 2006-08-23 | Adopted 8/24/2006
1.3 | Implementation Guide Gray Box | 814_09 | Emergency CC 2006_703 | Correct 'EFR' Evaluate for Resubmission to remove 'For ERCOT Use Only' since this is a respons from TDSP in the REF~1P | Closed | 2006-08-23 | Adopted 8/24/2006
1.4 | Implementation Guide Gray Box | 814_14 | Emergency CC 2006_703 | Correct DTM~376 header gray box to be clear that segment is only required when Mass Transitin and Move-out date is needed to be communicated to the gaining CR from ERCOT | Closed | 2006-08-23 | Adopted 8/24/2006
1.5 | Implementation Guide Change | 814_15 | Emergency CC 2006_703 | Correct ASI to remove the 'RL' data element from this segment, which is not necessary since 'Accept' will accomplish the same thing. | Closed | 2006-08-23 | Adopted 8/24/2006
1.6 | Implementation Guide Gray Box; Updated Market Requirements | 814_02 | Emergency CC 2006_700 | Add two new MSC Codes to the SAC04 of the 814_02 Transaction to meet a regulatory requirement identified by TXU ED | Closed | 2006-08-23 | Adopted 8/24/2006
1.7 | Implementation Guide Change | 650_01 | Emergency CC 2006-701 | Add new 'YNQ Yes/No Friday Overdue Authorization for Disconnects for Non-Payment' segment; recommendation from Terms and Conditions Task Force | Closed | 2006-08-23 | Adopted 8/24/2006
1.8 | Implementation Guide Change | 650_04 | Emergency CC 2006-702 | Provides the TDSP with the mechanism to correctly communicate the action (BGN08) taken when services have been Reconnected due to Denial of Access (RC004) by the TDSP | Closed | 2006-08-23 | Adopted 8/24/2006
1.9 | Updated Change Control document | 814-25 | Corrected CC 2006-694 | Removed 814_25 from Affected TX SET Transaction(s) section of Change Control form since it does not contain the N1 Service Address loop | Closed | 2006-08-23 | Adopted 8/24/2006
1.1 | Updated Change Control document | 650_02 | Corrected CC 2006- 698 | Corrected typo in 650_02 transactions in Detailed Description and Reason for Proposed Change(s) section of Change Control Form to state transaction 650_02 instead of 650_01 | Closed | 2006-08-23 | Adopted 8/24/2006
2.1 | Updated Change Control document | 814_19 | Corrected CC 2006-692 | Added 814_10 to 'Affected EDI Transaction Set' section | Closed | 2006-09-11 | Adopted 9/11/2006
2.2 | Implementation Guide Gray Box; Updated Market Requirements | 814_08, 814_09 | Corrected CC 2006-692 | Added 814_08, 814_09 to first bullet ('TS' indicator on BGN segment) | Closed | 2006-09-11 | Adopted 9/11/2006
2.3 | Updated Change Control document | 814_09 | Corrected CC 2006-692 | Added to New Cancellation Code 'MTC' bullet | Closed | 2006-09-11 | Adopted 9/11/2006
3.1 | ERCOT Coding Change | 814_05 | CC 2006-692 | Missing from section to use existing REF~7G segment with new code of '017' to represent service terminated because service provider went out of business. Decision was made for ERCOT to change the '017' reject code to A13 on the outbound 814_05 and put '017' into the REF03 | Closed | 2006-10-03 | Adopted 10/3/2006
3.2 | Updated Change Control document | 814_14 | CC 2006-692 | Add description to Change Control to state: Need new REF~ACD segment on 814_14 for POLR Customer Class designation (Implementation Guides are correct); updated change control | Closed | 2006-10-03 | Adopted 10/3/2006
3.3 | Market Requirements Document Change | n/a | n/a | Removed Appendix C: File Layout for Reporting of POLR Customer Class and modified Section 1.A Reporting of POLR Customer Class to clarify that this will be done through TML | Closed | 2006-10-03 | Adopted 10/3/2006
3.4 | Market Requirements Document Change | n/a | n/a | Modified Appendix B: File Layout for Customer Billing Contact Information to include all record types and file types used for sending and receiving Customer Billing Contact Information Files | Closed | 2006-10-03 | Adopted 10/3/2006
3.5 | Market Requirements Document Change | n/a | n/a | Added Appendix C: TDSP Priority Code tables for use in prioritizing Move-ins (Protocol Revision (PRR672) | Closed | 2006-09-11 | Adopted 10/3/2006
4.1 | Requirements/Implementation Guide Clarifications; Market Requirements Document Change | n/a | n/a | Clarification on use of "Mass Transition Customer" in 814_03. ERCOT will place "Mass Transition Customer" in the Customer Name field on the 814_03. TXU ED requested ERCOT to send a file containing ESI ID, Customer Name, and Primary Phone number to the TDSPs during a mass transition. This will not be included in scope of Texas SET 3.0, but will be included in a SIR during a retail release following Texas SET 3.0 implementation. RMGRR will be written to detail this process. TDSPs requested 814_PCs from CRs for every 814_04 they send the POLR CR during a mass transition. POLR CRs to review internally to see if this is possible. | Closed | 2006-10-24 | Discussed 10/24/2006; Resolved 11/6/2006
4.2 | Requirements Clarification | n/a | n/a | Allocation of ESI IDs in a mass transition - what is the source of the load-share data used as a basis for the allocation? POLRs provide the MWH information to the PUCT. PUCT confirmed the percentages will be sent to ERCOT for use in the ESI ID allocation. | Closed | 2006-10-24 | Resolved 10/24/2006
4.3 | Testing Clarification | n/a | n/a | New CRs must send a test Customer Billing Contact Information (CBCI) file containing mock data to ERCOT during flight test. TTPT Script Sub-team asked if ERCOT will provide the mock data. Answer from ERCOT testing team: No, file layouts will be provided to new MPs at Market Orientation; however, new CRs need to understand how to format their files and must create their own mock data. | Closed | 2006-10-24 | Resolved 10/24/2006
4.4 | Testing Clarification | n/a | n/a | In testing Mass Transition scripts specific to POLRs during Flight test, TTPT Script Sub-team asked if all CRs must test this functionality? Answer from MCT: All eligible POLRs and designated POLRs must test the POLR Scripts. | Closed | 2006-10-24 | Resolved 10/24/2006
5.1 | Requirements Clarification; Market Requirements Document Change | n/a | n/a | Will CRs need to send an initial load production Customer Billing Contact Information (CBCI) to ERCOT after go-live of Version 3.0 on 7/1/07? Answer: Yes, this will be done during the last two weeks of July, 2007. As a reminder, the CBCI file sent during Flight 0407 by all CRs is a test file and cannot be considered production. Market Requirements | Closed | 2006-11-07 | Discussed 11/7/2006; Resolved 12/11/2006 | Question from 11/08 RMS meeting
5.2 | Requirements Clarification | 650_04 | n/a | On 650_04 reconnects (RC004) for Denial of Access, should market participants sent the BGN02 from the Disconnect in the BGN06? Answer: No, this is not required. Texas SET Issue for changes to gray box will be written for future implementation. In addition, this issue will include BGN matching for Disconnect for Non-pay discussed at a previous meeting. | Closed | 2006-11-06 | Resolved 11/6/2006 | Question from 10/24 MCT meeting
5.3 | Requirements Clarification | 867_03, 810_02 | n/a | Request for clarification on the addition of the new replacement code on the 810_02 and 867_03 (Terms & Conditions Requirement 3 in the Texas SET 3.0 Market Requirements document). AEP & CNP must send cancel/rebills for all months unless its an IDR. For IDRs, they only send cancel/rebill for month impacted. TXUED - only sending the impacted month. No word on procedure of other TDSPs. | Closed | 2006-11-06 | Resolved 11/6/2006 | JG Email
5.4 | Requirements Clarification | 867_03 | n/a | How to handle 867_03 cancel/rebills that occur after Version 3.0 is in production but are for billing periods prior to Version 3.0 and the months being cancelled were estimated? The REF~5I segment for Estimates was added to the 867_03 transaction in Version 3.0 and does not exist in Version 2.1. AEP submitted proposed solution for TDSPs to send 867_03s with a "D10" reason code (Other) in the REF02, the reason explanation of "Before V3.0", and Estimation counters of "0". It was determined to use this proposed solution at 12/11/2006 MCT meeting and the Market Requirements document have been redlined documenting these changes. | Closed | 2006-11-06 | Discussed 11/6/2006; Resolved 12/11/2006 | CR Email
6.1 | TML Requirements Clarification | 814_14 | n/a | Question: How will TML be updated to distinguish 814_14 Drops to AREP from 814_14 Drops to POLR? Answer: TML is being updated to reflect if transactions are related to a Mass Transition so the 814_14 will have an indicator that it is a Mass Transition Drop. You will be able to distinguish between the two. | Closed | 2006-11-21 | 2006-12-11 | KP Email
6.2 | Requirements Clarification | 814_15 | n/a | Question: Is ERCOT prepared to receive 814_15 rejects for ANSI errors? Answer: Nothing is changing with Texas SET 3.0 that would change the way an 814_15 reject is handled | Closed | 2006-11-21 | 2006-12-11 | KP Email
6.3 | Requirements Clarification | n/a | n/a | Customer Billing Contact Information File. When ERCOT sends a response file identifying the records that have failed, does ERCOT expect the CR to fix the file and re-submit a new file? The CR has until the 15th of the corresponding month to re-submit a corrected file. Is there a naming convention for the ERROR file? MTCRCustomerInformationERCOTResponse. Or will there even be an error file sent to the originating CR of the April and October customer billing contact information file? Yes. Can an "umbrella" CR with multiple DUNS numbers send one production file for all of their entities' ESI IDs and can one DUNS number be included for all recores in the file? No, CRs that have more than one DUNs number must submit separate files for each DUNs number. | Closed | 2006-11-21 | 2006-12-11 | JR Email
6.4 | Requirements Clarification | n/a | n/a | What happens if a customer calls in for a MVI/MVO during a Mass Transition? How does this affect the data we have in the system and the ERCOT process? MIMO rules will continue to handle the processes. | Closed | 2006-11-21 | 2006-12-11 | KP Email
6.5 | Requirements Clarification | n/a | n/a | How will first notice of the ESI IDs be provided (to POLR CRs) and what data will we get? This is prior to receiving the 814_14? Lists of ESI IDs will be generated during the ESI ID allocation process and at the time the 814_03s are sent out. | Closed | 2006-11-21 | 2006-12-11 | KP Email
6.6 | Requirements Clarification | 810, 867 | n/a | Can the TDSP continue to send us (CR) 810 transactions even after the 867 is estimated for the 3rd time? Yes. | Closed | 2006-11-21 | 2006-12-11 | KP Email
6.7 | Requirements Clarification | n/a | n/a | Will the TDSP disconnect Special Needs customers or will they be estimated like critical load customers? All TDSPs will follow their processes for Special Needs Customers; no changes. | Closed | 2006-11-21 | 2006-12-11 | KP Email
6.8 | Requirements Clarification | n/a | n/a | If TDSP installs a new meter, what do the transactions look like? Does CR get an exchange? Yes. Is there a gap in consumption? No. No changes to existing processes. | Closed | 2006-11-21 | 2006-12-11 | KP Email
6.9 | Requirements/Implementation Guide Clarifications | 810 | n/a | How will charges show on the 810 for meter changes made as a result of TDSP Action following Denial Of Service, e.g. if a remote Reading Meter is installed or Service is disconnected and subsequently reconnected? What codes will be used? Using existing SAC04 codes; see TX SET 810 Implementation Guide. Will the charge reference a service order number if applicable? Yes. | Closed | 2006-12-11 | 2006-12-11 | KC email
7.1 | Requirements Clarification | 867 | n/a | Confirmation from TDSPs: After the original 867/810, if there is a cancel, all restatements therafter will be a '05', not a '00' | Closed | 2007-01-24 | 2007-01-24 | JR Question
7.2 | Requirements Clarification | 814_14/safety net MVIs | n/a | How will the POLR CR know that the TDSP has worked a safety net move-in? How did the Market decide the POLR CR would be notified? ERCOT has no way to notify the POLR of this since a safety net is between the CR and TDSP. 814_04s will reject with 'SNP' from TDSP. Until ERCOT gets the safety net move-in transaction, ERCOT will continue to try to drop the transaction. The list of esi ids to the POLR CR and the transactions may not match for the POLR CR due to this situation. The POLR CR should continue to attempt to reconcile the missing 814_14 transactions to their list. | Closed | 2007-01-24 | 2007-01-24 | Question from 1/03/07 Texas SET Conference Call
7.3 | Customer Billing Contact Information File | n/a | n/a | When will the CRs be provided the NAESB information in order to test sending and receiving the Customer Billing Contact Information file in Flight 0407? CRs will receive the NAESB information prior to Testing Worksheets being unlocked during Flight 0407 registration (March 6, 2007). This information will be disseminated via Market Notice and will not be posted on MCT documents on the public website due to security concerns. | Closed | 2007-01-24 | 2007-01-24 | JR Email
7.4 | Requirements Clarification | 814_08 | n/a | Can the CR submit the MVO as soon as they get the 814_08 with "EFR" because the CSA should have been deleted at ERCOT by that time? CR can submit MVO as soon as they receive the 814_08 with EFR. ERCOT will not send until the CSA is terminated. | Closed | 2007-02-05 | 2007-02-05 | JR Email
7.5 | Requirements Clarification | 814_14 | n/a | Does the POLR have to wait until we get the 867_04 initial read to submit the MVO based on the Date in the 814_14 "RL" DTM~376? POLR does not need to wait to submit the MVO. ERCOT systems will recognize the Drop and allow the MVO as soon as the drop is created. | Closed | 2007-02-05 | 2007-02-05 | JR Email
8.0 | Customer Billing Contact Information File | n/a | n/a | Regarding formatting of the Customer Billing Contact Information file (.csv): 1.) On the data values, should there be no quotes, single quotes, or double quotes? The validations for this file were built around TX SET implementation guide validations. As a general rule, it is recommended that special characters (including quotes, single quotes, or double quotes) be avoided. There is the chance that these would impact ERCOT's systems and/or a POLR CR's systems. 2.) Can there be embedded commas? Yes, since this is a pipe-delimited file 3.) Are there MS Excel rules? (e.g. no spaces outside quotes) Excel rules are not considered as this is only a .csv flat file | Closed | 2007-02-15 | 2007-02-19 | SS Email
8.1 | POLR Rule Customer Class | n/a | n/a | CR asks: What should we do if we received a drop for a customer that belongs in a customer class that we are not supposed to serve as a volunteer POLR? That is, what do we do if ERCOT sends a drop for an ESIID whose customer class is a 3 but we re only supposed to get 1s as the volunteer POLR. Do we reject it? If so, what code? Will ERCOT do anything with the reject? Should we contact ERCOT directly? CR needs to log a MarkeTrak issue in this situation and ERCOT will work it manually. The CR does not need to send an 814_15 reject. | Closed | 2007-02-16 | 2007-02-16 | JG Email
8.2 |  |  |  | In the event of a Mass Transition, is there a possibility of receiving a backdated switch request? This could only happen if there is a major system outage at ERCOT. This will not be the normal situation. Date used is T +2. | Closed | 2007-02-21 | 2007-02-21 | BG question to KS
8.3 | Customer Billing Contact Information File |  |  | What is the NAESB file type used in sending Customer Billing Contact Information file? NAESB file type "FF" | Closed | 2007-02-21 | 2007-02-21 | JR Email
8.4 | Denial of Access | 867_03 | n/a | If a REP requests a re-read after a DOA estimate and the TDSP gets an Actual Read and does a cancel/re-bill of the previous 867_03 Estimate, what will the counter in the re-billed 867_03 show, given that the re-bill is an Actual? CNP, AEP, and TNMP will not reset the counters; TXU ED will reset the counters | Closed | 2007-02-21 | 2007-02-21 | DOA Conference Call follow-up at MCT
8.5 | Implementation Guide | 814_14 | 2006-692 | Should the change log in the 814_14 Implementation Guide be updated to state that the TS code was added to the BGN07? No, MCT stated that the brief change control description is sufficient | Closed | 2007-02-21 | 2007-02-21 | KC email
8.6 | Change Control | 814_08 | 2006-692 | Bullet number 5 on the summary of changes states that the ASI01 was changed on the 814_08; however the change in the Implementation Guide was to the REF~1P; what should be done? MCT corrected the change control to show that the element referenced is the REF02 of the REF~1P on the 814_08 and a note was added to the change control documenting the correction. | Closed | 2007-02-21 | 2007-02-21 | KC email
8.7 | Implementation Guide | 814_03, 814_08, 814_14 |  | Is the verbiage in the gray box for the TS code in the BGN07 correctly stated as "required as a response to ERCOT initiated transaction…" when these transactions are initiating transactions? MCT agreed the term "response" in the gray box is referring to the TS code and not to the type of transaction. | Closed | 2007-02-21 | 2007-02-21 | KC email
9.1 | Customer Billing Contact Information File |  |  | What file extension should be used on the CBCI? If the file is encrypted = .pgp but should still = .csv once decrypted | Closed | 2007-03-29 | 2007-03-29 | email
9.2 | Customer Billing Contact Information File |  |  | When the ERCOT receives the Customer Billing Contact File and there are issues with some of the records, but not all, does the CR resend the entire file or the ones that there were issues with? The CR will need to resend the entire file since ERCOT saves the most recent file for potential use during a mass transition. | Closed | 2007-03-29 | 2007-03-29 | DE email
9.3 | Customer Billing Contact Information File |  |  | Can ERCOT provide test data for our CBCI file? ERCOT will not provide test data for the file; the purpose of testing this during Flight 0407 is to have the CR send a file containing their own test data. | Closed | 2007-03-29 | 2007-03-29 | email
9.4 | Customer Billing Contact Information File |  |  | Question about the Customer Billing Information file: We have many customers for which we do not have a phone number. I do not recall the market discussing what to send when information is not available. Our system is programmed to populate this field with all 9s in these cases. Will this cause us to "reject" at ERCOT? ERCOT will only check to see if the field is populated. | Closed | 2007-03-29 | 2007-03-29 | JG Email
9.5 | Customer Billing Contact Information File |  |  | Question about the Customer Billing Information file: What about the zip code formatting? The RMG says ERCOT will validate the format. Does that mean you will validate whether it is ##### or #####-####? Note that this is a postal code to allow for addresses outside the U.S. Also, punctuation (spaces, dashes, etc.) must be excluded. Postal codes will only contain uppercase letters (A to Z) and digits (0 to 9). | Closed | 2007-03-29 | 2007-03-29 | JG Email
9.6 | Customer Billing Contact Information File |  |  | CBCI File name stated in RMG and not in Market Requirements document. File should be named according to RMG but ERCOT will not reject if the name is different. | Closed | 2007-03-29 | 2007-03-29 | email
9.7 | Customer Billing Contact Information File |  |  | If the larger CRs send a single CBCI file is ERCOT OK with the size of the file? | Open | 2007-03-29 |  | MCT question
9.8 | Requirements Clarification | 814_12 |  | Is there a MIMO rule that prohibits a CR from sending an 814_12 on a priority MVI order that is already in a schedule status? While there is no rule that specifically prohibits submitting a date change on a scheduled priority MVI, the fact that they are already in their window when they schedule will mean that any date changes will be rejected for being in the window. They CAN be date changed prior to being scheduled. (And if for some reason we receive a MVI with a priority code that is requesting a date further in the future, or that is scheduled further in the future, it could be date changed.) | Closed | 2007-03-29 | 2007-03-29 | BP email
9.9 | Requirements Clarification | 814_16 |  | Is there an evaluation window for priority MVI orders? The evaluation window for Priority MVIs is the same for regular MVIs – 2 business days prior to the SMRD. Since priority MVIs are requesting today or tomorrow, it means that ERCOT will receive them and schedule them within that window. | Closed | 2007-03-29 | 2007-03-29 | BP email
9.1 | Implementation Guide Gray Box and example | 867_03 |  | 867_03 – sub-element separators are stated incorrectly as element separators in REF~5I in both gray box and example. Will be handled as a clean-up after production implementation of 3.0. | Closed | 2007-03-29 | 2007-03-29 | multiple MP emails