## Slide 1: Texas Nodal Market Implementation Scope Change Control Process Modifications March 7th, 2007

## Slide 2: Of the 3 existing processes, only one is formally administered by Nodal PMO to assess impacts before submittal to PRS…
Draft NPRR
TPTF
PRS
TAC
Board
Approved
NPRR
Draft NPRR
PRS
TPTF
TAC
Board
Approved
NPRR
Draft NPRR
Nodal PMO (Impact
Assessment)
PRS
TAC
Board
Approved
NPRR
1
2
3
TPTF
Author solicits help from TPTF in developing a NPRR before PRS review
PRS requests TPTF review of NPRR submitted directly to PRS
Nodal Program initiated NPRR

## Slide 3: To clear the backlog and improve the effectiveness of the NPRR approval process, we propose the following…
The current updated baseline we are targeting is issues raised on or before March1st, 2007
Within these are –
  30 outstanding approved NPRRs
  15 draft/pending NPRRs
  22 white papers (8 EMS/MMS & 14 IDA white papers)
  5 change requests that are not NPRRs or white papers
The Nodal Program will have one impact assessment process in 2 steps
  Impact categorization (IC) i.e. 1-4 & essential for “go-live”
  Detailed cost & schedule impact assessment by projects/vendors (IA) for all category 1’s & 2’s
For the backlog, category 3 & 4 will be accepted within the existing budget/contingency
For the backlog, categories 1 & 2 will have a cost and schedule impact leading to suitably packaged change requests
Going forward, categories 1, 2 & 3 will be subject to potential change requests ( as designs and development will have progressed that much further)
Going forward, category 4 will be accepted within existing budget
The Nodal Program proposes a “Wednesday meeting” with all projects to clear the backlog of approved NPRRs/pending NPRRs/White papers as well as going forward to conduct impact categorization (IC)

## Slide 4: Proposed detailed process for Nodal protocol impact assessment…
The Impact assessment team will report the status of NPRRs to TPTF, PRS, CCB and the Nodal Steering Board on a periodic basis
Draft NPRRs
being tabled if
found not
essential for
Go-Live
PRS does an initial
language review
before sending it to
the Nodal PMO for
impact assessment
Nodal PMO to
submit a detailed
impact assessment
before a second
review by PRS
Draft NPRRs not
seeking
additional funds
and essential for
Go-live will be
accepted within
existing budget
A
C
B
D

## Slide 5: Some of the implications of the revised process are...
Draft NPRR
Impact
categorization
Is it essential
For
Go-Live
Confirm with PRS
Draft NPRR
“Tabled”
NO
A
Draft NPRR
Impact
categorization
Is it essential for
Go-Live
Pending NPRR
YES
B
Does the impact
require additional
funds?
NO
A draft NPRR that is not essential for go-live should be “tabled”
For the backlog, an approved NPRR essential for go-live and not seeking additional funds (i.e. category 3 or
4) will not go through the impact assessment process – we accept the costs within existing budgets/contingency
Draft NPRR
NODAL Impact
Assessment Process
PRS Second Review
C
All NPRRs to go through the Nodal PMO initially, instead of being directly forwarded to PRS for their second review
D
Draft NPRR
Does it have detailed
Cost & schedule impact
Information?
PRS Initial
Review
Draft NPRR
“Tabled”
NO
PRS to “Table” draft NPRRs with no cost/schedule information
PRS initial review
TPTF review

## Slide 6: The initial impact categorization is done across four different categories with 1 being a high impact and 4 being the least…
Impact category | Implication
Category 1 impact Core Functionality (Code & Internal processes, all Algorithms, and Emergency & Safety) | Change Request (CR) will have implications to cost and/or schedule Implementation before Nodal “Go Live” requires inclusion into a Release Post Nodal “Go Live” creates “boxed” language in the Nodal Protocols Recommendation: Case by case inclusion into Nodal Program.
Category 2 impact Procedural (Business process, procedures, display presentation) | Change Request (CR) could have implications to cost and/or schedule Core Systems do not require changes, but surrounding business processes and procedures will need to be changed Implementation before Nodal “Go Live” requires inclusion into a Release Post Nodal “Go Live” creates “boxed” language in the Nodal Protocols Recommendation: Case by case inclusion into Nodal Program.
Category 3 impact Minimal (Documentation only) | No impact to core systems or business processes Requires updating documentation for traceability Recommendation: Inclusion into Nodal Program
Category 4 impact None (No impact to systems or already part of base product) | No impact to core systems or business processes Recommendation: Inclusion into Nodal Program