## Slide 1: Texas Nodal Market Implementation Executive Dashboard Concept & Approach March 2007

## Slide 2: The PMO has delivered a balanced scorecard to give a one-page view of program progress…
This formula represents the objectives against which Program progress will be measured
There is a growing demand for more detailed metrics and greater visibility into Nodal Progress
The Program currently did not have a single source that provided a consolidated picture of progress
This document is a guide for understanding each measure contained in the balanced scorecard, and how to interpret the data displayed

## Slide 3: The program success criteria have been applied to the four elements of a balanced scorecard…
Nodal Program Progress
ERCOT Readiness
Nodal Delivery
MP Readiness
Ensure system readiness
Ensure process readiness
Ensure people readiness
Ensure staff satisfaction
Protocol alignment
Program Timeliness
Manage Budgetary performance
Manage risk effectively
Manage quality compliance
Manage change effectively
Ensure MP system readiness
Ensure MP process readiness
Ensure trained Market Participants
Ensure Market Participant Satisfaction
Nodal
Program
Success
ERCOT
Readiness
MP
Readiness
Nodal
Delivery
=
*
*
Readiness Delivery
The objectives against which Program progress will be measured
Measures Delivered
Measures to be Delivered
Key

## Slide 4: Measures delivered and are available to use…
Perspective | Measure | Current Performance Indicator | Metric / Formula | Rationale
Nodal Delivery | Deliver Nodal program aligned to defined protocols | Tracing of requirements to Nodal Protocols | % of protocols traced to requirements – All Protocol sections must be addressed by at least one requirement | Ensuring that initially, the Nodal requirements have appropriate coverage of the Nodal protocols.
 | Manage budget effectively | Program EAC Variance | Actual spend vs. normalized budgeted spend as a % over time | Performance against budgeted spend can give a trended project indicator of future performance, whilst still lagging.
 | Manage risk effectively | Top 3 risks & top 3 issues | Risks and issues prioritized by impact and probability | These are the most important risks and issues to have effectively managed and mitigated – and therefore should be given prominence.
 | Manage quality compliance | Adherence to Nodal Quality Plan | % of projects in line with time-driven program milestones | It is important to ensure that all Nodal projects are in line with the quality objectives of the program
ERCOT Readiness | Ensure system readiness metrics are achieved on time | Agreed verified metrics per date in advance of delivery | # of metrics verified complete vs. metrics scheduled to completed by date, as a % | Completion is planned to occur in advance of test start date.
 | Ensure process readiness metrics are achieved on time | Agreed verified metrics per date in advance of delivery | # of metrics verified complete vs. metrics scheduled to be completed by date, expressed as a % | Completion is planned to occur in advance of test start date.
MP Readiness | Ensure system readiness metrics are achieved on time | Agreed verified metrics per date in advance of delivery | # of metrics verified complete vs. metrics scheduled to be completed by date, expressed as a % | Completion is planned to occur in advance of test start date.
 | Ensure process readiness metrics are achieved on time | Agreed verified metrics per date in advance of delivery | # of metrics verified complete vs. metrics scheduled to be completed by date, expressed as a % | Completion is planned to occur in advance of test start date.

## Slide 5: Measures to be delivered once appropriate data exists…
Perspective | Measure | Current Performance Indicator | Metric / Formula | Rationale
Nodal Delivery | Program Timeliness | Tracing of requirements to Nodal Protocols | % of protocols traced to requirements. | Ensuring that initially, the Nodal requirements have appropriate coverage of the Nodal protocols.
 | Manage change effectively | Program EAC Variance | Actual spend vs. normalized budgeted spend as a % over time | Performance against budgeted spend can give a trended project indicator of future performance, whilst still lagging.
ERCOT Readiness | Ensure people readiness | Agreed verified metrics per date in advance of delivery | # of metrics verified complete vs. metrics scheduled to completed by date, as a % | Completion is planned to occur in advance of test start date.
 | Ensure staff satisfaction | Agreed verified metrics per date in advance of delivery | # of metrics verified complete vs. metrics scheduled to be completed by date, expressed as a % | Completion is planned to occur in advance of test start date.
MP Readiness | Ensure trained Market Participants | Expectations met/missed | # of expectations met vs. total # of distinct expectations | MP satisfaction is a lagging indicator of external confidence in delivery
 | Ensure market participant satisfaction | Expectations met/missed | # of expectations met vs. total # of distinct expectations | MP satisfaction is a lagging indicator of external confidence in delivery

## Slide 6: Each measure on the dashboard has been created based on operational data…

## Slide 7: The current version is displayed below…

## Slide 8: Frequently Asked Questions…
Q: How do I access the scorecard?
A: Follow the link below to the Nodal Sharepoint:
http://cpwp002d:8061/Nodal%20Dashboard/nbs.aspx
Q: Who gets to see the scorecard?
A: From 5 March onwards, the Nodal leadership and Nodal project teams are able to see the scorecard. Further distribution will be decided at a later date.
Q: How will I be affected by the scorecard?
A: The scorecard will do no more than raise the visibility of existing data sources within the program to Nodal leadership
Q: How can I make suggestions/changes to the scorecard?
A: Suggested changes should be submitted to the PMO, which will then be subject to the scorecard’s change control process