## Slide 1: Market Coordination Team Update Retail Market Subcommittee April 11, 2007 Susan Munson Retail Market Liaison

## Slide 2: Risks / Issues
Issue | Mitigation | Owner
PR50121_07 RBP – Stabilization necessary for successful implementation | Schedule management Milestone completion | ERCOT
ERCOT February Retail Release | Schedule and resource management Milestone completion | ERCOT
PUCT Mandate of 07/01/2007 poses tight timeline | Schedule and resource management Milestone completion | All
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 3: Project Schedule
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 4
PR40038_01 Status
Status:
  On target for schedule, budget, and scope
Project Phases:
  Initiation – Completed
  Planning – Completed
  Execution – Mandated completion date July 1, 2007; Go-Live 06/24/2007
  Closing – Target completion is post go-live
Recent Activity as of March 5, 2007:
  Complete Test Plans, Scripting and Data Prep for ITEST
  Complete Core Build TIBCO, Siebel, Paperfree, TML, NAESB, EIS)
  Migrate Core Build to iTEST (TIBCO, Siebel, Paperfree, TML, NAESB, EIS)
  Begin UAT on 03/05/2007
Next Steps for ERCOT as of March 5, 2007:
  Finalize Build ETS and Reprocessing
  Complete Market Test Plans, Scripting, and Data Prep
  Set Up Market Test Environment
  Migrate to Market Test Environment
Next Steps for MCT:
  Continue to monitor Market issues and progress
  Continue work on Production Implementation and Contingency Plan
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 5: Change to Market Requirements – March MCT
Added “Appendix F: Replacement Invoice and Usage Data Example” to clarify Ts & Cs Requirement 3: Adjustments To Previously Transmitted Data
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 6: Information on PR 40038
Draft Production Implementation and Contingency Plan for Texas SET 3.0
  Conference Call to be held to discuss the Draft Plan
        Thursday, April 12
        10:00 – 11:30 am CPT
        512-225-7280 (pass code: 1571)
  Draft Plan is located in Key Documents on MCT page of ERCOT.com
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 7: Reminder: Where are Texas SET 3.0 Key Documents Kept?
  MCT page – ERCOT.com
  http://www.ercot.com/committees/board/tac/rms/mct/index.html
  And what is there?
  Texas SET Version 3.0 Requirements Final Version 1.9
  Texas SET 3.0 - MCT Issues & FAQs Log
  Texas SET Version 3.0 Change Controls
  Texas SET Guides Version 3.0
  Texas SET Version 3.0 Implementation Plan DRAFT
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 8
Meeting Dates and Locations 2007
  April 26 – ERCOT Met Center
  May 24 – ERCOT Met Center
  June 27 – ERCOT Met Center or Conference Call
  July 25 – Location TBD
  August 29 – Location TBD
(Note: all meetings are held in conjunction with TX SET meetings)
Future Meetings/Market Communications
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 9: ERCOT Contacts
ERCOT Project Manager ERCOT SR. Business Analyst
Hope Parrish Jennifer Frederick
hparrish@ercot.com jfrederick@ercot.com
512-248-6522 (w) 512-248-6733 (w)
512-771-9582 (c) 512-413-0815 (c)
ERCOT Market Liaison
Susan Munson
smunson@ercot.com
512-248-3881 (w)
512-826-0564 (c)
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 10: Questions?
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO