## Slide 1: ERCOT Project Update Commercial Operations Subcommittee April 10, 2007 Adam Martinez Market Operations Division Projects Organization
Please Note: These slides are best viewed in Slideshow mode

## Slide 2: 2007 MO PPL
Unplanned 2006 Carry-over Projects
(Green Shaded Area)
Projects ABOVE the Capability Line
(Orange Shaded Area)
Projects BELOW the Capability Line
(Yellow Shaded Area)

## Slide 3: Unplanned 2006 Carry-Over Projects
Only remaining active project is ERCOT.com Registered Access
  Scope of project is presentation of Operations and System Planning Data (Tmaps) data on the ERCOT public website
  This project was transferred from the RO PPL to the MO PPL in late March
  RMS requested the transfer, COPS informed at March meeting

## Slide 4: Projects ABOVE the Capability Line
New project added above the capability line – Collage Infrastructure Project
  ERCOT source, Priority 1 – Critical, Rank 8.5, $250-$500K initial budget
  Collage is the ERCOT’s content management tool for its public websites
    ERCOT.com, Texas Nodal Market Implementation website, Operations and System Planning Data, other smaller websites (Retail Testing Website, internal ERCOT employee sites)
  Project addresses potential limitations with Collage environments ability to manage and maintain websites’ content
    Nightly content update process increased from 7 hrs to 12 hrs since last year. Expect trend to continue due to continued growth in volume of content updated to websites
    Options have been analyzed and remedial steps have been taken, but problem requires redesign of Collage architecture and nightly process to mitigate risk of website content delays or failures

## Slide 5: Projects ABOVE the Capability Line
Several projects above the capability line have been cancelled
  Extension of Credit Against OOM Start Up – Requirements fulfilled by ERCOT manual process; no Market impact
  SCE Performance Enforcement Criteria – Requirements fulfilled by ERCOT manual process; no Market impact
  Siebel to L* Rewrite – Scope addresses rewrite of internal ERCOT process using new TIBCO technology. Current process runs as required and TIBCO resources are constrained so business has cancelled project and will revisit need under 2008 PPL Project Process; no Market impact
  Transition of Production Reporting to EIS-Wholesale – Scope addresses transition of internal ERCOT reports that use production as source data to using EIS/ODS as source. Delays with EIS/ODS environment stability and resource constraints for EIS resources resulted in business decision to cancel the project for this year and revisit need under 2008 PPL Planning process; no Market impact

## Slide 6: Projects BELOW the Capability Line
Several projects below the capability line have been cancelled
  Lodestar Web Services – Scope addresses transition of Lodestar extracts/reports that are mass produced to production from the EIS environment using web services; Delays with EIS/ODS environment stability; resource constraints for EIS resources; commitment to deliver Lodestar upgrade, and ability to provide one-off web services via other projects has resulted in business decision to cancel the project for this year and revisit need under 2008 PPL Planning process; potentially limits Market’s access to web services not already scoped in other projects or planned for Nodal
  URC for Uncontrollable Resources - Requirements fulfilled by ERCOT manual process; no Market impact

## Slide 7: Financial Overview
MO PPL Budget Activity | Amount | Notes/comments
Funds released by cancellation of project ABOVE the Capability Line | $619K | Extension of Credit Against OOM Start Up Requirements fulfilled by ERCOT manual process; no Market impact Siebel to L* Rewrite Transition of Production Reporting to EIS-Wholesale
Funds released by cancellation of project UNDER the Capability Line | $0 | Lodestar Web Services URC for Uncontrollable Resources No funds available to release since projects were not above the line and allocated any of the $1.5M funding
Funds requested by addition of new project | $400K | Collage Infrastructure Project
Current Forecast Spend of projects above the Capability Line | $1.495K | Budget range of $1M – $2M
Approved MO Capability Line Budget Funding | $1.5M | Has not changed since initial allocation identified under 2007 PPL Planning process
Budget Variance | $5k | Difference between budget allocation and forecast spend All projects COPS and MOCART want for 2007 are currently funded New projects and/or initiation of projects below the line (with change in priority or rank) will require funding increase and/or impacts to current project budgets

## Slide 8: Questions / Contacts
Adam D. Martinez
Manager, Market Operations Divisional Projects Organization
ERCOT
(512) 248-3883
amartinez@ercot.com
  Page 9