## Slide 1: Market Coordination Team Update Retail Market Subcommittee April 11, 2007 Susan Munson Retail Market Liaison

## Slide 2: Risks / Issues
Issue | Mitigation | Owner
Resource Constraint from May Retail Release | Schedule and resource management Milestone completion | ERCOT
PUCT Mandate of 07/01/2007 poses tight timeline | Schedule and resource management Milestone completion | All
AIX Server Consolidation | Schedule and resource management Milestone completion | ERCOT
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 3: Project Schedule
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 4
PR40038_01 Status
Status:
  On target for schedule, budget, and scope
Project Phases:
  Initiation – Completed
  Planning – Completed
  Execution – Mandated completion date July 1, 2007; Go-Live 06/24/2007
  Closing – Target completion is post go-live
Recent Activity as of April 4, 2007:
  CORE UAT 100% Complete
  Migrate Core Build to CERT (TIBCO, Siebel, Paperfree, TML, NAESB, EIS)
  Begin Connectivity Testing
Next Steps for ERCOT as of April 4, 2007:
  Begin Flight Test
  Begin ETS and Reprocessing Testing
  Finalize Production Migration Tasks
Next Steps for MCT:
  Continue to monitor Market issues and progress
  Continue work on Production Implementation and Contingency Plan
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 5: April Status Reporting - CRs
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 6: April Status Reporting - CRs
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 7: April Status Reporting – ERCOT and TDSPs
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 8: April Status Reporting – ERCOT and TDSPs
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 9: CRs not Reporting - April
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO
Alliance Power Company LLC
Ambridge Energy
Andeler Retail
Current Power and Light LLC
Electric Now LP
Hwy 3 MHP, LLC dba Smart Choice Power
National Power Company Inc.
New Mexico Natural Gas LP dba Texas Power
Pre Buy Electric LLC
Sure Electric LLC
Young Energy

## Slide 10: Change to Market Requirements – March MCT
Added “Appendix F: Replacement Invoice and Usage Data Example” to clarify Ts & Cs Requirement 3: Adjustments To Previously Transmitted Data
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 11: Information on PR 40038
Draft Production Implementation and Contingency Plan for Texas SET 3.0
  Conference Call to be held to discuss the Draft Plan
        Thursday, April 12
        10:00 – 11:30 am CPT
        512-225-7280 (pass code: 1571)
  Draft Plan is located in Key Documents on MCT page of ERCOT.com
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 12: Reminder: Where are Texas SET 3.0 Key Documents Kept?
  MCT page – ERCOT.com
  http://www.ercot.com/committees/board/tac/rms/mct/index.html
  And what is there?
  Texas SET Version 3.0 Requirements Final Version 1.9
  Texas SET 3.0 - MCT Issues & FAQs Log
  Texas SET Version 3.0 Change Controls
  Texas SET Guides Version 3.0
  Texas SET Version 3.0 Implementation Plan DRAFT
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 13
Meeting Dates and Locations 2007
  April 26 – ERCOT Met Center
  May 24 – ERCOT Met Center
  June 27 – ERCOT Met Center or Conference Call
  July 25 – Location TBD
  August 29 – Location TBD
(Note: all meetings are held in conjunction with TX SET meetings)
Future Meetings/Market Communications
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 14: ERCOT Contacts
ERCOT Project Manager ERCOT SR. Business Analyst
Hope Parrish Jennifer Frederick
hparrish@ercot.com jfrederick@ercot.com
512-248-6522 (w) 512-248-6733 (w)
512-771-9582 (c) 512-413-0815 (c)
ERCOT Market Liaison
Susan Munson
smunson@ercot.com
512-248-3881 (w)
512-826-0564 (c)
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 15: Questions?
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO