## Market Enhancements
Enhancements
Category |  | Source | Issue | Issue (Business problem trying to solve) | Market Proposal | Discussion | ERCOT Proposal Comments | Who Submitted | SIR | In or Out Scope?
Business | Annual Validation | MMWG | TDSPs currently getting one MT issue with all ESIs. TDSPs unable to process in timely manner |  | Report # of ESIs within each MT issue not just # of MTs issues | ERCOT could add field on the issue to reflect the # of ESIs included. Some TDSPs would like a one to one for each AV update while ERCOT and other concerned about too many files being sent at one time and the potential impacts to the system | ERCOT needs more clarification on the request: - Is the request for 1 to 1 relationship? Or - Is the request for information on number of ESI IDs to be included in AV issues?
Reporting | Prior year subtype reports | MMWG | Market would like to see #s for prior year | MPs want to be able to see MarkeTrak Numbers from prior year to compare with current year. |  |  | ERCOT believes this is available through current reporting functionality. Need more details if MPs do not agree.
Reporting | Average Completion Time | MMWG | Market would like to see average time to complete MT issues |  | Need to clarify if by all MPs or market average |  | ERCOT needs more details on calculation parameters: - Average time in each state? - Average time from beginning to end? - How would auto close be handled in the calculation?
Business | Escalation Process | MMWG | MPs would like info those that have been escalated, timeframe and the reason, even though comments have been added or issues closed they are still being escalated. | MPs would like to see information on issues that have been escalated such as when, and for what reason, they were escalated. | maybe implement a way to assign issues to the primary escalation contact - but would have to all be users. Or a way to get contact info from issue page. Maybe add a button to escalate issue via email to primary & secondary contacts from the issue itself. | ERCOT to bring process to next MMWG meeting | ERCOT needs more details on what escalation contact is being requested: - What player's escalation contact is needed?
Business | Escalation Process | MMWG | Even though comments have been added, or issues closed, they are still being escalated. | Even though comments have been added to a MarkeTrak issue, or issues is closed, they are still being escalated. |  | ERCOT to bring process to next MMWG meeting | ERCOT presented Escalation Process at 03/23/07 MMWG Meeting - ERCOT has requested specific examples but have received none to date.
Business | Priority Flag | MMWG | TDSPs need to be able to identify priority issues | TDSPs need to be able to identify priority issues | Add priority flag that can be sorted by and reported on - what is included? | Maybe add a field for a date to be worked by. Maybe include critical date field for all issue types. ERCOT would assign certain as priority rather than allow CRs to assign | ERCOT needs more details on priority flag: - what issues need priority flags? - what should constitute priority?
Business | New Statuses | MMWG | Need more detail on TDSP process w/IAS | TDSPs need more detail on the vote state of Inadvertent Gain Issues. | Add 3 new statuses: Received by TDSP & Completed by TDSP | add a button for the tdsp to say that they agree and also a button that says EDI received and 3rd button that all work is done. Cr would not be able to close the issue until TDSP agrees | Redesign workflow rather than just adding new states or buttons - Pending a proposal from Inadvertent Gain
Business | Billing Issue vs. Missing Transactions | MMWG | Some CRs not using types correctly | TDSPs are receiving incorrect issue types because of confusion with issue definitions. Need to restrict tran types on usage billing issues. | Better define how each subtype is to be used, potentially limit subtypes in drop down |  | Need definition from MPs on what tran types need to be included for Billing usage and missing transaction.
Reporting | Volume Limit | MMWG | MPs can only pull 3000 rows at a time | Some MPs need to pull statistics on more than 3000 issues. The limit of 3000 rows is restricting reporting capabilities and the work around is awkward. | Would like to increase to 5K -10K | May look at EIS for solution. This would result in replicated DB to run reports on without impacting users. Otherwise, increasing the row # will result in performance decrease
Other | Technical Distribution List | MMWG | Need better means to communicate w/ tech users | MPs are not able to communicate specifically with technical users. | Create new distribution list: could either be sign-up or new contact type | Maybe have two list - one API and one GUI. ERCOT working on getting setup | ERCOT implemented self-subscribing mailing lists.
GUI | Dashboard | MMWG | MPs would like a screen similar to old FT homepage |  | ERCOT needs more definition on what MPs want |  | ERCOT believes current functionality provides the same information available on FT so needs more details for this request: - What information was provided on FT that is not available via MT Reporting?
Business | IAS Transition Issue | ERCOT | Currently, when the Gaining MP submits an Inadvertent Switch MarkeTrak issue requesting the Losing MP to regain, the Gaining MP must wait for the Losing MP to click the "Begin Work" button before the Gaining MP can click "Agree". | Currently, when the Gaining MP submits an Inadvertent Switch MarkeTrak issue requesting the Losing MP to regain, the Gaining MP must wait for the Losing MP to click the "Begin Work" button before the Gaining MP can click "Agree". | Add a button -- see notes above | When the Gaining MP issues the MarkeTrak requesting the Losing MP to regain, once issue is created they should have the ability to click the "Begin Work" and "Agree" buttons. This would expedite 95% of the pending issues we know have in backlog | Redesign workflow rather than just adding new states or buttons - Pending a proposal from Inadvertent Gain
Reporting | Cell Merge |  | Currently, we are unable to merge cells after downloading reports into Excel format. We understand that this will require reconfiguration by the software vendor. | Currently, we are unable to merge cells after downloading reports into Excel format. | If MPs save to desktop, and open in Excel, this would solve the issue | Enable cell merge option. | Users are able to merge cells if saved to your computer first. When you select the Excel version you are given a choice of "open" or "save", you should select save. When you open from the download you are using a limited version of Excel and this is why all functionality is not available.
GUI Look and Feel | Contact Page |  | We have been unable to determine escalation MP contact’s for Inadvertent Switches utilizing MarkeTraks directory format. | We have been unable to determine escalation MP contact’s for Inadvertent Switches utilizing MarkeTraks directory format. | Search on contact page does not work with space - you must include either % or * | Create a MP contact page that mirrors the FasTrak contact page | ERCOT believes this is not a change to current functionality and is a training issue. - ERCOT can verify this if provided with a specific example.
GUI Look and Feel | Cursor Placement |  | Currently, when you click the “Search’ button, the cursor is positioned in the “Keyword(s)” field by default. | Currently, when you click the “Search’ button, the cursor is positioned in the “Keyword(s)” field by default. | Will request vendor to place in first field upper left-hand side | Place the cursor in the “Issue ID” field or allow the user personal settings capability. | ERCOT has asked for a vendor enhancement.
Other | Associate DUNS |  | Currently, the Marketrak tool is DUNS specific thus making it difficult to detect new issues as the user must sign on under each certificate to query. The FasTrak tool accommodated all ESID’s no matter the type i.e. SESCO, AE SMB Non-Res, AE Res, etc. | Currently, the Marketrak tool is DUNS specific thus making it difficult to detect new issues as the user must sign on under each certificate to query. The FasTrak tool accommodated all ESID’s no matter the type i.e. SESCO, AE SMB Non-Res, AE Res, etc. | Potential security issue. Tied to DCs. | Tie all associated DUNS together to create a more efficient reporting/querying process. | ERCOT security requirements prohibit associating multiple DUNS numbers to a single digital certificate.