## Sheet1
MarkeTrak - Phase 2 Requirements
| Requirement | Business Reason | discussion
1 | setup a MT distribution list - These distribution lists would allow a 3 way communication between ERCOT to MPs, MPs to ERCOT, and MPs to MPs | From lessons learned, allow a way to have a 3 way communication | done
2 | Provide update via API whenever a Market Participant's visability to an issue has been removed. | A need for an end to end process for the issue. From the API, we pull the information into our database - updates are made as changes are made to the issue. If ERCOT removes us from the issue, we are not aware. It remains as an active issue on our end because nothing has been sent on the API to inform us that we have been removed. It has definitely impacted our reporting. | "ERCOT Intervention" or issue deleted, would an email help?
3 | Bulk Insert, If a file is entered twice, 1) does it validate so it can not upload the same file name 2) bulk insert to withdraw | In the instance a file is loaded multiple times, need a way to withdraw the issues so that there are not duplicates. | SIR 11233 - next release
5 | Usage and Billing Subtype - only have the following tran-types available in the drop down: 867_03, 810_02, both, 867_03F | Will better define the subtype for usage and billing. Today the tran type is left blank, or may enter with 'all' which does not allow clear understanding of what is being requested. It will also help when no comments are provided. For MP's who have an automated process, will make their process more efficient.
6 | MarkeTrak should have the ability to Query List back to GO Live 11-13-06 in order to sync up systems. |  | need to brainstorm, new request type?
7 | Reports - Report by: drop down should have "year" as an option | Currently, when creating year to date reports the columns have to be added together to get totals by subtype. More efficient | Serena ticket: 5163626
8 | Reports - Total by row, column, | Currently limited on the way you total by row and column
9 | DEV Issue Sub-Type 'IDR usage present MP not ERCOT', add a 'TOTAL' field to GUI. This field would be required. Also map this to the API.
10 | Consistent sub-type verbiage requested across Bulk Insert & GUI grids.
11 | Bulk Insert Stoptime logic is adding one day to the date once a user inputs desired stoptime. Create issue with actual stoptime (date) that's requested by submitter. |  | SIR 11208 - next release
12 | On the GUI, when creating high date stoptime (i.e. 12/31/2037), if the user adds a timestamp in the text box (23:59:59), the issue creates but can not be withdrawn [if user needs to]. To enhance, validate on the date field so that if a timestamp is not needed, inform the user and do not create issue. |  | need discussion
13 | Remove 14-day wait from 'Auto Complete' to 'Auto Complete (Closed)'. Recommend transitioning straight from 'Pending Complete' to 'Auto Complete (Closed)' after 14 days {as oppsed to 28 days from 'Pending Complete' to 'Auto Complete (Closed)'}. |  | need discussion
14 | DEV LSE Issues: Once TDSP modifies date(s), ALL parties involved in issue should be able to view the Modified date. |  | need discussion
15 | Reports - Request higher limitation (or none, if possible) on current 3,000 row detail that users are able to export at one time to excel. Recommend at least 10,000 rows. |  | looking at ESI solution
16 | DEFECT - Reporting: When exporting details to excel EXCEEDING the 1st set of 3,000 rows and upon clicking the 'Excel' Button in report view, only the 1st set of 3,000 rows is actually exported to Excel. Using that 'Excel' button, logic should export the appropriate set of rows user is requesting (i.e. Last 200 rows). |  | discussed a resolution in 3/28 Retail Market Call
17 | DEFECT - Escalation notice functionality for DEV Issues appears not to work. |  | need discussion
18 | Reports - Search Filter should allow the user to utilize key word 'OR' instead of only 'AND' when querying the tool.
19 | For TDSP submitted DEV LSE Issues, allow user to proactively enter information in the field 'Service Hist With Duns for Affected Period' [if user sees fit at the time of submission]. This field would be optional. Map to GUI, Bulk Insert and API.
20 | Add the MarkeTrak Website as a permanent Link | More efficient to have the website available like TML. Many not aware of the website. Location of User's manual | SIR 11036 - next release
21 | Remove the "notes" option from the action drop down (may just need to have inquiry since there are notes that exists.) | Notes were being used instead of the comments field. The notes was not mapped in the wsdl and xsd for the API to pull in. In working through an automated process comments were not available. | done
22 | Define the tran_types to the sub type | Defined in the users guide | UG
23 | Clarify the use of the transition buttons. Ex. Instead of choosing the "complete" transition, the MP is selecting "Return to xxx" | Buttons need to be defined in the users guide. Examples should be provided. | UG
24 | Admin role - how to use copy function to set up user, add to users manual | Add copy procedure in users manual when adding a new user | UG
25 | Add information on the ERCOT Initated and LPA issues to the users manual - (need to understand as a MP receiving the issues) | Even though ERCOT is the only one who initiates the LPA and ERCOT initiated issues, we need to know the format of the spreadsheet, required and optional fields to facilitate in automating our backend process | UG
26 | ERCOT does not support the & sign in the API ( may be other characters) | Text fields, ex.Rec&apos;vd monthly usage files- also issue with pecent sign | for journal or text fields
27 | ERCOT should create a report to monitor issues that are created but not submitted | Prevent issues sitting in pending. | escalation?
28 | When opening a ticket with the ERCOT help desk to log a problem, we are not given a ticket to follow up on. Sometimes we never hear anything on the tickets we open |  | outside scope
29 | When adding a new user, they should have access to all issues from day one, not from the time they are set up in MarkeTrak | I | UG contains process to grant access to new users to old issues, vendor contacted
30 | Possibly add a Service Order Sub Type to D2D | Currently there is not a subtype for service order transactions. | fields?
31 | In the Workflow for Missing transaction - many time the issue is opened to the MP, instead of ERCOT, should this default to ERCOT
32 | Processing flow: beyond capablility to process therefore is hangs in an infinite retry. Transaction model, fails while processing > throw out > do not place back in que |  | need more detail
33 | Ability to send comments on all transitions | Most transitions comments are added. Currently it is a two step process. ( if set up to allow comments - what is the impact to the Quick Transitions) | eliminates Quick transitions
34 | Load Profile as individual MT issues - allows the backend process to work, better tracking of esiids and the amount of work | Allows automated process to work on these types of issues. More accurate reporting on volumns.
35 | A few fields not present in the WSDL (dev) a comment field - not issue comment |  | need more detail
36 | Database - MarkeTrak needs a Process History |  | need more detail
37 | Revise the IAS workflow - needs to flow through the different CR's to vote, then transition to the TDSP. If one of the CR's disagrees, then the issue goes to ERCOT | see proposed workflow - add a return button that would reset the "vote" of both CR's
38 | Better monitoring at ERCOT for downtime |  | outside scope
39 | Define create date and submit date in drop downs for reports | For reports - start date = | UG
40 | Add the 65004 to the drop down menu | Was left out of the drop down on the intitial roll out | SIR 10957 - next release
41 | Auto complete - should reflect "closed" | For reporting - the autocomplete issues appear to still be open | SIR 11205 - next release
42 | Contacts - is there a way to have a default, |  | defaul owner?
43 | When entering the Tran_type - needs to be the trantype of the transaction the CR is needing. (many times the tran type and what is asked in the comment are not the same | Training issue | UG
44 | Document wsdl | API documentation for MP's to have. Allow the development of API | API development guide
45 | Service period Start date added but is optional for missing transaction, projects, seibel chg/info, and other subtypes |  | are you requesting it be mandatory?
46 | Service period Start date added and is required for Rep of Record | Only required field is esiid - not enough to determine rep of record. Usually in the comments, the CR will specify a particular time period. Sometimes it is several months back. | and what? So? Am I missing something?
47 | Make comments required for Siebel chg/info sub types | Need comments to have enough information to research and reply to the issue
48 | Add ISA field and have it required for 997 issues and optional for projects and "other" sub types | This was a request from the March 6th meeting on 2006, there was not enough information provided to answer the issue
49 | Make tran type required for Cancellation w/approval and cancellation without approval
50 | make tran type required for missing txns | Currently, left blank or "all " is entered. Would facilitate automated processing, would give a place to start researching when no comments are provided
51 | make tran type required for usage/billing subtype | currently not always entered, Would facilitate automated processing, sometimes the tran type entered is the 814_01 or 814_16 -
52 | Need to have a process for ERCOT to check to see if rolodex and contacts are populated, and a way to go thru an update process |  | need discussion
53 | IF a MP is no longer in the Market, and there MT issues open to this Market Participant, ERCOT needs to notify MP's involved and close the issue | Issues are being created for MP's no longer in the Market. There will never be responded to and difficult to get action taken on. Should not be allowed to create an issue with MP no longer in market. Also if issues are present and the MP leaves the market, again issues will sit, need a process for handling these issues. | need to document approach
54 | IAS - many issues are in a state of "agreement reached", they are not closing, nor auto closing - some the BDMVI has been sent others the BDMVI has not been sent. Is there a way to verify and close if transaction sent. Is there a way to transition to another state ( possibly a new state) if the transactions has not been sent |  | I think I fixed this? Not sure what BDMVI is
55 | IAS escalation notices - not working quite right. Are they including "new" | yes, currently CR's not seeing these to transition. Also for those who are having issues with the reporting - would be notified in an email they have an issue to work | no, should it be?
56 | Copy/Paste from MarkeTrak to excel, etc. |  | can be done now?
57 | IAS - no agreement reached - in this state since Jan, however comments are still being added mt44457 |  | and the enhancement would be?
58 | Reports - year to date option | more efficient reporting - currently would copy - paste to excel - then format, add cols to get totals | see above request #7
59 | More on reporting in Users manual | An area where MP's are having issues | UG
60 | Can we define states that are "in progress" , "complete" - for reporting - currently define to provide our execs with this weekly |  | I think IssueStatus will work
61 | Unclear how to transition an issue to ERCOT. Looking for transition button 'return to ERCOT', VS using the 'assign owner' button |  | UG
62 | Merge capability for reports - subtype, subtype by state | Streamline reporting - create several reports - copy and paste to make one report | huh?
63 | Improved processing time for API query detail/update/response
64 | when you email from MarkeTrak - need a way to include the email as part of the issue | for tracking and audit purposes - what has been done to resolve issue. | Vendor Enhancements submitted: 5157756/ENH109708 - escalation emails 5157753/ENH109709 - notification emails 5163147/?????????? - Issue emails
65 | have a report type for all DEV | Option available for D2D, but not DEV, would have to run report for each subtype | Parent Project Type
66 | do not allow a change on the title | Reporting issue. - Some are overrideing the title with comments
Amongst each DEV issue sub-type, make population of the ‘Title’ field static. Validation could be done to ensure that a submitting MP can NOT populate this field with information that’s not relevant to that particular sub-type. (i.e. DEV IDR issue 101120: Title field is ‘IDRUsagepresentinbothsystemsbuthasdateissues’ but it’s a ‘In ERCOT system not MP’ sub-type).