## Slide 1: Texas Nodal Program Update
Jerry Sullivan
Executive Director, Texas Nodal Program

## Slide 2: Agenda
Item | Purpose | Page
Overall Program Status | For Information | 3
Market Participate Readiness Seminar Update | For Information | 4
Nodal Progress Highlights | For Information | 7
EDS Plan Update | For Information | 9
NPRR/Scope Change Control Update and draft resolution | For Information | 11
Organizational Development Plan | For Information | 14

## Slide 3: Program remains Amber and is being assessed continually
Scope / Quality
Schedule
Cost
Legend
Summary
Amber
Latest monthly committed cost and forecasts are under by 10% of budget to date. Funding for Identity Management and change controls being defined.
Amber
Amber
Backlog baseline established & impacts categorized. First set of 15 NPRRs passed through ERCOT process. QA plans and metrics finalized for April baseline.
Red
Amber
Green
Estimate at Complete = <$248m
Estimate at Complete = $248 - $263m
Estimate at Complete = >$263m
Go-live = 12/1/08
Go-live = <30 days+
Go-live = >30 days+
Program is aligned with current protocols
Program is aligned to previous version of protocols
Program is not wholly aligned to protocols
ERCOT / MP web services specifications issued on time. Market Readiness Seminar for MP started. Confidence in EDS 4 schedule delivery needs to be improved with greater details.

## Slide 4: Nodal success is dependent on three critical components
The success formula is stark and unforgiving…
Time
12/1/08
Today
Nodal Control
Milestones
Readiness Metrics
Importance to Nodal Success
Progress Indicators
Performance Indicators
…the emphasis will change over time
NODAL PROJECT
ERCOT STAFF
ALL OF US!
YOU

## Slide 5: Market Participant Readiness Update
Market Participant Readiness Seminar held on 4/26/2007
Approximately 125 Accountable Executives and Project Managers attended, representing approximately 70 market participants
Initial meeting concentrated on
  Nodal Overview
  Training
  EDS schedule and plans
  Communications
Message is contained within the “Understanding: Texas Nodal Market Readiness” brochure
Theme: “ NO MARKET PARTICIPANT IS LEFT BEHIND”

## Slide 6: TAC role in Market Participant Readiness
ERCOT is suggesting that TAC be the oversight for Market Participant Readiness
TAC should be a forum for Market Participants to provide feedback on their schedule, and testing capability
TAC should work with ERCOT to adjust Market Participant testing schedule as needed
TAC, with ERCOT readiness inputs, should “manage” the Wall of Shame
In order for Nodal to succeed, TAC must take an active role in Market Participant Readiness

## Slide 7: Major achievements have continued in April…
Vendors, Requirements, and CSDs
  Many vendor base products have been delivered ahead of schedule
  All vendors working on aggressive delivery schedule to make Nodal timelines
  Outstanding approvals relate to EDW (non-critical)
  Overwhelmingly positive response from Market Participants
  Requirements being updated to March 2007 Nodal Protocol Baseline
  All CSDs with the exception of EDW and Disputes (planned for 2Q2007) have been submitted or are approved from TPTF
  Most projects have started detailed design and build phase
Projects
  EMS: Nodal ICCP installation complete
  MMS: Accelerated SCED pre-FAT testing nearly complete and on schedule
  COMS: Lodestar Version 4.7 delivered successfully
  NMMS: Phase 1a delivered successfully
  MIS: prototype delivered early
  Interfaces (EIP): Enterprise Integration Project delivered final ERCOT/MP Interface Specs
  Interfaces (EIP): First interfaces exposed to market for MPs to test connectivity and offers
  Interfaces (EIP): About to select a System Integrator to build interfaces
  Interfaces (EIP): Substantial work in progress on multiple internal integrations, for example analyzing source and sink systems
  MER: Market Readiness brochures for MP readiness created and distributed
  Training: Launched web based training classes
  Training: Launched LMS (Learning Management Seminar) to automate testing
Market Operations Sandbox
  The goal is to prove the feasibility of the architecture and to promote Market Participant engagement
  3 Sandbox interfaces implemented and 19 MPs have tested
  Market Operations Sandbox and interface deployment schedule produced before the 4/30/2007 milestone to TPTF
Control Milestone | Baseline | Actual/Forecast | 
Program Budget baselined | 10/17/2006 | 10/17/2006 | 
Requirements approval | 10/31/2006 | 02/2007 | 
Vendor SOW BOD approval | 12/10/2006 | 02/2007 | 
Key CSD submission | 12/31/2006 | 12/31/2006 | 
Market Operations Sandbox | 01/31/2007 | 01/31/2007 | 
Key CSD approval | 02/28/2007 | 02/28/2007 | 
Interface specs – final | 03/31/2007 | 03/31/2007 | 
First interface exposed to MPs | 03/31/2007 | 03/31/2007 | 
EDS 1 start | 05/15/2007 | 04/01/2007 | 
EDS 2/3 plan shared with TPTF | 04/2007 | 04/2/2007 | 
EDS 2 start | 08/2007 | 07/2007 | 
EDS 3 start | 01/2008 | 07/2007 | 
EDS 4 plan shared with TPTF | 09/2007 | 07/2007 | 
EDS 4 start | 07/2008 | 01/2008 | 
Real Time Go Live | 12/1/2008 | 12/1/2008 | 
Day-Ahead Go Live | 12/8/2008 | 12/8/2008 | 
Future milestones are dictated by the Nodal Build critical path schedule

## Slide 8: Timeline update

## Slide 9: The EDS 1 & 2 detailed planning and execution activities are underway …
EDS 1 (Alarm Processing and Point to Point Verification)
Approach: Approach document drafted and approved by TPTF
Beta Testing: Beta Test identified 10% error rate.
Point-to-Point Verification: ERCOT recommendation for complete point-to-point verification approved by TPTF
EDS Execution: Alarm processing configuration initiated, Point-to-Point testing to begin June 07
EDS 2 (Load Modeling, State Estimator, Network Security Analysis and Network Model Management Verification)
Approach: Draft document issued for TPTF review and comments.
Updated Approach: Revised document to be released week of May 7th.
EDS Execution: Scheduled to begin in May 07.
The diagrams show the EDS timelines and high-level functionality for each of the phase & Beta Test results

## Slide 10: The EDS 3 & 4 detailed planning and execution activities are ramping up …
EDS 3 (SCED, Load Frequency Control and CRR trial Auction)
Approach: Draft document issued for TPTF review and comments.
Detailed Plan: Detailed plan issued for TPTF review and comments.
MP Handbook: Document Market participant EDS day to day testing activities and scenarios. Draft version scheduled for end of May release.
EDS 4 (DAM, RUC, SASM, Settlements and Outage Scheduler, and 168 hour test)
Approach: EDS 4 approach document to be issued for May 5 TPTF meeting
The diagrams show the overall EDS schedule and high-level EDS 3 timelines

## Slide 11: Periodic program baseline synchronization with latest Protocol revisions
40 of the 65 (65%) items have at least 1 project with a high or a medium impact (category 1 or 2)
25 of the 65 (35%) items have all projects with a
minimal or no impact
(category 3 or 4)
Impact categorization continues for new items to get ahead for the next synchronization – work in progress
Backlog list of
65 items
including –
Approved NPRRs
Draft NPRRs
White Papers
Baseline 0
(May, 2006)
Ongoing NPRRs
& white papers
The “Impact Categorization Matrix” helps triage the impacts for all the items across all the projects
Baseline 1
(March 1, 2007)

## Slide 12: ERCOT has an agreed approach to evaluate the system wide impacts of NPRRs
Assign owners to produce suitably packaged “Change Requests”
Group the items for implementation synergies/efficiencies
TCCB analysis – Identify high level recommendations & time frame for implementations (i.e. EDS1/2/3 etc.)
Update schedule, budget and system architecture. Validate timeframes.
TCCB reviews the budget, schedule and technical impact
Submit to CCB for approval
The next steps and … … some implications
All NPRRs to go through the Nodal PMO initially, instead of being directly forwarded to PRS for their second review
A draft NPRR that is not essential for go-live should be “tabled”
For the backlog, category 3 & 4 will be accepted within the existing budget/contingency
For the backlog, categories 1 & 2 will have a cost and schedule impact leading to suitably packaged change requests
Going forward, categories 1, 2 & 3 will be subject to potential change requests ( as designs and development will have progressed that much further)
A total of 11 “Baseline 1” Change Requests are covering all associated NPRRs are in preparation

## Slide 13: Further baselines are envisioned
The process is set up to handle further changes as they come through…
May 2006 Protocols
Current Baseline
Next Baseline
Future Baseline
Baseline advance point
Baseline 2
(TBD)
Baseline 1
(March, 2007)
Current
Future
Baseline 0 and
Approved changes
from Baseline 1
Baseline 1
(March, 2007)
Baseline 2
(TBD)
ILLUSTRATIVE
ILLUSTRATIVE
Baseline 3
(TBD)
Current Baseline
Next Baseline
Future Baseline
Enterprise level architecture impact
Grouping items for efficiency
Detailed cost & schedule impact
Submit & approve Change Requests
Update requirement documents
Update use cases & test cases
Update design documents
Implement
Evaluate whether Essential for Go-Live
Categorize impacts in 1-4
Approve and agree baseline scope
Impact assessment continues for new items to get ahead for the next baseline
Baseline 0
(May, 2006)

## Slide 14: Proposed TAC resolution to limit additional scope change
The objective of the Nodal program is to design and implement the nodal market system and transition from the current zonal market to the nodal market by 12/1/2008.
The budget presented to the Board of Directors, TAC and TPTF was based on this timeline and the scope defined under the May 2006 version of the protocols (termed “Baseline 0”).
Multiple NPRRs have been approved since May 2006 and the program is currently working to incorporate them into a revised baseline (“Baseline 1”). The scope of the revised baseline includes the previous baseline plus NPRRs approved as of March 31st, 2007.
As the program continues through its delivery cycle, and the systems are built and tested, additional changes requiring additional work and rework will potentially have an exponential impact on cost and schedule.
Such changes are to be minimized. As a practical measure:
  An NPRR that is not essential for Go-Live should be deferred until after nodal goes live.
  An NPRR that addresses the correct working of the Nodal Market will be considered as essential for Go-Live.
  An NPRR that deals with adding or enhancing functionality to the existing systems will be considered not essential for Go-Live.
ERCOT will make the ultimate determination as to whether an NPRR is essential for Go-Live in consultation with TPTF, PRS and TAC

## Slide 15: Nodal Organization Development Plan
Top Down Sizing Analysis (complete)
Accelerated Organization Sizing
Current State Baseline Analysis
ISO Benchmarking
System Ops
Phase One April ’07 – Nov ‘07
Future-State Sizing Analysis
Gap Assessment
Efficiency Analysis Post Go-Live
Performance &
Quality Analysis
~ 25 of 45
Departments
Impacted
Preliminary Organization Alignment Analysis
Market
Trials
Phase Two Nov ‘07 – Nov ‘08
Refined Sizing Analysis
Refined Alignment Analysis
Staffing & Recruiting Plan
Staffing & Recruiting Plan
July 1st ‘07