## Slide 1: Texas Nodal Market Implementation Data Center Server Consolidation
May 4 2007
TAC Meeting
David Forfia
Data Center Infrastructure
Notes: <number>

## Slide 2: Nodal is migrating 73 servers to 4 AIX servers
<number>
Texas Nodal Program Update
23 April 2007
Currently working with all Project Managers and ERCOT
committees to implement our plan.
Our Plan :
  Minimal disruption
  Optimize timing
  Minimize the risk
  Maximize the benefit
  Lower overall costs
  Safeguard Market Operations
  Improve service levels
  Not affect Texas Set 3.0 Implementation
Notes: <number>
<number>

## Slide 3: Consolidation addresses critical Data Center Capacity constraints
<number>
Texas Nodal Program Update
23 April 2007
Notes: <number>
<number>

## Slide 4
<number>
Texas Nodal Program Update
23 April 2007
Migration Metrics
65%
23
8
% Remaining
Retired/
Refresh
Migrated
89
Starting Total
Databases
22.9
Reduction
104
Modified
4
Retired
36%
% Remaining to Review
86%
% Remaining
184.9
Post Migration
Bytes Used
131
Reviewed
6
Migrated
207.8
Pre-Migration
Bytes Used
Database Storage (in GB)
205
Total Files
Applications/Scripts
74
Starting Total
Servers
Completed
Migrated 8 databases
Decommissioned 4 servers
Installed temporary storage
Completed presentations for TAC, RMS and COPS
In Progress
Working with MORO and CO Carts for sign-off on Wave Plan
Current Consolidation efforts have focused on low-hanging fruit
Notes: <number>

## Slide 5: Remaining work Potentially Impacts Projects
<number>
Texas Nodal Program Update
23 April 2007
Project Release Steps To Complete
Development
Product Testing
Integration Testing
Production
Potential Constraints
Access and availability of the testing environment
Data Center capacity for the projects
Market Operations / Retail Operations
60077_01 – ERCOT.COM Secured Area
50024_02 - Enhancements to SCR727 – Market Enhancements
PR 60101_01- Load Profile Transition Migration
PR 40066_04 – Lodestar Upgrade to 4.x
PR 50061_01 - EDW EAI Transition
PR 70006_01 – Website Enhancements for ERCOT outages
System Operations
50070 - Unit Testing - Electronic Submittal via Web
Corporate
None identified
Notes: <number>
<number>

## Slide 6
<number>
Texas Nodal Program Update
23 April 2007
High Level Wave Plan - completion by October
Application Migration Steps
Development
Product Testing
Integration Testing
Production results
Notes: <number>
<number>

## Slide 7: Questions
<number>
Texas Nodal Program Update
23 April 2007
Questions
Notes: <number>
<number>
<number>