## Enhancements
Enhancements
Category |  | Source | Issue | Issue (Business problem trying to solve) | Market Proposal | Discussion | ERCOT Proposal Comments | Who Submitted | SIR | In or Out Scope?
Business | Annual Validation | MMWG | TDSPs currently getting one MT issue with all ESIs. TDSPs unable to process in timely manner | Will need to fleshed out during call to review AV issues | Report # of ESIs within each MT issue not just # of MTs issues | ERCOT could add field on the issue to reflect the # of ESIs included. Some TDSPs would like a one to one for each AV update while ERCOT and other concerned about too many files being sent at one time and the potential impacts to the system | ERCOT needs more clarification on the request: - Is the request for 1 to 1 relationship? Or - Is the request for information on number of ESI IDs to be included in AV issues?
Reporting | Prior year subtype reports | MMWG | Market would like to see #s for prior year | MPs want to be able to see MarkeTrak Numbers from prior year to compare with current year. | Report # of issues by subtype for the prior year | Group feels that all requirements will be captured - no need for add'l development | ERCOT believes this is available through current reporting functionality. Need more details if MPs do not agree. |  |  | Out of Scope
Reporting | Average Completion Time | MMWG | Market would like to see average time to complete MT issues | Market needs to be able to monitor its progress on working MT issues. | Need to clarify if by all MPs or market average | Group feels that all requirements will be captured - no need for add'l development | ERCOT needs more details on calculation parameters: - Average time in each state? - Average time from beginning to end? - How would auto close be handled in the calculation? |  |  | Out of Scope
Business | Escalation Process | MMWG | MPs would like info those that have been escalated, timeframe and the reason, even though comments have been added or issues closed they are still being escalated. | MPs would like to be able to email directly from the MT screen using a button to any and all associated parties with the MT issue and/or Primary & Secondary Escalation contacts. MPs would like to be able to override auto-populated email address.Any emails sent would be logged on the screen.MPs would like to see information on issues that have been escalated such as when, and for what reason, they were escalated. | maybe implement a way to assign issues to the primary escalation contact - but would have to all be users. Or a way to get contact info from issue page. Maybe add a button to escalate issue via email to primary & secondary contacts from the issue itself. | ERCOT to bring process to next MMWG meeting | ERCOT needs more details on what escalation contact is being requested: - What player's escalation contact is needed?
Business | Escalation Process | MMWG | Even though comments have been added, or issues closed, they are still being escalated. | Even though comments have been added to a MarkeTrak issue, or issues is closed, they are still being escalated. | TXUED to provide ERCOT examples | ERCOT to bring process to next MMWG meeting | ERCOT presented Escalation Process at 03/23/07 MMWG Meeting - ERCOT has requested specific examples but have received none to date.
Business | Priority Flag | MMWG | TDSPs need to be able to identify priority issues | TDSPs need to be able to identify priority issues | 041707: Add SMRD as field and add priority flag based on the SMRD. TDSPs to consider multiplie queries -- pulling priorites/cancels first.that can be sorted by and reported on - what is included? | 041707 notes: MPs will consider doing two API pulls -- pulling only cancels first. 032307 notes:Maybe add a field for a date to be worked by. Maybe include critical date field for all issue types. ERCOT would assign certain as priority rather than allow CRs to assign | ERCOT needs more details on priority flag: - what issues need priority flags? - what should constitute priority?
Business | New Statuses | MMWG | Need more detail on TDSP process w/IAS | TDSPs need more detail on the vote state of Inadvertent Gain Issues. | Add 3 new statuses: Received by TDSP & Completed by TDSP | add a button for the tdsp to say that they agree and also a button that says EDI received and 3rd button that all work is done. Cr would not be able to close the issue until TDSP agrees | Redesign workflow rather than just adding new states or buttons - Pending a proposal from Inadvertent Gain
Business | Billing Issue vs. Missing Transactions | MMWG | Some CRs not using types correctly | TDSPs are receiving incorrect issue types because of confusion with issue definitions. Need to restrict tran types on usage billing issues. | 041707 notes: Add drop down menus to Missing Transaction -- only include 814s. Add drop down menu to Usage/Billing -- only 867s & 810s. All missing 867s & 810s would be filed under Usage/Billing issues. Also include drop down Menu or check box to indicate whether IDR or NIDR. Better define how each subtype is to be used, potentially limit subtypes in drop down |  | Need definition from MPs on what tran types need to be included for Billing usage and missing transaction.
Reporting | Volume Limit | MMWG | MPs can only pull 3000 rows at a time | Some MPs need to pull statistics on more than 3000 issues. The limit of 3000 rows is restricting reporting capabilities and the work around is awkward. | 041707 notes: Will need to include this in the SCR in order to cost estimate. Would like to increase to 5K -10K | May look at EIS for solution. This would result in replicated DB to run reports on without impacting users. Otherwise, increasing the row # will result in performance decrease
Other | Technical Distribution List | MMWG | Need better means to communicate w/ tech users | MPs are not able to communicate specifically with technical users. | Create new distribution list: could either be sign-up or new contact type | Maybe have two list - one API and one GUI. ERCOT working on getting setup | ERCOT implemented self-subscribing mailing lists. |  |  | Out of Scope
GUI | Dashboard | MMWG | MPs would like a screen similar to old FT homepage | MPs would like to see a count of each issue type rather than just a list of issues. Be able to drill down into issues. | ERCOT needs more definition on what MPs want | 041707 notes: MPs would like to see more detail on the dashboard. This can be done via query for homepage. | ERCOT believes current functionality provides the same information available on FT so needs more details for this request: - What information was provided on FT that is not available via MT Reporting?
Business | IAS Transition Issue | ERCOT | Currently, when the Gaining MP submits an Inadvertent Switch MarkeTrak issue requesting the Losing MP to regain, the Gaining MP must wait for the Losing MP to click the "Begin Work" button before the Gaining MP can click "Agree". | Currently, when the Gaining MP submits an Inadvertent Switch MarkeTrak issue requesting the Losing MP to regain, the Gaining MP must wait for the Losing MP to click the "Begin Work" button before the Gaining MP can click "Agree". | Add a button -- see notes above | 041707 notes: MPs to hold subteam to develop new workflows. When the Gaining MP issues the MarkeTrak requesting the Losing MP to regain, once issue is created they should have the ability to click the "Begin Work" and "Agree" buttons. This would expedite 95% of the pending issues we know have in backlog | Redesign workflow rather than just adding new states or buttons - Pending a proposal from Inadvertent Gain
Reporting | Cell Merge |  | Currently, we are unable to merge cells after downloading reports into Excel format. We understand that this will require reconfiguration by the software vendor. | Currently, we are unable to merge cells after downloading reports into Excel format. | If MPs save to desktop, and open in Excel, this would solve the issue | 041707 notes: This is not an MT issue. MPs need to save to desktop and open in Excel. Enable cell merge option. | Users are able to merge cells if saved to your computer first. When you select the Excel version you are given a choice of "open" or "save", you should select save. When you open from the download you are using a limited version of Excel and this is why all functionality is not available. |  |  | Out of scope
GUI Look and Feel | Contact Page |  | We have been unable to determine escalation MP contact’s for Inadvertent Switches utilizing MarkeTraks directory format. | We have been unable to determine escalation MP contact’s for Inadvertent Switches utilizing MarkeTraks directory format. | Search on contact page does not work with space - you must include either % or * | 041707 notes: Adding button to send email straight from MT page should resolve this issue -- see notes on Escalation Process enhancements. Create a MP contact page that mirrors the FasTrak contact page | ERCOT believes this is not a change to current functionality and is a training issue. - ERCOT can verify this if provided with a specific example.
GUI Look and Feel | Cursor Placement |  | Currently, when you click the “Search’ button, the cursor is positioned in the “Keyword(s)” field by default. | Currently, when you click the “Search’ button, the cursor is positioned in the “Keyword(s)” field by default. | Will request vendor to place in first field upper left-hand side | Place the cursor in the “Issue ID” field or allow the user personal settings capability. | ERCOT has asked for a vendor enhancement. |  |  | Out of Scope
Other | Associate DUNS | TXUES | Currently, the Marketrak tool is DUNS specific thus making it difficult to detect new issues as the user must sign on under each certificate to query. The FasTrak tool accommodated all ESID’s no matter the type i.e. SESCO, AE SMB Non-Res, AE Res, etc. | Currently, the Marketrak tool is DUNS specific thus making it difficult to detect new issues as the user must sign on under each certificate to query. The FasTrak tool accommodated all ESID’s no matter the type i.e. SESCO, AE SMB Non-Res, AE Res, etc. | Potential security issue. Tied to DCs. | Tie all associated DUNS together to create a more efficient reporting/querying process. | ERCOT security requirements prohibit associating multiple DUNS numbers to a single digital certificate. |  |  | Out of Scope
Reporting | Trend Reports | TXUED | Asks for start date and end date. Only looks at 30 days -- a month with 31 days ends up at 2 reports. Also puts inappropriate column headings that result in users having to cosmetically correct. | Needs months to be identified so that you can get data for entire month. Also want to be able to pull data for a year or for one date. Needs totaling functionality. |  | CNP will bring samples reports for what they want to be able to create.
| Personal Notifcations | DE | Would like to be able to set up "reminders" to notify users when an issue is about to go to Escalation | Bring unresolved issues to MPs attention prior to escalation
| Premise Type | TXUES | Add field for premise type | Allow MPs to work issues by business unit | Add a new required field for Premise Type
|  | CNP | setup a MT distribution list - These distribution lists would allow a 3 way communication between ERCOT to MPs, MPs to ERCOT, and MPs to MPs | From lessons learned, allow a way to have a 3 way communication |  | done
|  | CNP | Provide update via API whenever a Market Participant's visability to an issue has been removed. | A need for an end to end process for the issue. From the API, we pull the information into our database - updates are made as changes are made to the issue. If ERCOT removes us from the issue, we are not aware. It remains as an active issue on our end because nothing has been sent on the API to inform us that we have been removed. It has definitely impacted our reporting. |  | "ERCOT Intervention" or issue deleted, would an email help?
|  | CNP | Bulk Insert, If a file is entered twice, 1) does it validate so it can not upload the same file name 2) bulk insert to withdraw | In the instance a file is loaded multiple times, need a way to withdraw the issues so that there are not duplicates. |  | SIR 11233 - next release
|  | CNP | MarkeTrak should have the ability to Query List back to GO Live 11-13-06 in order to sync up systems. |  |  | need to brainstorm, new request type?
|  | CNP | DEV Issue Sub-Type 'IDR usage present MP not ERCOT', add a 'TOTAL' field to GUI. This field would be required. Also map this to the API.
|  | CNP | Consistent sub-type verbiage requested across Bulk Insert & GUI grids.
|  | CNP | Bulk Insert Stoptime logic is adding one day to the date once a user inputs desired stoptime. Create issue with actual stoptime (date) that's requested by submitter. |  |  | SIR 11208 - next release
|  | CNP | On the GUI, when creating high date stoptime (i.e. 12/31/2037), if the user adds a timestamp in the text box (23:59:59), the issue creates but can not be withdrawn [if user needs to]. To enhance, validate on the date field so that if a timestamp is not needed, inform the user and do not create issue. |  |  | need discussion
|  | CNP | Remove 14-day wait from 'Auto Complete' to 'Auto Complete (Closed)'. Recommend transitioning straight from 'Pending Complete' to 'Auto Complete (Closed)' after 14 days {as oppsed to 28 days from 'Pending Complete' to 'Auto Complete (Closed)'}. |  |  | need discussion
|  | CNP | DEV LSE Issues: Once TDSP modifies date(s), ALL parties involved in issue should be able to view the Modified date. |  |  | need discussion
|  | CNP | DEFECT - Reporting: When exporting details to excel EXCEEDING the 1st set of 3,000 rows and upon clicking the 'Excel' Button in report view, only the 1st set of 3,000 rows is actually exported to Excel. Using that 'Excel' button, logic should export the appropriate set of rows user is requesting (i.e. Last 200 rows). |  |  | discussed a resolution in 3/28 Retail Market Call
|  | CNP | DEFECT - Escalation notice functionality for DEV Issues appears not to work. |  |  | need discussion
|  | CNP | Reports - Search Filter should allow the user to utilize key word 'OR' instead of only 'AND' when querying the tool. |  |  | This is a training issue.
|  | CNP | For TDSP submitted DEV LSE Issues, allow user to proactively enter information in the field 'Service Hist With Duns for Affected Period' [if user sees fit at the time of submission]. This field would be optional. Map to GUI, Bulk Insert and API.
|  | CNP | Add the MarkeTrak Website as a permanent Link. Should be in next release. | More efficient to have the website available like TML. Many not aware of the website. Location of User's manual |  | SIR 11036 - next release
|  | CNP | Remove the "notes" option from the action drop down (may just need to have inquiry since there are notes that exists.) | Notes were being used instead of the comments field. The notes was not mapped in the wsdl and xsd for the API to pull in. In working through an automated process comments were not available. |  | done
|  | CNP | ERCOT does not support the & sign in the API ( may be other characters) | Text fields, ex.Rec&apos;vd monthly usage files- also issue with pecent sign |  | for journal or text fields
|  | CNP | ERCOT should create a report to monitor issues that are created but not submitted | Prevent issues sitting in pending. |  | escalation?
|  | CNP | When adding a new user, they should have access to all issues from day one, not from the time they are set up in MarkeTrak |  |  | UG contains process to grant access to new users to old issues, vendor contacted
|  | CNP | Possibly add a Service Order Sub Type to D2D | Currently there is not a subtype for service order transactions and they are being filed under OTHER. |  | fields?
|  | CNP | In the Workflow for Missing transaction - many time the issue is opened to the MP, instead of ERCOT, should this default to ERCOT | May need to clarify when to assign to whom.
|  | CNP | Ability to send comments on all transitions | Most transitions comments are added. Currently it is a two step process. ( if set up to allow comments - what is the impact to the Quick Transitions) |  | eliminates Quick transitions
|  | CNP | A few fields not present in the WSDL (dev) a comment field - not issue comment |  |  | need more detail
|  | CNP | Database - MarkeTrak needs a Process History |  |  | need more detail
|  | CNP | Add the 65004 to the drop down menu | Was left out of the drop down on the intitial roll out |  | SIR 10957 - next release
|  | CNP | Auto complete - should reflect "closed" | For reporting - the autocomplete issues appear to still be open |  | SIR 11205 - next release
|  | CNP | Contacts - is there a way to have a default, |  |  | defaul owner?
|  | CNP | Service period Start date added but is optional for missing transaction, projects, seibel chg/info, and other subtypes |  |  | are you requesting it be mandatory?
|  | CNP | Service period Start date added and is required for Rep of Record | Only required field is esiid - not enough to determine rep of record. Usually in the comments, the CR will specify a particular time period. Sometimes it is several months back. |  | and what? So? Am I missing something?
|  | CNP | Make comments required for Siebel chg/info sub types | Need comments to have enough information to research and reply to the issue
|  | CNP | Add ISA field and have it required for 997 issues and optional for projects and "other" sub types | This was a request from the March 6th meeting on 2006, there was not enough information provided to answer the issue
|  | CNP | Need to have a process for ERCOT to check to see if rolodex and contacts are populated, and a way to go thru an update process | MPs to work with their ERCOT Rep to find good contact |  | need discussion
|  | CNP | IAS - many issues are in a state of "agreement reached", they are not closing, nor auto closing - some the BDMVI has been sent others the BDMVI has not been sent. Is there a way to verify and close if transaction sent. Is there a way to transition to another state ( possibly a new state) if the transactions has not been sent |  |  | I think I fixed this? Not sure what BDMVI is
|  | CNP | IAS escalation notices - not working quite right. Are they including "new" | yes, currently CR's not seeing these to transition. Also for those who are having issues with the reporting - would be notified in an email they have an issue to work |  | no, should it be?
|  | CNP | Copy/Paste from MarkeTrak to excel, etc. |  |  | can be done now?
|  | CNP | IAS - no agreement reached - in this state since Jan, however comments are still being added mt44457 |  |  | and the enhancement would be?
|  | CNP | Reports - year to date option | more efficient reporting - currently would copy - paste to excel - then format, add cols to get totals |  | see above request #7
|  | CNP | Merge capability for reports - subtype, subtype by state | Streamline reporting - create several reports - copy and paste to make one report |  | huh?
|  | CNP | Improved processing time for API query detail/update/response
|  | CNP | when you email from MarkeTrak - need a way to include the email as part of the issue | for tracking and audit purposes - what has been done to resolve issue. |  | Vendor Enhancements submitted: 5157756/ENH109708 - escalation emails 5157753/ENH109709 - notification emails 5163147/?????????? - Issue emails
|  | CNP | have a report type for all DEV | Option available for D2D, but not DEV, would have to run report for each subtype |  | Parent Project Type
|  | CNP | do not allow a change on the title | Reporting issue. - Some are overrideing the title with comments
|  | CNP |  | Amongst each DEV issue sub-type, make population of the ‘Title’ field static. Validation could be done to ensure that a submitting MP can NOT populate this field with information that’s not relevant to that particular sub-type. (i.e. DEV IDR issue 101120: Title field is ‘IDRUsagepresentinbothsystemsbuthasdateissues’ but it’s a ‘In ERCOT system not MP’ sub-type).
Business |  | TXUES | Currently the losing MP depends on the gaining MP to place a comment on the IAS issue regarding their intentions to cancel the pending MVO. | The other MP issues an IAS/Gain issue then realizes they have a pending MVO and must submit a Cancel with Approval. Once the Cancel With Approval is submitted and linked to the IAS Marke Trak , the Losing MP is unable to see the link. | Enable all MP's to see links no matter who submitted it. As long as that MP is involved in the IAS.

## Workflow Issues
Workflow Issues
Source | Issue | Issue (Business problem trying to solve) | Market Proposal | Discussion | ERCOT Proposal Comments
MMWG | Need more detail on TDSP process w/IAS | TDSPs need more detail on the vote state of Inadvertent Gain Issues. | Add 3 new statuses: Received by TDSP & Completed by TDSP | add a button for the tdsp to say that they agree and also a button that says EDI received and 3rd button that all work is done. Cr would not be able to close the issue until TDSP agrees | Redesign workflow rather than just adding new states or buttons - Pending a proposal from Inadvertent Gain
ERCOT | Currently, when the Gaining MP submits an Inadvertent Switch MarkeTrak issue requesting the Losing MP to regain, the Gaining MP must wait for the Losing MP to click the "Begin Work" button before the Gaining MP can click "Agree". | Currently, when the Gaining MP submits an Inadvertent Switch MarkeTrak issue requesting the Losing MP to regain, the Gaining MP must wait for the Losing MP to click the "Begin Work" button before the Gaining MP can click "Agree". | Add a button -- see notes above | 041707 notes: MPs to hold subteam to develop new workflows. When the Gaining MP issues the MarkeTrak requesting the Losing MP to regain, once issue is created they should have the ability to click the "Begin Work" and "Agree" buttons. This would expedite 95% of the pending issues we know have in backlog | Redesign workflow rather than just adding new states or buttons - Pending a proposal from Inadvertent Gain
CNP | Processing flow: beyond capablility to process therefore is hangs in an infinite retry. Transaction model, fails while processing > throw out > do not place back in que |  |  | Duplicate Issue
CNP | Revise the IAS workflow - needs to flow through the different CR's to vote, then transition to the TDSP. If one of the CR's disagrees, then the issue goes to ERCOT | see proposed workflow - add a return button that would reset the "vote" of both CR's
CNP | Unclear how to transition an issue to ERCOT. Looking for transition button 'return to ERCOT', VS using the 'assign owner' button | Address with workflow group |  | Workflow

## User Guide Revisions
Revision Request
Source | Issue | Issue (Business problem trying to solve) | Document to be Revised | Owner | Status | Completed Date
CNP | Define the tran_types to the sub type |  | User Guide Revision
CNP | Clarify the use of the transition buttons. Ex. Instead of choosing the "complete" transition, the MP is selecting "Return to xxx" | Buttons need to be defined in the users guide. Examples should be provided. | User Guide Revision
CNP | Admin role - how to use copy function to set up user, add to users manual | Add copy procedure in users manual when adding a new user | User Guide Revision
CNP | Add information on the ERCOT Initated and LPA issues to the users manual - (need to understand as a MP receiving the issues) | Even though ERCOT is the only one who initiates the LPA and ERCOT initiated issues, we need to know the format of the spreadsheet, required and optional fields to facilitate in automating our backend process | User Guide Revision/Load Profiling Guide Revision
CNP | When adding a new user, they should have access to all issues from day one, not from the time they are set up in MarkeTrak | UG contains process to grant access to new users to old issues, vendor contacted | User Guide
CNP | When entering the Tran_type - needs to be the trantype of the transaction the CR is needing. (many times the tran type and what is asked in the comment are not the same | Training issue | User Guide Revision
CNP | Document wsdl | API documentation for MP's to have. Allow the development of API | API development guide
CNP | IF a MP is no longer in the Market, and there MT issues open to this Market Participant, ERCOT needs to notify MP's involved and close the issue | Issues are being created for MP's no longer in the Market. There will never be responded to and difficult to get action taken on. Should not be allowed to create an issue with MP no longer in market. Also if issues are present and the MP leaves the market, again issues will sit, need a process for handling these issues.
CNP | More on reporting in Users manual | An area where MP's are having issues | User Guide Revision
CNP | Can we define states that are "in progress" , "complete" - for reporting - currently define to provide our execs with this weekly |  | User Guide Revision

## Action Items
Description | Owner
Create list of reports with descriptions | MMWG
Discuss w/MMWG idea of creating reports for each subtype but only pulling a few | MMWG
Clarify what PRIOR YEAR reporting requirements are | MMWG
Clarify privileges & rights, potential changes to access | ERCOT
Better definition of private vs. public reports | ERCOT
ERCOT to bring escalation process to next MMWG meeting | ERCOT
Identify all subtypes/issus that would be priority | MMWG
Detail TDSPs processes for IAS issues - Possibly develop consistency | Will need to coordinate w/ IGTF
Define subtypes - missing trans vs. billing issues | MMWG/ERCOT
MarkeTrak will now be included in SLA - may need to provide reporting suggestions | Will need to coordinate w/TDTWG
New distribution list for Technical Users | MMWG/ERCOT
Clarify Dashboard requirements - real time? | MMWG
Add root causes to issue spikes when possible | MMWG | move to enhancement
ERCOT to bring list of requirements not implemented with MT Phase I | ERCOT
Look at DEV process - seems to be an issue with TDSP automated processes
Provide description for each MT subtype | MMWG
Consider revising subtype names or adding add'l subtypes | MMWG
ERCOT and MPs to analyze "other" MT Issues for potential new subtypes | ERCOT
Consider graphing report #s | MMWG/ERCOT
Review annual validation process | ERCOT, TXUED, CNP, DE
TXUED to develop proposal for prioritzing issues | ERCOT/TDSPs
Subteam to revise workflow for inadvertent ( will need to coordinate with IAG WORKSHOP) | ERCOT, TXUED, CNP, CNE, AEP
Bring redlined version of MT Guide | ERCOT
Sample reports that contain more than 3K rows | TXUED CNP
Capture CNP enhancements in spreadsheet and send to MMWG | Jgarcia
Define tran types in User Guide | ERCOT

## DRAFT - Timeline
DRAFT TIMELINE
2007-02-26 | Begin reporting requirements gathering
2007-03-23 | Review reporting requirements
Begin enhancements requirements gathering
2007-04-12 | Finalize reporting requirements
Review enhancements requirements
2007-05-02 | Review draft SCR
2007-05-09 | Present SCR to RMS (non-voting)
2007-05-14 | File SCR
2007-06-13 | RMS Vote
2007-07-11 | RMS for IA and CBA
2007-07-19 | PRS Vote
2007-08-02 | TAC Vote
2007-09-18 | BOD Vote