|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Technical Advisory Committee Reliability and Operations Subcommittee for March 2007 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | ERCOT is currently tracking 178 active generation interconnection requests totaling over 78,000 MW. This includes over 25,000 MW of Wind Generation. |  |  |  |  |  |  |  |
| 2. | Transmission Services has updated and posted the 1st Quarter Transmission Information Tracking System (TPIT) and Cost Summary Report. |  |  |  |  |  |  |  |
| 3. | Regional Planning is currently reviewing proposed transmission improvements with a total cost of approximately $201 M to $250 M. |  |  |  |  |  |  |  |

Document Revisions

| Date | Version | Description | Author(s) |
| --- | --- | --- | --- |
| April 4, 2007 | 1.0 | First draft | Transmission Services |
| April 12, 2007 | 1.1 | Draft update | Regional Planning, Regulatory Compliance and Reporting |

Table of Contents

1.	Generation Interconnection	1

1.1.	New Generation Beginning Commercial Operations	1

1.2.	Active Generation Interconnection Requests	1

1.3.	Potential Future Generation Interconnections	1

2.	Dynamic Analysis and Modeling	1

3.	Regional Planning Activities	1

3.1.	Coal Unit Integration Study	1

3.2.	CREZ Study (SB20).	1

3.3.	Entergy Integration Study	1

3.4.	Regional Planning Group Project Reviews	1

3.5.	Other Projects/Studies	1

4.	NERC Activities	1

4.1.	Reporting	1

5.	Resource Adequacy/CDR	1

6.	Load Forecasting	1

6.1.	Modeling	1

7.	Data Activities	1

8.	TPIT	1

9.	Maps/Graphics	1

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” data folder posted in the “Operations and System Planning” data area on the ERCOT website.

## New Generation Beginning Commercial Operations

No new generators went into commercial operation.

## Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Currently tracking 178 active generation interconnection or change requests |  |  |  |  |  |
|  |  | North | South | West | Total |
| Security Screening Study |  | 3 | 6 | 13 | 22 |
| SSS Completed |  | 13 | 13 | 20 | 46 |
| Full Interconnect Study |  | 14 | 23 | 46 | 83 |
| FIS Completed |  | 0 | 0 | 2 | 2 |
| Interconnect Agreement Completed |  | 7 | 4 | 14 | 25 |
| Capacity for Grid, MW |  | 25,503 | 30,869 | 21,825 | 78,197 |
| Wind MW (under development) |  | 1,333 | 4,328 | 19,677 | 25,338 |

| Fuel | Public | Non-public | Total |
| --- | --- | --- | --- |
| Natural gas | 2.850 | 14,730 | 17,580 |
| Nuclear | 5,986 | 19,200 | 25,186 |
| Coal | 4,971 | 4,052 | 9,023 |
| Wind | 3,038 | 22,300 | 25,338 |
| Other | 0 | 1,070 | 1,070 |
| Totals | 16,845 | 61,352 | 78,197 |

## Potential Future Generation Interconnections

The table below summarizes the publicly known potential future generation projects for the ERCOT region.  (IA=Interconnect Agreement, PL=Public Letter)

| FUTURE GENERATION INTERCONNECTIONS (PUBLIC PROJECTS) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR # | Site Name | Status | County | Region | Fuel | In Service Date | MW into Grid | Change from Last Report |
| 06INR0016 | Dow 9 | IA | Brazoria | South | Gas | Mar-07 | 0 |  |
| 06INR0037 | Cirello 1 | IA | Taylor | West | Wind | Mar-07 | 233 |  |
| 06INR0035 | Colorado Bend 1 | IA | Wharton | South | Gas | Apr-07 | 275 |  |
| 06INR0036 | Quail Run 1 | IA | Ector | West | Gas | Apr-07 | 275 |  |
| 06INR0038 | Scurry County 1 | IA | Scurry | West | Wind | May-08 | 130 |  |
| 03INR0030 | Wild Horse 1 | IA | Cottle | West | Wind | Jun-07 | 126 |  |
| 07INR0003 | Whirlwind 1 | IA | Floyd | West | Wind | Sep-07 | 60 |  |
| 06INR0021 | Barton Chapel | IA | Jack | North | Wind | Oct-07 | 120 |  |
| 04INR0011 | Mesquite Wind 2 | IA | Shackelford | West | Wind | Dec-07 | 200 |  |
| 04INR0017 | Ocotillo Wind Farm 1 | IA | Howard | West | Wind | Dec-07 | 59 |  |
| 04INR0020 | Project Snyder | IA | Scurry | West | Wind | Dec-07 | 63 |  |
| 07INR0045 | Roscoe 1 | IA | Scurry | West | Wind | Dec-07 | 209 |  |
| 07INR0010 | Stanton Wind 1 | IA | Martin | West | Wind | Dec-07 | 101 |  |
| 03INR0034 | Silver Star 1 | IA | Erath | North | Wind | Dec-07 | 60 |  |
| 07INR0023 | Sweetwater Wind 4 | IA | Nolan | West | Wind | Dec-07 | 300 |  |
| 07INR0030 | Buffalo Gap 3 | IA | Nolan | West | Wind | Apr-08 | 138 | Signed IA |
| 06INR0035 | Colorado Bend 2 | IA | Wharton | South | Gas | May-08 | 275 |  |
| 06INR0036 | Quail Run 2 | IA | Ector | West | Gas | May-08 | 275 |  |
| 03INR0030 | Wild Horse 2 | IA | Cottle | West | Wind | Aug-08 | 39 |  |
| 05INR0015 | Gulf Wind 1 | PL | Kenedy | South | Wind | Sep-08 | 400 |  |
| 09INR0006 | Oak Grove 1 | IA | Robertson | North | Coal | Apr-09 | 855 |  |
| 09INR0006 | Greenville | PL | Hunt | North | Gas | May-09 | 1750 |  |
| 08INR0003 | Sandow 5 | IA | Milam | North | Coal | Jul-09 | 581 |  |
| 05INR0015 | Gulf Wind 2 | PL | Kenedy | South | Wind | Sep-09 | 400 |  |
| 09INR0015 | Comanche Peak 1 & 2 Upgrade | PL | Somervell | North | Nuclear | Oct-09 | 86 | Public letter |
| 09INR0006 | Oak Grove 2 | IA | Robertson | North | Coal | Oct-09 | 855 |  |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | Coal | Jun-10 | 750 |  |
| 05INR0015 | Gulf Wind 3 | PL | Kenedy | South | Wind | Sep-10 | 400 |  |
| 10INR0002 | Hugo | PL | Choctaw, OK | North | Coal | Feb-11 | 500 |  |
| 11INR0001 | Twin Oaks 3 | PL | Robertson | North | Coal | Jun-11 | 630 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Coal | Sep-11 | 800 |  |
| 15INR0002 | Comanche Peak 3 & 4 | PL | Somervell | North | Nuclear | Jan-15 | 3200 | Public letter |
| 15INR0008 | South Texas Project 3 & 4 | PL | Matagorda | South | Nuclear | Jan 2015 | 2700 | Public letter |
|  |  |  |  |  |  | Total | 16,845 |  |

# Dynamic Analysis and Modeling

- Continuing to support PTI in the development of combined cycle power plant stability models.

- Addressed issues with data from the “ERCOT Combined Cycle Dispatch survey” that were identified by PTI

- DFW Dynamic Reactive Devices

- Requested study data sets and reproduced TXU study results.  Further review of the project continues.

- Study of stability limits for power transfer out of West Texas

- Preparing for continuing studies in 2007 - need completion of DWG base case with wind models and approval of study scope.

- Preparing for 2007 screening studies.

- Testing and verifying compatibility of wind user models with PSS/e V30.3.2

- Recompiled code for Bonus, Micon and Kennetech models.

- Downloaded latest PSS/e wind package including GE, Vestas and generic type 3 models.

- Working with Gamesa to resolve initialization/convergence issues with their model.

- Other models to pursue – Clipper, other?

- Supporting System Operations in the analysis and enforcement of real time voltage stability limits and transient stability limits.

- Continuing participation on generic wind model development.  ERCOT will research if such models can be developed in-house for TSAT

- Supporting ongoing DWG activities including efforts to develop transient voltage recovery criteria, revision of high-set Under-Frequency Load Shedding schemes and draft requirements for field testing of NERC generator performance standards (PRC-019, PRC-024, MOD-026, MOD-027).

- Review of study scopes and/or dynamic studies produced by TO’s associated with generation interconnection projects into ERCOT.

# Regional Planning Activities

The following summarizes numerous significant activities associated with regional planning issues.

## Coal Unit Integration Study

  - The scope of this study was reduced significantly when TXU cancelled interconnection agreements for most of their planned coal units.  The majority of the work associated with this project has been undertaken in response to various RPG project reviews.

## CREZ Study (SB20).

  - Responded to numerous questions from parties in PUCT Docket 32672 through two technical conferences

  - Finalized contract with GE Energy for Ancillary Services study related to wind impact.  Study has begun and is scheduled for completion by October 31, with the final report due in December.

## Entergy Integration Study

  - Responded to numerous RFIs in March related to first technical conference in this case on April 2.  The second technical conference will be held April 11 and more RFIs are likely.

## Regional Planning Group Project Reviews

  - TXUED TNP One – East Bell County 345kV Double Circuit Project has been submitted. This is a $63 million project in north central Texas driven primarily by the proposed addition of new coal generation in the area.  Comments have been received from stakeholders, which TXUED has addressed, and the ERCOT Independent Review of this project is underway.

  - TXUED Anna-Collin-NW Carrollton has been submitted and the ERCOT Independent Review is complete.  The Anna-Collin portion of the project was presented to TAC in March and will be recommended to the Board in April.

  - TXU Able Springs has been submitted.  It is a $12.8 million project primarily to serve a customer in Kaufman County.  It is currently under review.

  - CNP Houston Area Constraint Mitigation Phase II Project has been submitted.  It is a $37.9 million project to increase the North to Houston import capability.  It has completed the comment phase with no comments requiring CNP resolution and is currently in ERCOT Independent Review.

  - TXUED has submitted the Jewett to West Fairfield 138 kV line rebuild project.  This is a $17.9 M dollar project in Leon and Freestone counties.  This project is currently under review.

  - LCRA has submitted the Evant to Lampasas 138 kV line rebuild project.  This is the first project to be submitted by a transmission operator that originated from the ERCOT 2006 Five Year Plan.  This is a $7.8 M dollar project in Lampasas County that is currently in the comment phase.  This project has been endorsed by the Regional Planning Group.

  - LCRA has submitted the Paleface to Miller 138 kV line rebuild project. This is a $9.4 M dollar project in Travis and Blanco counties.  This project is currently under review.

  - TXUED has submitted the Parkdale Dynamic Reactive Project.  This is a $45-$98 M dollar project to add a dynamic reactive device in the DFW area.  This project is currently in ‘Study Mode’.

  - GVEC has submitted the Wilson to Sutherland Springs 138 kV line project.  This is a $5.4 M dollar project to add a new 138 kV line in Wilson county.

  - CPSE has submitted the Skyline Auto #3 Addition project.  This is a $4.0 M project to add a third 345/138 kV autotransformer at Skyline substation in Bexar county.

## Other Projects/Studies

    - Regulatory support related to Entergy Integration study and CREZ study.

# NERC Activities

## Reporting

  - Revised ERO-2007LTRA (formerly EIA-411) according to TAC-approved methodology

  - Completed Summer Assessment

  - Started work on FERC 714

# Resource Adequacy/CDR

- Most Notice of Probabilities of Return for moth-balled units have been returned by generating companies.

- Notices of capacity for private network units have been sent by Client Relations.  Some have been completed and submitted.

# Load Forecasting

## Modeling

ERCOT Staff:

- Completed the Load Shape and Energy forecasting models for the 2007 long-term peak and energy demand forecast.  These updated models were used to obtain a long-term forecast for the 2007 cycle.

- Completed testing the new models using extreme weather profiles to determine their impacts on the summer peak demand forecast.

# Data Activities

- Advised SPWG model development for case building

# TPIT

- 1ST quarter TPIT & Cost Summary Report posted March 1ST.

- Individual TPIT spreadsheets sent to TPIT contacts for 2nd quarter updates

- TPIT data due back May 1st, 2007

# Maps/Graphics

- Started on an 8.5”x11” AutoCAD Transmission map book to augment the large Transmission map.

- Plotted Transmission, Zone, area maps for mailing and internal use and plotting oversized documents for others.