## Sheet1
The Structure Group Comments for the EDS 3 System Plan
2007-04-30
Section | Issue/Question
1.2 | It would be helpful to organize the tasks by the different groups (ERCOT, Market Participants, IMM). This would make it clear where the responsibilities for each stakeholder lies.
1.4 | The document states, "EDS 3 activities start in July 2007 with the ability to upload offers into SCED for data validation, over time the environment will be incrementally upgraded with new functions and defect fixed through July 2008. " When specifically in July will these activities start?
1.5 | This is a suggestion for an additional section that addresses Market Participant Expectations. Under this section, please list specifically what activities are optional versus mandatory for each Release of EDS. Also indicate any consequences or dependencies for MPs that do not participate. If an MP doesn’t participate during Release 5, can they not participate in subsequent testing? Does ERCOT submit proxy data on their behalf? The other option would be to cover it in each section below. I think it makes sense to set the tone before you get into the details. It would also be nice to outline what a Market Participant that does not operate resources is supposed to be doing or can do during this time.
2.1 | All discussions in the TPTF meetings about EDS 3 have indicated that the EDS 3 - Release 5 is mandatory for all market participants. This statement about Release 5 does convey "mandatory". "Early system deliveries will initially provide QSEs the opportunity to submit, modify, cancel, and retrieve input data for SCED execution."
2.2 | Again, this section does sound mandatory. Is it mandatory?
2.2 | Can vendors sign up for support workshops? Can vendors submit data on behalf of Market Participants? How often will MPs have to submit information? Can they submit all of their offers for the week all at once? Do you have to follow the market rules and timing? Are you testing the rules for when offers can be modified and how?
2.3 | Suggestion to preface the list of market participant readiness activities with the following statement just to add a little more clarity: "Here are the key activities that are expected from each Market Participant before and during EDS Release 5:"
2.3 | Are there deadlines associated with the MP readiness activates? Is so, it would be helpful to see them listed next to each of the readiness activities.
2.3 | Regarding the statement, "QSE ability to produce offer curve creation and submission to ERCOT ". Can MPs do this via the Portal or is this only via the Machine-to-Machine interface?
2.3 | Will QSE's need to demonstrate bid submissions capability one time or continuously?
2.3 | Regarding the statement, "Offer curve and Schedule submission to support RT testing". Should COP and Output Schedule be included for submission to support RT testing?
2.3 | Regarding the statement, "Market Participant schedule time to support EDS". How much time will MPs need to schedule? What is a typical day going to consist of?
2.4 | If entry into EDS Release 5 is mandatory, it should probably be indicated here with the Entry Criteria.
2.4 | It would be helpful to organize the tasks by the different groups (ERCOT, Market Participants, IMM). This would make it clear where the responsibilities for each stakeholder lies.
2.4 | Regarding the statement, "Individual Resource offer curves created by MPs". Will all the validation rules be in effect? Are there going to be competitive constraints designated? Will the IMM be monitoring offers during this time? If not, you may not get very productive results to analyze.
2.5 | "QSE's submission of Resource offer curves " is listed as entry and exit criteria. Why does this appear in both places?
3.3 | Suggestion to preface the list of market participant readiness activities with the following statement just to add a little more clarity: "Here are the key activities that are expected from each Market Participant before and during EDS Release 6:"
3.3 | Regarding the statement, "QSE EMS Nodal system changes complete". How much lead-time will MPs be given to update their systems? What does this really mean?
5 | Will the billing determinants also be provided?
7.1 | I would suggest breaking this into a separate approach document for EDS if you haven’t already done so. This will need to be repeated in the subsequent detailed planning documents (if you put it in here).
9 | I would move this to the Overview section – this seems to address what I was trying to communicate in the new section I created called “Market Participant Expectations”. The term required might be confusing if some of the activities are not truly required (pre-October)
7,9,11 | Some of graphics in these sections are blurry and difficult to read.
General | It appears the EDS 3 Detailed plan is not going to be out until May. This makes planning and estimating very difficult as the current level of detail in the EDS 3 approach is not sufficient to perform these tasks with any degree of accuracy. Furthermore, there are little to no details regarding EDS 4 at this time. If participants don't know what testing activities will be performed and when, then they will have trouble putting together a viable work plan.
General | Market Trials Start Milestone - The EDS timelines shows a Market Trials start of January 1, 2008. However, your Market Trials Approach says that Market Trials includes all EDS testing. Since EDS 1 is already underway, should we assume Market Trials is underway? If not, when is the true start of Market Trials (e.g., EDS 3?). The start of Market Trials does not sync up with your EDS 3 approach when you state all QSEs must be ready by Oct'2007.
General | Stages of EDS Testing - In the latest EDS 3 approach, you define three different testing windows: Interface Testing, Data Validation Testing, and Release Testing. According to the documentation, it appears that Interface Testing and Data Validation testing is optional, while Release Testing is required. Is this correct? If so, it appears October 2007 is the date that all QSEs should be targeting. Can a QSE participant in earlier testing if it chooses? What service levels will ERCOT provide? Will this be defined in the EDS 3 detailed plan?
General | Staffing - Nodal EDS prep and execution teams are expected to be in place for EDS 3. For what dates? Start of Interface Testing? Start of Data Validation? Start of Release Testing? At this point, high-level draft calendars would be helpful.
General | Your EDS 3 PowerPoint presentations state that only CRR settlement will be available. However, the detailed plan says CRR and RT settlements will be available. Can you clarify which is correct? Will enough Information be published to support shadow settlement testing?