## Slide 1: Market Coordination Team Update Retail Market Subcommittee May 9, 2007 Jennifer Frederick Senior Business Analyst/MODPO

## Slide 2: Risks / Issues
Issue | Mitigation | Owner
Resource Constraint from May Retail Release (Low) | Schedule and resource management Milestone completion | ERCOT
PUCT Mandate of 07/01/2007 poses tight timeline (Med) | Schedule and resource management Milestone completion | All
AIX Server Consolidation (Low) | AIX and TX SET Project Teams working closely together on dates. All servers used by TX SET have been scheduled for after 07/01/2007. | ERCOT
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 3: Project Schedule
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 4
PR40038_01 Status
Status:
  On target for schedule, budget, and scope
Project Phases:
  Initiation – Completed
  Planning – Completed
  Execution – Mandated completion date July 1, 2007; Go-Live 06/24/2007
  Closing – Target completion is post go-live
Recent Activity as of May 1, 2007:
  Began Flight Test
  Migrate ETS and Reprocessing Build
  Began UAT for ETS and Reprocessing
  Began Regression Testing
  Define Shut down Plan with MCT
  Migrated TX SET Changes Operational Data Store (Database table changes to EDW)
  Migrated new columns to TDSP ESIID Extract and Siebel Service Order Extract Internally at ERCOT (Part of PR50059_03 EIS Release)
Next Steps for ERCOT as of May 1, 2007:
  Complete UAT
  Finalize Production Migration Tasks
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 5
PR40038_01 Status
Recent Activity for MCT:
  RMGRR for Customer Billing Contact Information file – change to RMGRR042 allowing CRs whose systems were unable to send .csv files to now send files with *.csv*
  Completed Draft Production Implementation Plan – will be Final on May 11, 2007
Next Steps for MCT:
  Continue to monitor Market issues and progress
  Develop Production Contingency Plan
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 6: May Status Reporting - CRs
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO
To be updated prior to 5/9/07 RMS meeting

## Slide 7: May Status Reporting – ERCOT and TDSPs
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO
To be updated prior to 5/9/07 RMS meeting

## Slide 8: CRs not Reporting - May
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO
To be updated prior to 5/9/07 RMS meeting

## Slide 9: Information on PR 40038
Draft Production Implementation Plan for Texas SET 3.0
  Conference Calls were held to discuss the Draft Plan on Thursday, April 12 and Wednesday, April 18
  Draft Plan is located in Key Documents on MCT page of ERCOT.com and is also included with RMS meeting documents
  Please review the plan and forward any comments and/or questions to Susan Munson (smunson@ercot.com)
  Draft Implementation Plan will become Final Implementation Plan on Friday, May 11
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 10: Customer Billing Contact Information File Naming Convention
MCT proposed RMGRR052 to change Customer Billing Contact Information (CBCI) file naming convention
  Why? Some CRs are unable to send a file with .csv file extension as specified by RMGRR042 and required in current RMG
  File naming convention as defined in RMGRR052 will provide CRs whose systems append data to the file extension to send the file with .csv anywhere in the CBCI file name (.csv*)
  CRs are required to successfully test sending CBCI files to ERCOT to comply with POLR rule to be implemented as part of Texas SET 3.0 by July 1, 2007
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 11: Reminder: Where are Texas SET 3.0 Key Documents Kept?
  MCT page – ERCOT.com
  http://www.ercot.com/committees/board/tac/rms/mct/index.html
  And what is there?
  Texas SET Version 3.0 Requirements Final Version 1.9
  Texas SET 3.0 - MCT Issues & FAQs Log
  Texas SET Version 3.0 Change Controls
  Texas SET Guides Version 3.0
  Texas SET Version 3.0 Implementation Plan DRAFT
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 12
Meeting Dates and Locations 2007
  May 24 – ERCOT Met Center
  June 25 – Emergency MCT Conference Call (only if needed)
  June 28, 9:00 AM CPT – MCT and TX SET Conference Call
  July 25 – Location TBD
  August 29 – Location TBD
(Note: all meetings are held in conjunction with TX SET meetings)
Future Meetings/Market Communications
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 13: ERCOT Contacts
ERCOT Project Manager ERCOT SR. Business Analyst
Hope Parrish Jennifer Frederick
hparrish@ercot.com jfrederick@ercot.com
512-248-6522 (w) 512-248-6733 (w)
512-771-9582 (c) 512-413-0815 (c)
ERCOT Market Liaison
Susan Munson
smunson@ercot.com
512-248-3881 (w)
512-826-0564 (c)
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 14: Questions?
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO