## Slide 1: PR50121_07 Retail Business Processes (RBP) Project Update
A Sub-project of the Service Oriented Architecture (SOA) Initiative

## Slide 2: Overview
Review Project Status
Review Transaction Metrics
Questions

## Slide 3: Project Status
Project Phases
Execution
  Go-Live – Completed 12/10/2006 (within schedule and budget)
  Stabilization effort – Completed 03/26/2007
Closing – Started
Recent Activities As of 05/01/2007
Completed Stabilization Efforts
Completed Architecture Assessment by TIBCO
Completed Draft Monitoring Enhancement Plan to be completed by Retail Commercial Operations in conjunction with Nodal efforts
Next Steps
Compile Overall Project Lessons Learned
Obtain Project Sign-Off
Close Project
Prepare Metrics for August RMS
PR50121_07 RBP PPL Source: ERCOT Priority: 1.0 Rank: .08 Budget: $1-3M Program Area: RO

## Slide 4: Transaction Processing Metrics – Middleware
DATE | AVG Volume per 10 minutes (Seebeyond) | AVG Processing Time in Seebeyond Application
12/04/2006 (Mon) | 339 | 1500
12/05/2006 (Tues.) | 356 | 1471
12/06/2006 (Wed.) | 338 | 533
12/07/2006 (Thurs) | 315 | 457
Total Average December, 2006 | 337 | 990.25
DATE | AVG Volume per 10 minutes (TIBCO) | AVG Processing Time in TIBCO Application
03/12/2007 (Mon) | 325 | 372
03/13/207 (Tues) | 420 | 496
03/14/2007 (Wed) | 394 | 490
03/15/2007 (Thurs) | 373 | 530
Total Average March, 2007 | 378 | 472
December, 2006 (Seebeyond) compared to March, 2007 (TIBCO)
PR50121_07 RBP PPL Source: ERCOT Priority: 1.0 Rank: .08 Budget: $1-3M Program Area: RO

## Slide 5: Transaction Processing Metrics – Middleware Cont’d
DATE | AVG Volume per 10 minutes (Seebeyond) | AVG Processing Time in Seebeyond Application
12/04/2006 (Mon) | 339 | 1500
12/05/2006 (Tues.) | 356 | 1471
12/06/2006 (Wed.) | 338 | 533
12/07/2006 (Thurs) | 315 | 457
Total Average December, 2006 | 337 | 990.25
DATE | AVG Volume per 10 minutes (TIBCO) | AVG Processing Time in TIBCO Application
04/30/2007 (Mon) | 407 | 437
05/01/2007 (Tues) | 425 | 369
05/02/2007 (Wed) | 417 | 393
05/03/2007 (Thurs) | 353 | 370
Total Average April, 2007 | 400.5 | 392.25
December, 2006 (Seebeyond) compared to April, 2007 (TIBCO)
PR50121_07 RBP PPL Source: ERCOT Priority: 1.0 Rank: .08 Budget: $1-3M Program Area: RO

## Slide 6: Transaction Processing Metrics – Against Protocol
Table below represents Initiating Transactions Only provided by ETS. Complete Transaction Protocol Report from ETS is located with Meeting Materials.
Business Process | Transaction Type | # Required Responses | Resulting Transactions | 12/7/2006 Avg Time Within Protocol (Seebeyond) | 05/03/2007 Avg Time Within Protocol (TIBCO)
Switch | 814_01 | 2735 |  |  | 
 |  |  | 814_02 | 01:25:27 | 00:29:36
 |  |  | 814_03 | 01:54:47 | 00:37:16
 |  |  | 814_08 | 00:35:26 | 00:15:37
Move-In | 814_16 | 7935 |  |  | 
 |  |  | 814_03 | 01:04:07 | 00:35:38
 |  |  | 814_17 | 01:01:35 | 00:38:53
CSA | 814_18 | 2839 |  |  | 
 |  |  | 814_18 | 01:00:45 | 01:11:57
 |  |  | 814_19 | 04:05:06 | 01:13:41
Move-Out | 814_24 | 4770 |  |  | 
 |  |  | 814_03 | 01:01:06 | 00:34:28
 |  |  | 814_24 | 01:00:51 | 00:34:22
 |  |  | 814_25 | 00:59:47 | 00:22:55
PR50121_07 RBP PPL Source: ERCOT Priority: 1.0 Rank: .08 Budget: $1-3M Program Area: RO

## Slide 7: Questions / Contact
Adam D. Martinez
Mgr, Market Operations Divisional Projects Organization
ERCOT
(512) 248-3883
amartinez@ercot.com
Hope Parrish
PM, Market Operations Divisional Projects Organization
ERCOT
(512) 248-6522
hparrish@ercot.com