Registration and Qualification Guide for the Nodal Market

v0.4

Revision History

| Date | Version | Description | Author |
| --- | --- | --- | --- |
| 4/25/07 | 0.40 | Release to TPTF for comments | M. Mereness / IRT |

Table of Contents

1.0 Summary of Registration and Qualification Guide	2

2.0 Background on the Qualification Approach for the nodal market	3

3.0 Purpose of document	4

4.0 Qualification by Participant Activity	5

4.1  Qualification Steps for CRR Account Holder	6

4.2  Qualification Steps for QSE without Resources	7

4.3  Qualification Steps for QSE with Resources	8

4.4  Participation Requirements of TSP	9

5.0 Qualification Step Descriptions	10

5.1 Registration Activities	10

Step R1 - Registration Application	10

Step R2 - Standard Form Agreements	11

Step R3 - Designate Counter-Party	11

Step R4 - Attestation of Qualification for Ancillary Services	12

Step R5 - Incremental Resource Asset Registration	13

5.2 Qualification Activities	14

Step Q1 - Credit Application	14

Step Q2 - Communication Installation (Wide Area Network data circuit)	15

Step Q3 – ERCOT Digital Certificates for ERCOT Systems	17

Step Q4 - Connect to API/Web Services/MIS for Market Interface Testing	17

Step Q5 - Communications (System Operations Real Time-ICCP)	18

Step Q5 - EDS1/Release1 - Network configuration verification and alarm testing	18

Step Q5 - EDS1/Release2 - Verify ICCP Links and Point-to-Point Verification	19

Step Q5 - EDS2/Release3 - Verify State Estimator, N/W Security Analysis, Telemetry Performance	20

Step Q5 - EDS2/Release4 - Verify Network Operations Model and Change Requests via NOMCR	21

Step Q6 - Communications (Market Operations)	22

Step Q6 - EDS3/Release5 - SCED Offers, ERCOT LMPs Testing	23

Step Q6 - EDS3/Release6 - Load Frequency Control Testing	24

Step Q6 - EDS3/Release7 - CRR Allocation and Auction Testing	24

Step Q6 - EDS4/Release8 – Real-Time Settlement and Energy Offers Testing	25

Step Q6 - EDS4/Release9 - DAM, RUC, SASM, Outages, Disputes, 168Hr Test	26

Step Q7 - Site Visit	27

# 1.0 Summary of Registration and Qualification Guide

This document is designed as a roadmap for Market Participants to understand the activities required of them in initiating business or transitioning current business to the ERCOT nodal market.  This document describes the basic areas in which Market Participants will be engaging ERCOT, from ERCOT Legal for Standard Form Agreements, to ERCOT development for interface testing, to ERCOT Operations for coordinated load frequency control testing.  This guide includes summaries of the necessary Registration and Qualification activities leading up to completion Market Participant preparedness.  More details and background of the registration and qualification process are defined in the TPTF-approved Registration Approach Document_v1.0, and the TPTF-reviewed Qualification Approach Document v0.72 documents.

A tabular summary of the registration and qualification activities are presented in Figure 1 below.  All registration and qualification steps are not required for all Market Participants.  The remainder of this document is dedicated to mapping out the specific steps required for each Market Participant type to meet registration and qualification requirements.  Please note Market Participants can register to function in multiple roles, but do not need to complete duplicate paperwork for each role (for example, if Company XYZ registers as a QSE and CRR Account Holder, there is only the need to complete a single Standard Form Agreement.)  Also, for readers looking for dates of these described activities, those dates should soon be available in a summary reference document on the Nodal Transition Readiness Center site providing an activity list and calendar.

Figure 1- Table of Registration and Qualification Steps

X   Required

X* Required only for new MP

O   Optional

# Please include a table that identifies all of the forms used for Qualification and Testing, identify whether forms are existing forms or new forms.  If new forms, please indicate:

# the date the form will be provided to the MP for review and comment,

# the due date for comments,

# the date on which ERCOT expects to post the forms as final and the location of the posting for all forms, and

- the last date on which the MP must submit the form to ERCOT.

Please make clear that the dates identified in this document and the accompanying Power Point presentation include the issue date of the form, a due date for MP’s comments, and the date on which the form is to be available for use by MPs.

# 2.0 Background on the Qualification Approach for the nodal market

ERCOT’s transition to the nodal market changes many of the interactions between ERCOT and Market Participants.  The nodal protocols introduce new markets, create new transactions and modify requirements for existing transactions between ERCOT and Market Participants.  As such, ERCOT and Market Participants are developing new systems. These changes in the market require training on the nodal market rules, systems, transactions, communication protocols and other requirements.

The ERCOT protocols require Market Participants to demonstrate, to ERCOT’s reasonable satisfaction, they are capable of performing the functions required of them as stated in the protocols.  ERCOT is obligated to assure each Market Participant has met the necessary requirements for entry into the market and to monitor and support continued operation in the market.  To assure Market Participants are capable of successful operations in the nodal market, ERCOT has defined readiness activities that must be completed before entering the market including qualification tests for those Market Participants required to be qualified by the protocols.  This is consistent with current market procedures, where ERCOT qualifies the entities functioning as scheduling entities (QSEs).

For transitioning to the nodal systems, the communication, migration, and testing plans will be conducted and coordinated through a series of four Early Delivery Systems (EDS) spanning 2007 and 2008.  These systems are being developed and delivered in phased releases for the purpose of ERCOT and Market Participant incremental testing and carrying forward to go-live systems. This will enable all parties to test and stabilize their nodal systems.  Market Participants are required to participate in all EDS phases, and ERCOT will monitor and report participation by Market Participant.   Participation activities are provided for each Market Participant function and outlined in Section 4 below.

# 3.0 Purpose of document

This document is intended to serve as a guide to each Market Participant required to participate and be qualified for the nodal market.  This is done by presenting qualification activities for each Market Participant type in a manner that will readily communicate the list of applicable qualification activities, the sequence in which the qualification activities are to be executed, corresponding timeline and in relation to the nodal program timeline.

Market Participants should utilize the section of the guide corresponding to their participation activities in the nodal market. The qualification guide is focused on the activities specific to qualification as it applies to Congestion Revenue Rights (CRR) Account Holders, Qualified Scheduling Entities (QSE), and Transmission Service Providers (TSP).  Although TSPs are not formally “qualified” by ERCOT protocols, there are a series of activities that are required and captured in this document to communicate TSP obligations in participating and adapting to network model process and system changes.

For each Market Participant type and level, the guide will delineate each qualification activity as follows:

- Who- Describe which Market Participant activities are impacted

- What - Describes the nature of the activity

- When - Defines the timeline for qualification

- Participation- Describe if requirement is mandatory and the outcome of qualification step

- References - Provides reference materials to facilitate the successful completion of the qualification activity

Each Market Participant is encouraged to contact their assigned Account Manager with any questions. If a Market Participant is new to the market or does not know who their assigned Account Manager, they are encouraged to contact ERCOT’s Client Services department at (512) 248-3900 or via e-mail at NodalMarketTransition@ercot.com for further assistance.

# 4.0 Qualification by Participant Activity

The following pages provide a listing of the activities applicable to the Market Participant depending on their functional role(s) in ERCOT.  For each role, a table is created highlighting the applicable activities.

Based on the highlighted steps below, the reader can identify the necessary steps for their qualification activities and proceed to Section 5.0 Qualification Step Descriptions to get more information on completing each of these steps.  Included in Section 5 are more details and reference documents that will be useful in understanding and supporting those activities.

Qualification testing during this transition will be both cumulative and repetitive as incremental releases of systems introduce new functionality to be tested, as well as require some level of regression testing on existing functionality for both ERCOT and Market Participant systems.  ERCOT will track individual qualifications with scorecards for each Market Participant, and communicate with the Market Participant regarding their individual qualification status over time.   The culmination of qualification activities will be in the final 168-hour test as described later in this document.  Upon successful completion of the 168-hour test, individual qualification activities will be assessed for each Market Participant and ERCOT digital certificates will be provisioned for those Market Participants that successfully qualify.  For those participants that do not meet the qualification requirements, ERCOT will work directly with those parties, as time and bandwidth allow, providing for additional testing.

## 4.1  Qualification Steps for CRR Account Holder

The new role of CRR Account Holder in the ERCOT market will require new registration and qualification activities.  The table below of qualification activities highlights the steps which will be required of CRR Account Holders to qualify for the nodal market.

| Steps | Description |
| --- | --- |
| Registration | Registration Activities |
| R1 | Registration Applications |
| R2 | Standard Form Agreements |
| R3 | Designate Counter-Party |
| R4 | Attestation of Qualification for Ancillary Services |
| R5 | Resource Asset Registration |
| Qualification | Qualification Activities |
| Q1 | Credit Application |
| Q2 | Communication Installation (Wide Area Network data circuit) |
| Q3 | ERCOT Digital Certificates for ERCOT systems |
| Q4 | Connect to API/Web Services/MIS for Market Interface Testing |
| Q5 | Communications (System Operations- Network Model and Real Time-ICCP) |
| Q5-E1R1 | EDS1/Release1 - Network configuration verification and alarm testing |
| Q5-E1R2 | EDS1/Release2 - Verify ICCP Links and Point-to-Point Verification |
| Q5-E2R3 | EDS2/Release3 - Verify State Estimator, N/W Security Analysis, Telemetry Performance |
| Q5-E2R4 | EDS2/Release4 - Verify Network Operations Model and Change Requests via NOMCR |
| Q6 | Communications (Market Operations) |
| Q6-E3R5 | EDS3/Release5 - SCED Offers, ERCOT LMPs Testing |
| Q6-E3R6 | EDS3/Release6 - Load Frequency Control Testing |
| Q6-E3R7 | EDS3/Release7 - CRR Allocation and Auction Testing |
| Q6-E4R8 | EDS4/Release8 - Real-Time Settlement and Energy Offers |
| Q6-E4R9 | EDS4/Release9 - DAM, RUC, SASM, Outages, Disputes, 168Hr Test |
| Q7 | Site Visit (upon request) |

(Note- the gray text in the table implies the step is not required.  Only the steps in bold-font are required.)

## 4.2  Qualification Steps for QSE without Resources

For QSEs without Resources, the table below highlights the steps required of a QSE seeking qualification to participate in the nodal market with a focus on serving load and/or marketing activities.  Please note this would be the equivalent of a Level 1 or Level 2 qualified QSE in the zonal market.  In nodal, ERCOT will only consider qualification of QSE with Resources, and QSE without Resources.

| Steps | Description |
| --- | --- |
| Registration | Registration Activities |
| R1 | Registration Applications |
| R2 | Standard Form Agreements |
| R3 | Designate Counter-Party |
| R4 | Attestation of Qualification for Ancillary Services |
| R5 | Resource Asset Registration |
| Qualification | Qualification Activities |
| Q1 | Credit Application |
| Q2 | Communication Installation (Wide Area Network data circuit) |
| Q3 | ERCOT Digital Certificates for ERCOT systems |
| Q4 | Connect to API/Web Services/MIS for Market Interface Testing |
| Q5 | Communications (System Operations- Network Model and Real Time-ICCP) |
| Q5-E1R1 | EDS1/Release1 - Network configuration verification and alarm testing |
| Q5-E1R2 | EDS1/Release2 - Verify ICCP Links and Point-to-Point Verification |
| Q5-E2R3 | EDS2/Release3 - Verify State Estimator, N/W Security Analysis, Telemetry Performance |
| Q5-E2R4 | EDS2/Release4 - Verify Network Operations Model and Change Requests via NOMCR |
| Q6 | Communications (Market Operations) |
| Q6-E3R5 | EDS3/Release5 - SCED Offers, ERCOT LMPs Testing |
| Q6-E3R6 | EDS3/Release6 - Load Frequency Control Testing |
| Q6-E3R7 | EDS3/Release7 - CRR Allocation and Auction Testing |
| Q6-E4R8 | EDS4/Release8 - Real-Time Settlement and Energy Offers |
| Q6-E4R9 | EDS4/Release9 - DAM, RUC, SASM, Outages, Disputes, 168Hr Test |
| Q7 | Site Visit (upon request) |

(Note- the gray text in the table implies the step is not required.  Only the steps in bold-font are required.)

## 4.3  Qualification Steps for QSE with Resources

QSEs that represent ERCOT Generation or Load Resources will be required to participate in almost all aspects of EDS.  The table below reflects the qualification activities which will be required of the QSE with Resources to qualify for the nodal market.  Please note this would be the equivalent of a Level 3 or Level 4 qualified QSE in the zonal market.  In nodal, ERCOT will only consider qualification of QSE with Resources, and QSE without Resources.

| Steps | Description |
| --- | --- |
| Registration | Registration Activities |
| R1 | Registration Applications |
| R2 | Standard Form Agreements |
| R3 | Designate Counter-Party |
| R4 | Attestation of Qualification for Ancillary Services |
| R5 | Resource Asset Registration |
| Qualification | Qualification Activities |
| Q1 | Credit Application |
| Q2 | Communication Installation (Wide Area Network data circuit) |
| Q3 | ERCOT Digital Certificates for ERCOT systems |
| Q4 | Connect to API/Web Services/MIS for Market Interface Testing |
| Q5 | Communications (System Operations- Network Model and Real Time-ICCP) |
| Q5-E1R1 | EDS1/Release1 - Network configuration verification and alarm testing |
| Q5-E1R2 | EDS1/Release2 - Verify ICCP Links and Point-to-Point Verification |
| Q5-E2R3 | EDS2/Release3 - Verify State Estimator, N/W Security Analysis, Telemetry Performance |
| Q5-E2R4 | EDS2/Release4 - Verify Network Operations Model and Change Requests via NOMCR |
| Q6 | Communications (Market Operations) |
| Q6-E3R5 | EDS3/Release5 - SCED Offers, ERCOT LMPs Testing |
| Q6-E3R6 | EDS3/Release6 - Load Frequency Control Testing |
| Q6-E3R7 | EDS3/Release7 - CRR Allocation and Auction Testing |
| Q6-E4R8 | EDS4/Release8 - Real-Time Settlement and Energy Offers |
| Q6-E4R9 | EDS4/Release9 - DAM, RUC, SASM, Outages, Disputes, 168Hr Test |
| Q7 | Site Visit (upon request) |

(Note- the gray text in the table implies the step is not required.  Only the steps in bold-font are required.)

## 4.4  Participation Requirements of TSP

The TSP is responsible for participation in the EDS activities related to the network model.  Nodal requirements include retiring RTU communication with ERCOT and transitioning to ICCP only, transitioning from submitting network model changes in Service Requests to Network Operations Model Change Request (NOMCR), and other activities.  These activities are limited to EDS1 and EDS2 activities and are highlighted in the table below.

| Steps | Description |
| --- | --- |
| Registration | Registration Activities |
| R1 | Registration Applications |
| R2 | Standard Form Agreements |
| R3 | Designate Counter-Party |
| R4 | Attestation of Qualification for Ancillary Services |
| R5 | Resource Asset Registration |
| Qualification | Qualification Activities |
| Q1 | Credit Application |
| Q2 | Communication Installation (Wide Area Network data circuit) |
| Q3 | ERCOT Digital Certificates for ERCOT systems |
| Q4 | Connect to API/Web Services/MIS for Market Interface Testing |
| Q5 | Communications (System Operations- Network Model and Real Time-ICCP) |
| Q5-E1R1 | EDS1/Release1 - Network configuration verification and alarm testing |
| Q5-E1R2 | EDS1/Release2 - Verify ICCP Links and Point-to-Point Verification |
| Q5-E2R3 | EDS2/Release3 - Verify State Estimator, N/W Security Analysis, Telemetry Performance |
| Q5-E2R4 | EDS2/Release4 - Verify Network Operations Model and Change Requests via NOMCR |
| Q6 | Communications (Market Operations) |
| Q6-E3R5 | EDS3/Release5 - SCED Offers, ERCOT LMPs Testing |
| Q6-E3R6 | EDS3/Release6 - Load Frequency Control Testing |
| Q6-E3R7 | EDS3/Release7 - CRR Allocation and Auction Testing |
| Q6-E4R8 | EDS4/Release8 - Real-Time Settlement and Energy Offers |
| Q6-E4R9 | EDS4/Release9 - DAM, RUC, SASM, Outages, Disputes, 168Hr Test |
| Q7 | Site Visit (upon request) |

(Note- the gray text in the table implies the step is not required.  Only the steps in bold-font are required.)

# 5.0 Qualification Step Descriptions

## 5.1 Registration Activities

### Step R1 - Registration Application

| Activity | Registration Application |
| --- | --- |
| Who | CRR Account Holders New QSEs only New TSPs only |
| What | Each Market Participant is to complete an application form for each role in which it plans to participate in ERCOT. If a Market Participant wishes to function as a QSE and CRR Account Holder, that Market Participant would complete registration application forms for each role. Some registration applications require a fee, which is stipulated in the registration application form. All CRR Account Holders are required to complete a Market Participant registration application form for CRR Account Holder. New QSEs and TSPs are required to complete a Market Participant registration application form for their respective activities. Existing QSEs/TSPs (optional): do not need to re-register unless they are considering changes to their business that may submit a “Notice of Change of Information” request updating registration records already on file, such as updating contacts, bank information, etc. Note that any new Load Serving Entities and Resource Entities must also register, but there are no changes to the forms that already exist in the zonal market. |
| When | The objective is to update and complete most of the registration paperwork between June 1 and November 1, 2007 to allow time for updates to the Registration data in preparation for populating data for EDS activities. New CRR Account Holder and updated QSE Registration applications are expected to be available for download on ERCOT’s website by June 1, 2007. |
| Participation | - Registration step is required. - Registration step is satisfied when the Market Participant has submitted a properly completed registration application form(s) and any applicable fees to ERCOT, and ERCOT has confirmed receipt. |
| References | Registration Approach document provides further details of registration activities: http://nodal.ercot.com/docs/pd/irt/index.html#oth In June 2007, the new and updated registration application forms can be downloaded from ERCOT’s website at the following location: http://nodal.ercot.com/readiness/index.html For any questions in completion of the registration application form, contact ERCOT’s Client Services department by phone at (512) 248-6900 via e-mail at NodalMarketTransition@ercot.com. |

### Step R2 - Standard Form Agreements

| Activity | Standard Form Agreements |
| --- | --- |
| Who | All LSEs, QSEs, TSPs, DSPs, CRR Account Holders, Resource Entity, REC Account Holder |
| What | Market Participants are required to execute the approved nodal version of the Standard Form Market Participant Agreement (SFMPA) with ERCOT. This agreement is embodied in Section 22 of the ERCOT Nodal Protocols. This process of circulating and signing the updated agreements will be administered by the ERCOT Legal department. |
| When | For existing Market Participants, the SFMPA will be circulated in the June-November 2007 timeframe (note that this timing is dependent on the ERCOT stakeholder process for NPRR058 which has some necessary revisions to Protocols Section 22). For new Market Participants, the SFMPA is signed during the process of submitting applications to become a new participant in ERCOT activities. |
| Participation | - Registration step is required. - Registration step is satisfied when ERCOT Legal and Market Participant have signed the Standard Form Agreement. What is the desired completion time for MP execution of the SFMPA? |
| References | Section 22 of the ERCOT protocols contains the Standard Form Market Participant Agreement; however, this agreement is under revision by NPRR058- Clarification of Standard Form Market Participant Agreement. This NPRR and the Nodal Protocols can be downloaded from ERCOT’s website at the following location. http://nodal.ercot.com/protocols/index.html |

### Step R3 - Designate Counter-Party

| Activity | Designate Counterparty |
| --- | --- |
| Who | CRR Account Holders QSEs |
| What | Counter-Party is a concept used in Nodal Protocols to allow for the netting of credit across all QSEs and CRR Account Holders that are under a single Market Participant. To allow for this netting to occur, one of the CRR Account Holders or QSEs for the Market Participant must be designated to serve as the Counter-Party. The QSE or CRR Account Holder with this designation will have access to download the Available Credit Limit for the Market Participant. For new QSEs and CRR Account Holders, this information will be captured on the new registration forms. For existing QSEs, ERCOT Wholesale Client Services will be creating a new form to send to each Market Participant for the designation of which QSE or CRR Account Holder shall be the designee for the Market Participant to serve as the counterparty. {Question: You previously state that all CRR Account Holders must complete a MP registration. Does this mean that a QSE which will also be a CRR Account Holder must separately register as a CRR Account Holder? If this is true, can the Account Holder form be used to identify the counter party in the QSE/CCR Account Holder relationship?} |
| When | This will be done in the same timeframe as updating other registration information, June1-November 1, 2007. |
| Participation | - Registration step is required. - Registration step is satisfied when Market Participant has submitted Counter-Party designation document to ERCOT, and ERCOT has confirmed receipt. |
| References | For new participants, this designation will be part of the new Registration forms and can be downloaded from ERCOT’s website after June 1, 2007 at the following location: http://nodal.ercot.com/readiness/index.html For existing QSEs, ERCOT will be providing the Accountable Executives with the document to formally select the designation. For any questions, contact ERCOT’s Client Services department by phone at (512) 248-6900 via e-mail at NodalMarketTransition@ercot.com . |

### Step R4 - Attestation of Qualification for Ancillary Services

| Activity | Attestation of Qualification for Ancillary Services |
| --- | --- |
| Who | Existing QSEs with Resources only |
| What | This is an optional step, but recommended to existing QSEs with Resources providing Ancillary Services in the current ERCOT market. If the Attestation described herein is not utilized, each Resource is required to follow full qualification processes as described in Nodal Protocols and Operating Guides. For existing QSEs representing Resources, the Market Stakeholders and ERCOT Operations agreed to an approach of allowing QSEs to self-certify their Resources for Ancillary Services by completing an “Attestation of Qualification for Ancillary Services”. This approach was agreed to recognizing there will be focused testing on load frequency control during EDS 3 and 4. The approach agreed to was for the QSE to exercise due diligence in identifying their Resources which are currently providing A/S in the current zonal market, and committing to develop and transition those Resources to meet the requirements of the Nodal Protocols and operating guides. In addition, ERCOT will develop monitoring tools needed to individually assess the Resource performance during EDS3 and 4 testing, with special attention to performance of these Resources during Load Frequency Control testing. {Note: The EMS Conceptual Design provides the system for the collection of data during the EDS test sequence; it is not clear which ERCOT organizational function is responsible for evaluating the performance data. We do not believe this to be an EDS test team responsibility.} With the completion of this Attestation, the Resource(s) of interest will be qualified and recorded in the ERCOT systems, and remain qualified pursuant to successful participation in EDS and LFC activities. [Note: We interpret this to mean that QSEs will be able to schedule their resources for performance testing at a time during the EDS 3 and 4 timeline when LFC is in service. This should include retest, if needed. If the Resource cannot be qualified during the EDS 3 or 4 timelines, the QSE will need to qualify the Resource in accordance with the Nodal Protocols and Operating Guides. For new participants, A/S qualification testing will be conducted for as required by Nodal Protocols and Operating Guides. |
| When | The attestation form will be issued on xx/xx/xxxx, MP comments will be due xx/xx/xxxx, and the form will be finalized for execution on xx/xx/xxxx. |
| Participation | - Registration step is optional. - Registration step is satisfied when Market Participant has submitted Attestation to ERCOT, and ERCOT has confirmed receipt. |
| References | For existing QSEs, ERCOT will be contacting the Accountable Executives with the Attestation to report the designation of Resources providing Ancillary Services. For new participants, this will be part of the qualification procedures being developed in the Nodal Operating Guides. For any questions, contact ERCOT’s Client Services department by phone at (512) 248-6900 via e-mail at NodalMarketTransition@ercot.com. |

### Step R5 - Resource Asset Registration

| Activity | Resource Asset Registration {Note: There is no need to use the term “incremental”. The Nodal Protocols require new resource parameters for all its existing resources. Your forms should indicate that information already submitted and unchanged does not need to be resubmitted. However, the form should be complete in the sense that all of the required resource parameters are listed. |
| --- | --- |
| Who | QSEs with Resources |
| What | The nodal market design introduces new requirements in analyzing and dispatching Resources. To support these requirements, ERCOT will be updating and circulating an updated Asset Registration Forms (also know as the GARF). The Asset Registration Forms will address both Generation and Load Resources to ensure current asset data is correct and consistent, as well as solicit new Resource data elements as required in Nodal Protocols. ERCOT will send these forms to the QSEs and Resource Entities, as appropriate, to have thenew form(s) completed. |
| When | ERCOT will issue these forms for comment by xx/xx/xxxx, MP comments will be due xx/xx/xxxx, ERCOT will post the form on xx/xx/xxxx. MP should submit non-certified forms beginning xx/xx/xxxx with best information available to be used for testing. MP should provide incremental updates to Resource Registration Parameters periodicall throughout the testing process. For test purposes, ERCOT will populate the Resource Registration Parameters and overwrite with MP data. A certified version of Resource Registration Parameters must be provided by each MP by xx/xx/xxxx. |
| Participation | Registration step is required. Registration step is satisfied when the Market Participant has submitted updated asset registration data to ERCOT, and ERCOT has confirmed receipt. |
| References | For existing Resources, the new Asset Registration Forms will be circulated by ERCOT Wholesale Client Services. For new Resources, this will also be part of the new registration forms and can be downloaded from ERCOT’s website after June 1, 2007 at the following location: http://nodal.ercot.com/readiness/index.html For any questions, contact ERCOT’s Client Services department by phone at (512) 248-6900 via e-mail at NodalMarketTransition@ercot.com. |

## 5.2 Qualification Activities

### Step Q1 - Credit Application

| Activity | Satisfaction of credit requirements |
| --- | --- |
| Who | CRR Account Holders New QSEs only |
| What | Existing QSEs may continue with existing zonal market credit arrangements, however, with the introduction of the CRR Auction and Day Ahead Market, Market Participants should re-evaluate their credit arrangements with ERCOT in light of the credit requirements associated with participation in these additional markets as described below. It is also worth noting that the ERCOT Transition Plan 6.1(l) describes the transition of credit from the zonal market to the nodal market as follows: “The calculation of credit exposure is intended to use information from market settlement systems both before and after the Texas Nodal Market Implementation Date, regardless of how information is included on an Invoice. Invoices from the “old” market (before the Texas Nodal Market Implementation Date) will be used to calculate EAL until an Invoice that includes Initial Settlement Statements for a full seven days is generated under the “new” market (after the Texas Nodal Market Implementation Date). ERCOT shall base resettlement credit exposure on estimates from both settlement systems and shall take into consideration how much credit exposure is expected under each system. Notwithstanding the above, Financial Security required from each Counter-Party for the first six weeks from the date of conversion to the “new” market is equal to or greater than the Financial Security held on behalf of any Counter-Party at the date of conversion to the “new” market.” New QSEs and CRR Account Holders are required to complete a credit application form and to satisfy ERCOT’s creditworthiness requirements defined in Section 16 of the ERCOT protocols. The current Credit Application is posted as the Credit Application Form for QSE. Details of credit are posted on ERCOT’s website as the ERCOT Credit Worthiness Standards. As discussed in a previous step regarding Counter-Party, credit worthiness standards are enforced by ERCOT at an aggregate level, whereby multiple QSEs, Sub-QSEs, CRR Account Holders are consolidated from a credit perspective under a single Market Participant as a Counter-Party. An Initial Estimated Liability (IEL) will be determined by ERCOT according to section 16.11.4.2 of the ERCOT protocols. The calculated IEL, along with the applicable liabilities of other registered participants within the same Counter-Party, will be used to determine the Total Potential Exposure (TPE) of the Counter-Party. Satisfaction of ERCOT’s credit worthiness requirements for the purpose of initial qualification consists of meeting any collateral requirements determined by ERCOT for the applicable Counter-Party by subtracting the Counter-Party’s Unsecured Credit Limit from its Total Potential Exposure. |
| When | For new QSEs and CRR Account Holders, this will be done in the same timeframe as updating registration information, June1-November 1, 2007. |
| Participation | - Qualification step is required. - Qualification step is satisfied when ERCOT Finance has received and processed Credit Application. |
| References | Existing Credit Application Form for QSE is available, but will be updated and expanded to include CRR Account Holder and posted to the Nodal Transition Readiness Center at http://nodal.ercot.com/readiness/index.html Credit worthiness is described and posted in the posted version of Credit Worthiness Standards. Credit requirements are described in section 16.11 of the ERCOT Nodal Protocol, Financial Security for Counter-Parties (Nodal Protocols, Section 16), and ERCOT’s credit worthiness requirements are posted at: http://nodal.ercot.com/protocols/library/index.html |

### Step Q2 - Communication Installation (Wide Area Network data circuit)

| Activity | Communication Installation (Wide Area Network data circuit) |
| --- | --- |
| Who | New QSEs with Resources New TSPs only |
| What | Existing TSPs and QSEs with Resources- No incremental requirements if ICCP is in place and is capable of accommodating nodal communications. For new QSEs with Resources and new TSPs, there is a requirement for a private network connection to ERCOT for reliability and security reasons. Current estimates for this effort follow: -Initial Cost: Not to exceed $20,000 -Monthly Cost: Not to exceed $865 + LD Carrier Cost -Installation: 60-90 days from order -Testing Required Background All QSEs representing transmission connected Resources will be required to communicate with ERCOT via the Wide Area Network (WAN), which supports dedicated transfer of data between ERCOT and Market Participants. ERCOT Staff or its contractors will design, install, monitor and manage the ERCOT Private WAN. ERCOT will pay for all costs associated with each WAN connection and pass those actual costs to the Market Participant. The costs will be determined case-by-case, based on the communication options selected and bandwidth requirements of the Market Participant. ERCOT WAN Site Application and Equipment and Pricing Survey The Account Manager will forward WAN site surveys. These documents will provide ERCOT with contact information, desired installation options and bandwidth needs. These forms should be completed and returned to the Account Manager. Wide Area Network (WAN) Agreement The Account Manager will prompt ERCOT Legal to send an electronic copy of the applicable ERCOT WAN Agreement to the applicant. The Agreement should be executed as is, with no revisions. The executed Agreement should be returned to: Market Participant Registration, 7620 Metro Center Drive, Austin, Texas 78744. WAN cost estimate, Order and Installation Based on the survey, ERCOT will provide a cost estimate. ERCOT network Support will await approval from the applicant prior to ordering equipment and installation. Allow 60-90 days for installation after the date of order. Frame Relay Connectivity Test (data transfer) Upon installation of the Frame Relay, contact the Account Manager to schedule a one-hour Connectivity Test with ERCOT Network Support. Point to Point Installation (voice transfer) Voice communication installation options are identified in the WAN Application. Contact the Account Manager to schedule the maximum hour-long test (the test generally takes only a few minutes). |
| When | The completion of setting up a WAN connection takes an estimated 3-4 months. To ensure the communication installation is completed in time for EDS activities, this process should begin as soon as possible, and no later than August of 2007. |
| Participation | Qualification step is required. Qualification step is satisfied when ERCOT IT and Market Participant confirm proper connectivity. |
| References | For the latest forms and pricing, contact ERCOT’s Client Service department by phone at (512) 248-6900 via e-mail at ClientRelations@ercot.com. |

### Step Q3 – ERCOT Digital Certificates for ERCOT Systems

| Activity | ERCOT Digital Certificates for ERCOT Systems |
| --- | --- |
| Who | CRR Account Holders All QSEs and TSPs |
| What | Each existing and new Market Participant must have a digital certificate to participate in qualification activities. The current Market Interface Testing environment (“Nodal Sandbox”) allows access with any valid ERCOT digital certificate. With the release of the forthcoming EDS environments, new testing digital certificates will be needed. The existing process for requesting and digital certificates and security requirements are described in Nodal Protocols Section 16.12, User Security Administrator and Digital Certificates. However, the process for requesting the digital certificates for testing and EDS activities is still under development and will be communicated as the EDS environments are established. Digital certificates will be used during the EDS testing to ensure functional security is in place and tested. |
| When | Prior to initiation of EDS3 activities. Up to date calendar posting for EDS activities should soon be available in a reference document on the Nodal Transition Readiness Center site providing an activity list and calendar. |
| Participation | - Qualification step is required. - Qualification step is satisfied when Market Participant “User Security Administrator” requests and receives digital certificate from ERCOT. |
| References | Nodal Protocols Section 16.2.1, Criteria for Qualification as a Qualified Scheduling Entity, and Section 16.12, User Security Administrator and Digital Certificates. |

### Step Q4 - Connect to API/Web Services/MIS for Market Interface Testing

| Activity | Connect to API/Web Services/MIS for Market Interface Testing |
| --- | --- |
| Who | All QSEs |
| What | In order to make EDS testing more effective, ERCOT will release interfaces to the market for initial connectivity testing prior to the fully-functional application being available. This allows the MP and ERCOT to work out any issues with connectivity, security, and transaction structural errors prior to full functional testing. Companies and developers utilizing APIs (Automated Programmatic Interfaces), also known as Machine-to-Machine interfaces, will be very involved in this area of qualification. |
| When | This environment is in place and available in an ongoing basis. |
| Participation | - Current plan is for the qualification step to be required for API users, recognizing this environment will be an initial test-bed for validating technical success of API submissions. - ERCOT will track the MPs capable of interfacing with the API and scorecard which transaction tests are successfully submitted. |
| References | External interfaces and message structures are described in the Machine-to-Machine (External) Interface Specifications. The overview of the technical environment for testing and the sample client code-sets for accessing the test system are described in the postings available at: http://nodal.ercot.com/docs/pd/irt/index.html#oth including the documents of Sandbox Overview 1.1, Java and Microsoft.Net Client Packages. |

### Step Q5 - Communications (System Operations Real Time-ICCP)

| Activity | Communications (System Operations Real Time-ICCP) |
| --- | --- |
| Who | All QSEs with Resources All TSPs |
| What | New and Existing TSPs and New and existing QSEs with transmission connected Resources that have RTUs will need to convert over to ICCP communications for QSE-to-ERCOT telemetry. ICCP is a requirement of the nodal market to ensure adequate communication performance. The business case behind this transition is documented in TPTF discussion of Agenda Item 10 from the September 11, 2006 TPTF meeting at: http://www.ercot.com/calendar/2006/09/20060911-TPTF.html |
| When | This will be required prior to completion of EDS1 testing, which initiated in April 2007 and planned for completion later in the year. Up to date calendar posting for EDS activities should soon be available in a reference document on the Nodal Transition Readiness Center site providing an activity list and calendar. |
| Participation | Qualification step is required. Qualification step is satisfied when ERCOT IT and the Market Participant confirm full ICCP connectivity. |
| References | Details of the ICCP requirements are available in the following documents: - ICCP Communication Handbook: http://nodal.ercot.com/readiness/index.html - EDS 1 Approach: http://nodal.ercot.com/docs/pd/irt/index.html#oth |

### Step Q5 - EDS1/Release1 - Network configuration verification and alarm testing

| Activity | EDS1/Release1 - Network configuration verification and alarm testing |
| --- | --- |
| Who | Limited number of QSEs with Resources and TSPs |
| What | Description: This activity will analyze and improve the existing ERCOT operator alarm configuration. The EDS 1 team will work with the ERCOT operators to identify the desired alarm processing configuration to categorize, organize and prioritize alarms. This activity addresses ERCOT Nodal Transition Plan Tasks 5.4.1 (2f) and (2g), and will be verified using selected TSPs and QSEs. Specific TSP and QSE Activity: To verify the alarm configuration, ERCOT will work with selected Market Participant Operators to randomly test selected breakers and switches, and enter values that exceed selected limits to test message organization/categorization |
| When | Up to date calendar posting for EDS activities should soon be available in a reference document on the Nodal Transition Readiness Center site providing an activity list and calendar. |
| Participation | Not all Market Participants are required to participate in this activity, but reports will be generated on the outcome of the testing. Volunteers interested in participating can contact ERCOT’s Client Services department by phone at (512) 248-6900 via e-mail at NodalMarketTransition@ercot.com. |
| References | Details of the ICCP requirements are available in the following documents: - ICCP Communication Handbook: http://nodal.ercot.com/readiness/index.html - EDS 1 Approach: http://nodal.ercot.com/docs/pd/irt/index.html#oth |

### Step Q5 - EDS1/Release2 - Verify ICCP Links and Point-to-Point Verification

| Activity | EDS1/Release2 - Verify ICCP Links and Point-to-Point Verification |
| --- | --- |
| Who | All QSEs with Resources All TSPs |
| What | Release 2 will verify ICCP communication links from TSPs and QSEs and insure proper ERCOT communication links and failover. It will also perform point-to-point verification between ERCOT and each TSP and QSE for all SCADA telemetry. - Verify status by toggling each breaker and switch and verifying change in status and in quality code - Perform analog verification by cross-checking displayed values at ERCOT and at TSPs/QSEs for each telemetered analog point - Verify correct operation of telemetered quality codes by manually replacing selected analog points - Identify issues and request TSPs and QSEs to submit change request to correct errors Market Participant Exit criteria/Qualification: • Market Participants must have redundant ICCP capabilities and failover, configured to communicate with the ERCOT nodal EMS, which includes existing Zonal data points, new nodal data points and new nodal data sets, as specified by the Nodal Protocols. • Market Participant ICCP data links are to be configured with the same data sets as those used for both the ICCP and RTU data links, if applicable, in the zonal market. • QSEs will have a separate ICCP nodal environment that contains all points required by the Nodal Protocols. These points will not be contained in the zonal system. Also worth noting: • RTUs will not be configured in nodal but may be used to support EDS 1 mapping during the point-to-point testing. New points as required by Nodal Protocols must use ICCP. Zonal RTU communication will continue to the zonal systems. • ERCOT will provide the requirements for ICCP configuration, communication, failover, data and quality codes in April 2007. • The EDS 1 team will work with each Market Participant to confirm their scheduled start date and duration for the failover and point verification testing. |
| When | Up to date calendar posting for EDS activities should soon be available in a reference document on the Nodal Transition Readiness Center site providing an activity list and calendar. |
| Participation | - Qualification step is required. - Qualification step is satisfied when ERCOT IT and ERCOT Operations, in accordance with Market Participant, confirm proper ICCP connectivity and requirements. |
| References | Details of the ICCP requirements are available in the following documents: - ICCP Communication Handbook: http://nodal.ercot.com/readiness/index.html - EDS 1 Approach: http://nodal.ercot.com/docs/pd/irt/index.html#oth |

### Step Q5 - EDS2/Release3 - Verify State Estimator, N/W Security Analysis, Telemetry Performance

| Activity | EDS2/Release3 - Verify State Estimator, N/W Security Analysis, Telemetry Performance |
| --- | --- |
| Who | All QSEs with Resources All TSPs |
| What | Release 3 will include activities to address Telemetry and State Estimator performance and tuning, network load model restructuring, and network security analysis. As part of measuring data quality, Release 3 will use nodal EMS system functionality to measure Telemetry and State Estimator performance. Performance results will be available to ERCOT and submitted to TSPs and QSEs. Data points or the absence of data points that cause the SE to fail to meet the performance criteria will be analyzed and corrected between ERCOT and the TSP / QSE. Corrected telemetry will be observed and re-verified. Load modeling will be restructured to improve load adaptation and bus load forecasting. Network security will be addressed by verifying transmission constraints, dynamic ratings, SPS / RAP and load rollover mechanics. These activities address the ERCOT Nodal Transition Plan Tasks 5.4.1 (2b) (2c), 5.4.2 (1) (2) (4), and 5.4.3 (1) (2) (3). Exit criteria/Qualification: - TSP/QSE data points conform to Telemetry and SE performance criteria - Network Security Analysis functions are verified and ERCOT Operations has procedures in place to address: - Dynamic ratings management - Constraints and contingency - Special Protection Schemes (SPS) / Remedial Action Plans (RAP) - Load rollover - Transmission constraints management - Management of constraints as inputs to SCED - TSP/QSE make corrections to data points ERCOT Criteria: - ERCOT Operations have operating procedures in place to address TSP/QSE Telemetry and SE performance issues - The ERCOT SE is tuned and meets performance criteria - Load modeling has been restructured, load adaptation has been verified and bus load forecast changes have been verified |
| When | Up to date calendar posting for EDS activities should soon be available in a reference document on the Nodal Transition Readiness Center site providing an activity list and calendar. |
| Participation | - Qualification step is required. - Qualification step is satisfied when ERCOT is reasonably satisfied data corrections has been made to the network for the Market Participant’s respective points. |
| References | Details of the ICCP requirements are available in the following documents: - ICCP Communication Handbook: http://nodal.ercot.com/readiness/index.html - EDS 2 Approach: http://nodal.ercot.com/docs/pd/irt/index.html#oth |

### Step Q5 - EDS2/Release4 - Verify Network Operations Model and Change Requests via NOMCR

| Activity | EDS2/Release4 – Verify Network Operations Model and Change Requests via NOMCR |
| --- | --- |
| Who | All QSEs with Resources All TSPs |
| What | Release 4 will include activities to verify the nodal Network Model Management System (NMMS) database, the integration between NMMS and EMS, and the process that allows TSP and QSE to electronically submit model and ICCP changes to the NMMS database. A key activity will be to verify the Network Operations Model Change Request (NOMCR) and its change control process, beginning with TSP / QSE change request data submittals, acknowledgement and verification of the submittal, posting of updates to the NMMS database, and confirmation of the update with TSPs and QSEs. This activity addresses the ERCOT Nodal Transition Plan Task 5.4.1 (2a). Market Participant Qualification criteria: - Market Participant can successfully submit data changes via the NOMCR process ERCOT criteria: - ERCOT is ready to fully utilize the NOMCR process for all TSP/QSE data change requests - ERCOT has processes in place to use a “single entry model” to maintain both nodal and zonal network model databases when MPs submit changes via the NOMCR process - NMMS is the database of record for the network operations model, ICCP database, and operatorship / ownership information - NMMS database is under full change control - ERCOT discontinues the use of Service Requests for data changes and change control - ERCOT begins the use of the NOMCR process for data changes and change control |
| When | Up to date calendar posting for EDS activities should soon be available in a reference document on the Nodal Transition Readiness Center site providing an activity list and calendar. |
| Participation | - Qualification step is required. - Qualification step is satisfied when ERCOT records successful NOMCR transactions from Market Participant. |
| References | Details of the ICCP requirements are available in the following documents: - ICCP Communication Handbook: http://nodal.ercot.com/readiness/index.html - EDS 2 Approach: http://nodal.ercot.com/docs/pd/irt/index.html#oth |

### Step Q6 - Communications (Market Operations)

| Activity | Communications (Market Operations) |
| --- | --- |
| Who | All QSEs |
| What | Each QSE must maintain the capability for 7x24 operations and communications per protocols 16.2.1, Criteria for Qualification as a Qualified Scheduling Entity. In this protocol section, each QSE is required to “Maintain a 24-hour, seven-day-per-week scheduling center with qualified personnel for the purposes of communicating with ERCOT for scheduling and deploying the QSE’s Ancillary Services in Real-Time. Those personnel must be responsible for operational communications and must have sufficient authority to commit and bind the QSE and the Entities that it represents.” For existing QSEs, this is not a change in requirements for nodal support. For new QSEs, this requirement must be met and is subject to verification by a site visit upon reasonable notice from ERCOT. |
| When | Up to date calendar posting for EDS activities should soon be available in a reference document on the Nodal Transition Readiness Center site providing an activity list and calendar. |
| Participation | - Qualification step is required. - Qualification step is satisfied in QSE providing 7x24 phone number, and ability to be called upon during testing and production activities. |
| References | Protocol section 16.2.1, Criteria for Qualification as a Qualified Scheduling Entity. |

### Step Q6 - EDS3/Release5 - SCED Offers, ERCOT LMPs Testing

| Activity | EDS3/Release5 - SCED Offers, ERCOT LMPs Testing |
| --- | --- |
| Who | All QSEs with Resources |
| What | Release 5 will be the initial release of the Security Constrained Economic Dispatch program. The focus of the release is to work with Participants to ensure that: - QSEs can submit, modify, and retrieve SCED input data - ERCOT can execute SCED and distribute Locational Marginal Prices (LMPs) for evaluation - Review of SCED produced LMPs for reasonableness - Post LMPs and other data as required by the ERCOT Nodal Transition Plan section 5.4.4 - Begin the 6 month LMP posting period as required by the ERCOT Nodal Transition Plan Market Participant Qualification Criteria: - Submit Three-Part Supply Offer - Submit COP - Submit Output Schedules into SCED - Utilize both the Graphical User Interface and/or Machine to Machine interfaces for SCED inputs ERCOT Criteria: - Provide a SCED environment for Market Participant EDS Activities - Execute SCED to create Base Points and LMPs - Verify Base Points and associated LMPs for reasonability - Post LMPs and other data available as required in the Nodal Protocols |
| When | Up to date calendar posting for EDS should soon be available in a reference document on the Nodal Transition Readiness Center site providing an activity list and calendar. |
| Participation | - Qualification step is required. - Qualification step is satisfied by demonstrating ability to submit required transactions to ERCOT as described by the EDS plan (tracked by ERCOT with a scorecard). |
| References | EDS 3 – Detailed Plan: http://nodal.ercot.com/docs/pd/irt/index.html#oth |

### Step Q6 - EDS3/Release6 - Load Frequency Control Testing

| Activity | EDS3/Release6 – Load Frequency Control (LFC) Testing |
| --- | --- |
| Who | All QSEs with Resources |
| What | Release 6 addresses the LFC testing requirements of Section 5.4.8 of the ERCOT Nodal Transition Plan (Load Frequency Control Testing). This activity will test the QSEs and associated resources ability to respond to Load Frequency Control signals produced by the nodal system. The EDS 3 team will work with the ERCOT operators and QSEs to carry out coordinated QSE-by-QSE testing. will be the initial release of the Security Constrained Economic Dispatch program. The focus of the release is to work with Participants to ensure that: - Validate completion of all communication system testing - Verify proper operations of the LFC functions - Compare nodal ACE results with zonal ACE results - Verify for each registered Reg Up and Reg Down resources, the ability to provide Regulation Control on nodal systems Market Participant Qualification Criteria: - Ability of QSE to receive and respond to the Regulation dispatch signal from ERCOT in accordance with the Resources’ Participation Factors ERCOT Criteria: - Ability to evaluate Resource response and assess performance - Compare nodal ACE with zonal ACE |
| When | Up to date calendar posting for EDS activities should soon be available in a reference document on the Nodal Transition Readiness Center site providing an activity list and calendar. |
| Participation | - Qualification step is required. - Qualification step is satisfied by demonstrating ability receive and respond to regulation dispatch in accordance with ERCOT signaling and Market Participant Participation Factors. |
| References | EDS 3 – Detailed Plan: http://nodal.ercot.com/docs/pd/irt/index.html#oth |

### Step Q6 - EDS3/Release7 - CRR Allocation and Auction Testing

| Activity | EDS3/Release7 – CRR Allocation and Auction Testing |
| --- | --- |
| Who | CRR Account Holders |
| What | Release 7 addresses Section 5.4.5 (Trial Operation of Congestion Revenue Rights Auction) of the ERCOT Nodal Transition Plan by testing the CRR Allocation and Auctions processing. The objectives of the EDS CRR Testing are to: - Demonstrate the ERCOT PCRR (Pre-assigned Congestion Revenue Rights) Allocation process - Provide Market Participants the opportunity to create test bids for CRRs on Transmission Elements - Execute Trial Auction for Monthly and Annual CRRs - Assign test PCRRs / CRRs to Account Holders for DAM and RT Operations testing of Settlement Systems Market Participant Qualification Criteria: - Upload and view monthly and annual CRR bids - Submit bilateral trades of CRRs ERCOT Criteria: - Conduct monthly and annual auctions - Issue test PCRRs and CRRs to Market Participants - Test invoicing of CRRs |
| When | Up to date calendar posting for EDS activities should soon be available in a reference document on the Nodal Transition Readiness Center site providing an activity list and calendar. |
| Participation | Qualification step is required. Qualification step is satisfied by demonstrating ability to submit required transactions to ERCOT as described by the EDS plan (tracked by ERCOT with a scorecard). |
| References | EDS 3 – Detailed Plan: http://nodal.ercot.com/docs/pd/irt/index.html#oth |

### Step Q6 - EDS4/Release8 – Real-Time Settlement and Energy Offers Testing

| Activity | EDS3/Release8 –Real-Time Settlement and Energy Offers Testing |
| --- | --- |
| Who | CRR Account Holders All QSEs |
| What | Release 8 has a focus on Settlement activities. The Settlement systems will be intergrated with the market systems and provide Real-Time Settlement Statements for the market to download and review. In addition, functionality for submitting Energy-Only Offers, also known as virtual offers, will be available for testing. Market Participant Qualification Criteria: - Download Real-Time Settlement Statements - Submit Energy-Only Offers ERCOT Criteria: - Accept and process Energy-Only Offers - Run Real-Time Settlement process and post Settlement Statements. |
| When | Up to date calendar posting for EDS activities should soon be available in a reference document on the Nodal Transition Readiness Center site providing an activity list and calendar. |
| Participation | - Qualification step is required. - Qualification step is satisfied by demonstrating ability to submit required transactions to ERCOT as described by the EDS plan (tracked by ERCOT with a scorecard). |
| References | EDS 4 – Detailed Plan (not yet available): http://nodal.ercot.com/docs/pd/irt/index.html#oth |

### Step Q6 - EDS4/Release9 - DAM, RUC, SASM, Outages, Disputes, 168Hr Test

| Activity | DAM, RUC, SASM, Outages, Disputes Testing, 168Hr Test |
| --- | --- |
| Who | CRR Account Holders All QSEs |
| What | Release 9 brings full nodal functionality together, with the culmination of releases leading into the execution the 168-hour test for ERCOT and the Market Participants. All remaining functionality will be released for testing, including: - Outage Scheduling for Resources and Transmission - All Markets systems- DAM, RUC, SASM, SCED - All EMS systems - All Settlement Statements and Invoices (CRR, DAM, RT) Market Participant Qualification Criteria: - Enter Resource and Transmission Outages into Outage Scheduler - Fully participate in markets as applicable - Download Settlement data and extracts ERCOT Criteria: - Provide Outage Scheduler interface and accept Outages from QSEs and TSPs - Ability to run all markets (SCED, DAM, RUC, SASM) - Ability to run EMS systems and maintain frequency with nodal tools - Ability to settle all markets |
| When | Up to date calendar posting for EDS activities should soon be available in a reference document on the Nodal Transition Readiness Center site providing an activity list and calendar. |
| Participation | - Qualification step is required. - Qualification step is satisfied by demonstrating ability to submit required transactions to ERCOT as described by the EDS plan (tracked by ERCOT with a scorecard). This will be the most comprehensive and closely monitored qualification testing activity. Successful participation in this 168-hour test is the key to final qualification of the Market Participant, and will result in ERCOT granting access to the ERCOT production systems to the successfully qualified Market Participants. |
| References | EDS 4 – Detailed Plan (not yet available): http://nodal.ercot.com/docs/pd/irt/index.html#oth |

## Step Q7 - Site Visit

| Activity | Site Visit |
| --- | --- |
| Who | New QSEs only |
| What | Part of protocols 16.2.1, Criteria for Qualification as a Qualified Scheduling Entity, is allowing ERCOT to perform a site visit to verify the QSE systems and communications meet the requirements of protocols and operating guides. This visit is allowed in section 16.2.1 as “Allow ERCOT, upon reasonable notice, to conduct a site visit to verify information provided by the QSE.” For existing QSEs, this is not a change in requirements for nodal support. For new QSEs, this requirement is allowed for by protocols. |
| When | As requested by ERCOT, upon reasonable notice. |
| Participation | For new QSEs, this site visit would be granted upon request form ERCOT. |
| References | Protocol section 16.2.1, Criteria for Qualification as a Qualified Scheduling Entity. |