## Sheet1
Section/Title | Comment | Assigned To
1.2 Document Relationship | NERC Regional differences document has not been approved - update upon approval | Group
2.2.3 Response to Transient Voltage Disturbance | Section reference will have to be updated after Nodal Op. Section 3 is complete | A. Boren
2.3.2.3, Additional Operational Details for Responsive Reserve Providers | (6)(d) - Feedback from ERCOT is required | Jose/Colleen
2.4, Outage Coordination | Ask Robert Matlock to look at this; possibly Ralph Poston | Jose/Colleen
2.7.4.1, Maintaining System Voltage | Reference Protocols Section 3.15, Voltage Support | ??
2.7.4.1, Maintaining System Voltage | (4) - Wayne Kemper Homework | Wayne Kemper
3.1.4, Ancillary Service Qualification and Testing Program | Compare to Section 8.1.2.2.1 | Steve Knapp
3.1.5, Resource Entities | Fill in gaps for Load Resource communication | Rick Keetch
3.1.5, Resource Entities | (8)-(10) - follow up on communication process | Wayne Kemper
3.1.5.1, Unit Capability Requirements | Get input from John Dumas/Curtis Crews on what they would like to see in Section 3.1.5.1 and 3.1.5.3 | Rick Keetch/Steve Knapp
3.1.5.1, Unit Capability Requirements | Is this section covered in Nodal? Check if enforcement of compliance template meets enforcement requirements | Vann Weldon
3.1.5.1, Unit Capability Requirements | Check that seasons are correctly defined | Group
3.1.5.3.3, Coordinated Reactive Testing | (6) and (7) - Check Section References | A. Boren
3.1.5.3.4, ERCOT Implementation | Review Compliance Requirements as they apply to NERC Reliability Standards | Vann Weldon
3.1.6, Transmission Service Providers (TSP) | (2) - Review Authorized Rep requirement in TO and Resource Operations | ??
3.1.6.2, Transmission Owner Responsibility for a Vegetation Management Program | Review TO and TSP sections and make sure requirements fit in each section and any overlap will go into a new section | Wayne Kemper
3.1.6.2.2, ERCOT Requirements for Reporting Sabotage Information | Check Protocols to see how they are referencing NERC Standards | A. Boren
3.1.7, Responsibility for Equipment Ratings | Does this meet definition of methodology of FAC-008 | Vann Weldon
4.3.1, Remedial Action Plans (RAP) | Move to Section 7 | Group
4.5, Emergency Electric Curtailment Plan (EECP) | Copy updated language from Nodal Protocols to Operating Guides once NPRR is approved | Group
5.1.7, System Modeling Information | Ask Curtis Crews to review and comment | Jose/Colleen
5.1.7, System Assessments | Table 5-1, Colleen to look at this | Colleen
6.1.2, Relay Misoperation Report (Attachment 9B) | Check with SPWG to see if this is the form they are using or if it needs to be updated | Jose
7, Disturbance Monitoring and System Protection | Ask Rick Gurley to review | Jose
7.1.2, Fault Recording Equipment | Parentheses use does not make sense - Review | Group
7.1.2.1, Triggering Requirements | Parentheses use does not make sense - Review | Group
7.1.2.2, Location Requirements | Define Switching Station | Group
7.2.2, Design and Operating Requirements for ERCOT System Facilities | guide reference is confusing - is this Operating Guide or IEEE/ANSI? | Group
7.2.2, Design and Operating Requirements for ERCOT System Facilities | (15), (16) Check Section References | A. Boren
7.2.3, Performance Analysis Requirements for ERCOT System Facilities | (2) Check Section References | A. Boren
7.2.3, Performance Analysis Requirements for ERCOT System Facilities | (4) Is this Section outdated? | Group
7.2.5.1.1, Dependability | (1) Section reference is confusing | A. Boren
7.2.5.1.1, Dependability | (5) CT is not an acronym - needs to be defined or spelled out | Group
7.2.5.1.6, Analysis of System Performance and Associated Protection Systems | (2) "System" reference - is this referring to the ERCOT System? | Group
8.2, Communications | Need to add more verbiage to make it an introduction | Group
8.3, Telemetry | (1) ICCP is not defined or an acronym - do we want to add to definitions? | Group
8.3, Telemetry | (3) Check Section references | A. Boren
8.3.3.1, Weather Zone Data | Need additional review - should this be more generically references as "critical data"? | Group