## Slide 1: Texas Nodal Market Implementation Program
Overview of Nodal Change Control

## Slide 2: Current focus: clear the NPRR backlog and synchronize projects to a common baseline
To maintain overall system integrity – for Nodal to work as a whole – each project has to be synchronized on an explicit, current, common baseline
Baseline 0 May, 2006 Protocols
Baseline 1
NPRRs approved by March 31, 2007
NPRR “Backlog”
Nodal Projects
Pending Baseline
Current Baseline
Synchronization “deficit”

## Slide 3: Change control objectives: future NPRRs as well as the backlog
To maintain overall system integrity by ensuring each project is focused on an explicit, current, common baseline
To formally authorize additional scope into the program, and its budget and schedule implications
To verify that a request is approved by the appropriate authority
To ensure implementation of each accepted change
To support the maintenance of traceability across the system (from protocols to test cases) by synchronizing all projects to one version of the protocols
Current emphasis is the backlog and advancing the current baseline - but process must handle additional NPRRs and subsequent baseline advances

## Slide 4: The proposed process is designed to handle NPRRs and Nodal change requests in tandem
TPTF
PRS 1
IC (1-4)
PRS 2
TAC
CCB
CR* Approval
Process
Y/N for
Go-Live
IA (group
changes)
Draft
NPRR
CR*
Projects
BOD
Approves
PRS to do an initial
review and provide a
recommendation of
approval
PRS to approve
time and dollars
ERCOT to provide an
initial impact categorization
and a Program position for Go-Live
Approval depends on
budget thresholds and
funding sources
The process is modified slightly to accommodate the change control objectives…
CR* - A Change Request is the Nodal
program’s mechanism for incorporating
changes to scope, timescales, cost. A change
request normally incorporates multiple items
including NPRRs, white papers, etc.
Technical Change Control
Board to work with projects
to develop and submit
change requests to the CCB
CR Approval
Periodic updates will be provided to TPTF, PRS, TAC & BOD on the status of NPRRs
NPRR Approval

## Slide 5: Key concept: handle NPRRs through periodic baseline advances, rather than individually
The focus of each baseline “generation” is discrete
May 2006 Protocols
Current Baseline
Pending Baseline
Future Baseline
Baseline advance point
Baseline 2
(TBD)
Baseline 1
(March, 2007)
Current
Post-advance Point
Baseline 0 and
Approved changes
from Baseline 1
Baseline 1
(March, 2007)
Baseline 2
(TBD)
ILLUSTRATIVE
ILLUSTRATIVE
Baseline 3
(TBD)
Current Baseline
Next Baseline
Future Baseline
Program-level architecture impact
Grouping items for efficiency
Detailed cost & schedule impact
Submit & approve Change Requests
Update requirement documents
Update use cases & test cases
Update design documents
Implement
Evaluate Essential for Go-Live
Categorize impacts (1-4)
Approve and agree next baseline scope
Impact assessment continues for new items to get ahead for the next baseline
Baseline 0
(May, 2006)

## Slide 6: Pending baseline process: turning NPRRS into Change Requests
Technical Change Control Board conduct program-level architecture assessment & produce draft “Change Requests”
Group the items for implementation synergies/efficiencies
Establish detailed project cost and schedule analysis
TCCB update schedule, budget and system architecture. Validate implementation timeframes.
Submit to Program Change Control Board (CCB) for approval
The steps … … some implications
All NPRRs to go through the Nodal PMO initially, instead of being directly forwarded to PRS for their second review
The Program will take a position on a draft NPRR whether it’s essential for Go-Live. This will be validated through the formal stakeholder process
For the backlog, category 3 & 4 will be accepted within the existing budget/contingency
For the backlog, categories 1 & 2 will have a cost and schedule impact leading to suitably packaged change requests
Going forward, categories 1, 2 & 3 will be subject to potential change requests (as designs and development will have progressed that much further)
A total of 11 “Baseline 1” Change Requests are covering all associated 63 items including NPRRs, White Papers and change requests are in preparation
Complete impact categorization of finalized items
Agree baseline scope

## Slide 7: “Baseline 1” Status: Target completion of change requests – June 6th, 2007
5/25/2007
6/1/2007
6/6/2007
The current cycle time suggests re-baselining at 90 day intervals
8 weeks from declaration of Baseline 1 scope
Technical Change Control Board conduct program-level architecture assessment & produce draft “Change Requests”
Group the items for implementation synergies/efficiencies
Establish detailed project cost and schedule analysis
Technical Change Control Board update schedule, budget and system architecture. Validate implementation timeframes.
Submit to Change Control Board for approval
Complete impact categorization of finalized items
Agree baseline scope
3/31/2007





## Slide 8: “Baseline 2” scope definition: target by June 22nd, 2007 …
Projects & Market participants to “finalize” their NPRRs or White Papers if they are to be considered for inclusion in Baseline 2
19 NPRRs
As of 5/12/2007, there are 28 items in Baseline 2…
9 IDA white papers and
other implementation and
design solutions not
impacting protocols
For inclusion of an NPRR in future pending baselines, it
must have PRS’s initial
review and recommendation
of approval (PRS 1)

## Slide 9: Proposed a resolution to TAC to limit additional scope change
The objective of the Nodal program is to design and implement the nodal market system and transition from the current zonal market to the nodal market by 12/1/2008.
The budget presented to the Board of Directors, TAC and TPTF was based on this timeline and the scope defined under the May 2006 version of the protocols (termed “Baseline 0”).
Multiple NPRRs have been approved since May 2006 and the program is currently working to incorporate them into a revised baseline (“Baseline 1”). The scope of the revised baseline includes the previous baseline plus NPRRs approved as of March 31st, 2007.
As the program continues through its delivery cycle, and the systems are built and tested, additional changes requiring additional work and rework will potentially have an exponential impact on cost and schedule.
Such changes are to be minimized. As a practical measure:
  An NPRR that is not essential for Go-Live should be deferred until after nodal goes live.
  An NPRR that addresses the correct working of the Nodal Market will be considered as essential for Go-Live.
  An NPRR that deals with adding or enhancing functionality to the existing systems will be considered not essential for Go-Live.
ERCOT will work with TPTF and PRS to determine whether a specific NPRR is not “essential for Go-Live”

## Slide 10: APPENDIX A – NPRR view

## Slide 11: Appendix A – NPRR view
NPRR # | Title, Short Description | Status (As of 5/15/2007) | Baseline | Program Position on Go-Live (E/D/N)* | Group # | Highest Impact Category | CR#
1 | Section 1, Zonal PRR Synchronization and ERCOT Staff Clarifications | Approved | Baseline1 | E | 1 | 3 | 14
2 | Section 3, Zonal PRR Synchronization and ERCOT Staff Clarifications | Approved | Baseline1 | E | 6 | 1 | 19
3 | Section 5, Zonal PRR Synchronization and ERCOT Staff Clarifications | Approved | Baseline1 | E | 1 | 3 | 14
4 | Section 8, Zonal PRR Synchronization and ERCOT Staff Clarifications | Approved | Baseline1 | E | 5 | 1 | 18
5 | Section 7 ERCOT Staff and TPTF Clarifications | Approved | Baseline1 | E | 4 | 1 | 17
6 | Section 4 ERCOT Staff Clarifications | Approved | Baseline1 | E | 6 | 1 | 19
7 | Section 9 Zonal PRR Synchronization and ERCOT Staff Clarifications | Approved | Baseline1 | E | 1 | 3 | 14
8 | PRR307 Inclusion in Nodal | Approved | Baseline1 | N | 10 | 1 | 23
9 | Section 6 PRR Synchronization and ERCOT Staff Clarifications | Approved | Baseline1 | E | 5 | 1 | 18
10 | Synchronization of PRR630 and Section 3, Management Activities for the ERCOT System | Approved | Baseline1 | E | 1 | 3 | 14
*E-Essential for Go-Live;D-Desired for Go-Live;Not Essential for Go-Live

## Slide 12: Appendix A – NPRR view
NPRR # | Title, Short Description | Status (As of 5/15/2007) | Baseline | Program Position on Go-Live (E/D/N)* | Group # | Highest Impact Category | CR#
11 | Revision to Credit Requirements | Approved | Baseline1 | E | 1 | 3 | 14
12 | CRR Granularity in CRR Auction | Approved | Baseline1 | E | 6 | 1 | 19
13 | Section 2, Zonal PRR Synchronization and ERCOT Staff Clarifications | Approved | Baseline1 | E | 1 | 3 | 14
14 | Zonal PRR Synchronization for Section 16 | Approved | Baseline1 | E | 6 | 1 | 19
15 | Zonal PRR Synchronization Section 22 Attachment H | Approved | Baseline1 | E | 1 | 3 | 14
16 | TPTF Cleanup Items for Sections 2, 3, and 16 | Approved | Baseline1 |  | 5 | 1 | 18
17 | Discontinuation of Interest Charge for Defaulting Entities at Time of Uplift | Approved | Baseline1 | E | 1 | 3 | 14
19 | Black Start Testing Requirements | Approved | Baseline1 | E | 1 | 3 | 14
22 | MIS Posting for Area Trades | Approved | Baseline1 |  | 6 | 2 | 19
23 | Correction to Formatting of Section 8.1.2.2.1 | Approved | Baseline1 | E | 1 | 3 | 14
*E-Essential for Go-Live;D-Desired for Go-Live;Not Essential for Go-Live

## Slide 13: Appendix A – NPRR view
NPRR # | Title, Short Description | Status (As of 5/15/2007) | Baseline | Program Position on Go-Live (E/D/N)* | Group # | Highest Impact Category | CR#
24 | Synchronization of PRRs 627 and 640 | Pending Language TAC | Post Baseline1 |  |  |  | 
25 | Definition of Annual Planning Model | Approved | Baseline1 | E | 1 | 3 | 14
27 | Block Offers in CRR Auction | Approved | Baseline1 | E | 1 | 1 | 14
28 | CRR Trading in Blocks Only | Approved | Baseline1 | E | 1 | 3 | 14
29 | Network Model Testing Clarification | Approved | Baseline1 | E | 11 | 1 | 24
30 | Addition to CRR Account Holder Qualification Criteria | Approved | Baseline1 | E | 1 | 3 | 14
31 | Correction of Voltage Support Bill Determinants | Approved | Baseline1 | E | 7 | 3 | 20
32 | Correction of Black Start Bill Determinants | Approved | Baseline1 | E | 7 | 3 | 20
33 | Settlement of CRRs When DAM Does Not Execute | Approved | Baseline1 | E | 8 | 2 | 21
34 | Conforming Section 10 to Nodal Format | Approved | Baseline1 | E | 8 | 2 | 21
*E-Essential for Go-Live;D-Desired for Go-Live;Not Essential for Go-Live

## Slide 14: Appendix A – NPRR view
NPRR # | Title, Short Description | Status (As of 5/15/2007) | Baseline | Program Position on Go-Live (E/D/N)* | Group # | Highest Impact Category | CR#
35 | Nodal Protocol Clarifications Required For Net Metering Provisions | "Pending IA PRS" | Baseline1 | E | 2 | 1 | 15
36 | Market Operations Test Environment in Nodal | Pending Language PRS | Post Baseline1 |  | 6 | 1 | 19
37 | Conforming Section 13 to Nodal Format and Changing Frequency of Transmission Loss Base Case Calculations. | Pending IA PRS | Post Baseline1 |  | 1 | 1 | 14
38 | Synchronization of PRR624 | Approved | Baseline1 |  | 1 | 3 | 14
39 | Ancillary Service Offers for the Supplementary Ancillary Service Market | "Pending IA PRS" | Baseline1 |  | 6 | 1 | 19
40 | Emergency Electric Curtailment Plan (EECP) Event Realignment (PRR682) | Pending Language PRS | Post Baseline1 |  | 6 | 1 | 19
41 | Corrections to Section 4, Day-Ahead Operations | "Pending IA PRS" | Baseline1 | E | 2 | 1 | 15
42 | "Corrections to Section 5, Transmission Security Analysis and RUC" | "Pending IA PRS" | Baseline1 | E | 9 | 2 | 22
43 | "Corrections to Section 7, Congestion Revenue Rights" | "Pending IA PRS" | Baseline1 | E | 1 | 3 | 14
44 | Corrections to Section 6, Adjustment Period and Real-Time Operations | "Pending IA PRS" | Baseline1 | E | 7 | 2 | 20
*E-Essential for Go-Live;D-Desired for Go-Live;Not Essential for Go-Live

## Slide 15: Appendix A – NPRR view
NPRR # | Title, Short Description | Status (As of 5/15/2007) | Baseline | Program Position on Go-Live (E/D/N)* | Group # | Highest Impact Category | CR#
45 | Wind Power Forecasting | Pending Language TPTF | Post Baseline1 |  | 1 | 3 | 14
46 | Real-Time ICCP Communications Only | Pending BoD Approval | Baseline1 |  | 1 | 3 | 14
47 | Credit Monitoring – ERCOT Staff Clarifications (a.k.a Draft Comm Ops_NPRR_ CMM) | "Pending IA PRS" | Baseline1 | E | 2 | 1 | 15
48 | Revised Wording of Opportunity Outages for Transmission Facilities (Definition of Outage) | "Pending IA PRS" | Baseline1 |  | 1 | 3 | 14
49 | Generation Subsystem Changes to Incorporate Approved Whitepapers | "Pending IA PRS" | Baseline1 | E | 3 | 1 | 16
50 | Clarifications for HSL Values for WGRs and WGR Values to be Used in the RUC Capacity Short Calculation | Pending Language PRS | Baseline1 |  | 1 | 3 | 14
51 | Removal of the Pseudo Resource Requirement in the Real Time Security Constrained Economic Dispatch (SCED) Process | "Pending IA PRS" | Baseline1 |  | 6 | 1 | 19
52 | Settlement for Non-Modeled Generators | "Pending IA PRS" | Baseline1 |  | 6 | 1 | 19
53 | Creation of a New Trading Hub at Venus Switching Station | Pending Language TPTF | Post Baseline1 |  | 5 | 1 | 18
*E-Essential for Go-Live;D-Desired for Go-Live;Not Essential for Go-Live

## Slide 16: Appendix A – NPRR view
NPRR # | Title, Short Description | Status (As of 5/15/2007) | Baseline | Program Position on Go-Live (E/D/N)* | Group # | Highest Impact Category | CR#
54 | Update of Nodal Protocols to Comply with NERC Name Change – Companion to PRR711 | Pending Approval BoD | Post Baseline1 |  |  | 3 | 54
55 | Correction of Voltage Support QSE Total Bill Determinants | Pending IA PRS | Post Baseline1 | E |  |  | 55
57 | Posting Requirements Pursuant PUC Subst. R. 25.505 | Pending IA PRS | Post Baseline1 |  |  |  | 57
58 | Clarification of Standard Form Market Participant Agreement | Pending IA PRS | Post Baseline1 | E |  | 3 | 58
59 | Reconfiguring the Annual CRR Auction | Pending Language PRS | Post Baseline1 |  |  |  | 59
60 | Draft Hub Clarification | Pending Language PRS | Post Baseline1 |  |  |  | 60
61 | Scarcity Pricing Mechanism (Companion to PRR709) | Pending Language PRS | Post Baseline1 |  |  |  | 61
54 | Update of Nodal Protocols to Comply with NERC Name Change – Companion to PRR711 | Pending Approval BoD | Post Baseline1 |  |  | 3 | 54
55 | Correction of Voltage Support QSE Total Bill Determinants | Pending IA PRS | Post Baseline1 |  |  |  | 55
*E-Essential for Go-Live;D-Desired for Go-Live;Not Essential for Go-Live

## Slide 17: Appendix A – NPRR view
NPRR # | Title, Short Description | Status (As of 5/15/2007) | Baseline | Program Position on Go-Live (E/D/N)* | Group # | Highest Impact Category | CR#
TBD | Trade Validation by Matching Identical Trade Submissions | Drafted | Baseline1 |  | 7 | 1 | 20
TBD | Calculation of RRS Deployment by SCED (resulting from TPTF Approved White Paper 5) | TBD | Post Baseline1 |  |  |  | 
TBD | Section 5: Settlements Clean-up NPRR (Decommitment) | DRAFTED | Post Baseline1 |  |  |  | 
TBD | Telemetered Resource Status | DRAFTED | Post Baseline1 |  |  |  | 
TBD | Electrical Bus Clarification | Pending Language TPTF | Post Baseline1 |  |  |  | 
TBD | Constraint Competitiveness Test | TPTF Approved | Post Baseline1 |  |  |  | 
TBD | Modeling of Generic Transmission Constraints | Pending Language TPTF | Post Baseline1 |  |  |  | 
TBD | External Transmission Networks | Pending Language TPTF | Post Baseline1 |  |  |  | 
TBD | Corrections to Section 9 – Settlements Clean-up NPRR | Market Decision Pending | Post Baseline1 | E |  |  | 
*E-Essential for Go-Live;D-Desired for Go-Live;Not Essential for Go-Live

## Slide 18: Appendix B – Baseline 1 view

## Slide 19
Item | Description
NPRR 1 | Section 1, Zonal PRR Synchronization and ERCOT Staff Clarifications
NPRR 3 | Section 5, Zonal PRR Synchronization and ERCOT Staff Clarifications
NPRR 7 | Section 9 Zonal PRR Synchronization and ERCOT Staff Clarifications
NPRR 10 | Synchronization of PRR630 and Section 3, Management Activities for the ERCOT System
NPRR 11 | Revision to Credit Requirements
NPRR 13 | Section 2, Zonal PRR Synchronization and ERCOT Staff Clarifications
NPRR 15 | Zonal PRR Synchronization Section 22 Attachment H
NPRR 17 | Discontinuation of Interest Charge for Defaulting Entities at Time of Uplift
NPRR 19 | Black Start Testing Requirements
NPRR 23 | Correction to Formatting of Section 8.1.2.2.1
NPRR 25 | Definition of Annual Planning Model
NPRR 28 | CRR Trading in Blocks Only
NPRR 30 | Addition to CRR Account Holder Qualification Criteria
These items have minimal or no impact across all projects. These have already been approved by CCB and Projects have already started implementing these changes…
Group 1
Item | Description
NPRR 38 | Synchronization of PRR624
NPRR 43 | "Corrections to Section 7, Congestion Revenue Rights"
NPRR 46 | Real-Time ICCP Communications Only
NPRR 48 | Revised Wording of Opportunity Outages for Transmission Facilities (Definition of Outage)
NPRR 50 | Clarifications for HSL Values for WGRs and WGR Values to be Used in the RUC Capacity Short Calculation
Comment - Req | Responses - Only if not covered by (1) items on IDA Punch List, (2) White Papers or (3) NPRRs
WPEMS3 | Coincidental Deployment of Up and Down Regulation
WPEMS4 | Emergency Basepoints Calculation and Deployment
WPEMS6 | HDL And LDL During Start up and AS Recall
NPRR 27** | Block Offers in CRR Auction
WPIDA 039* | CRR Derating
Note - *EIP category 2 Impact; ** CRR category 2 impact

## Slide 20: This group of items were bucketed together based on category 1 impacts across multiple projects as well as a correlation between individual items…
Item | Description | Impact category 1 | Impact category 2
NPRR 35 | Nodal Protocol Clarifications Required For Net Metering Provisions | MMS, COMS | NMMS
CR 10 | Business Process for SPS/RAP in Nodal | MMS, NMMS | CRR, EIP
IDA WP 002 | Time Standards and DST | CRR | EIP, COMS
IDA WP 004 | Power Flow Consistency Requirements | EMS, MMS | NMMS
IDA WP 007 | Load Rollover | MMS, COMS, CRR | NMMS
IDA WP 008 | State Estimator Rollover Maintenance | MOTE | 
IDA WP 009 | SPS and RAP Modeling | NMMS | CRR
IDA WP 013 | Seasonal/Temperature/Hydrogen Pressure based Reactive Capacity Curves and MW Capability Curve | MMS | MOTE, EIP
IDA WP 031 | Behind the Meter Facilities and Non-Utility Transmission Equipments | EMS, MMS, NMMS | 
NPRR 47 | Credit Monitoring – ERCOT Staff Clarifications (a.k.a Draft Comm Ops_NPRR_ CMM) | MMS, CRR | EIP
NPRR 41 | Corrections to Section 4, Day-Ahead Operations | MMS | EIP
CR 57 | "Move Resource Parameters from Registration to MMS" | MMS | COMS, EIP
Group 2
Item | Description | Impact category 1 | Impact category 2
NPRR 49 | Generation Subsystem Changes to Incorporate Approved Whitepapers | EMS | MMS
CR 67 | Non-Spin Deployment (resulting from TAC approved process) | MMS, COMS | 
CR 68 | Calculation of RRS Deployment by SCED (resulting from TPTF Approved White Paper 5) | MMS | 
WPEMS1 | Ancillary Service Schedules and Deployment Telemetry | EMS | 
WPEMS2 | Base Point above HASL Flags | EMS | 
WPEMS7 | Non-Spin Deployment Notification and Availability | EMS, MMS | EIP
WPEMS8 | SCED Base Point Dispatch | EMS | EIP, MIS
Group 3

## Slide 21: This group of items were bucketed together based on impacts across 2 or more projects as well as a correlation between individual items…
Item | Description | Impact category 1 | Impact category 2
NPRR 5 | Section 7 ERCOT Staff and TPTF Clarifications | MMS | CRR
Item | Description | Impact category 1 | Impact category 2
NPRR 4 | Section 8, Zonal PRR Synchronization and ERCOT Staff Clarifications | MMS | EMS
NPRR 9 | Section 6 PRR Synchronization and ERCOT Staff Clarifications | MMS | EMS, MIS
NPRR16 | TPTF Cleanup Items for Sections 2, 3, and 16 | MMS | EMS
CR 55 | Synchronization of PRR 698, Remove Default QSE Provisions | MMS | MIS
Group 4
Group 5

## Slide 22: This bucket was put together by items belonging to individual systems…
Item | Description | Impact category 1 | Impact category 2
NPRR 2 | Section 3, Zonal PRR Synchronization and ERCOT Staff Clarifications | MMS | 
NPRR 6 | Section 4 ERCOT Staff Clarifications | MMS | 
NPRR 12 | CRR Granularity in CRR Auction | MMS | 
NPRR 14 | Zonal PRR Synchronization for Section 16 | MMS | 
NPRR 22 | MIS Posting for Area Trades |  | MMS
NPRR 39 | Ancillary Service Offers for the Supplementary Ancillary Service Market | MMS | 
NPRR 51 | Removal of the Pseudo Resource Requirement in the Real Time Security Constrained Economic Dispatch (SCED) Process | MMS | 
NPRR 52 | Settlement for Non-Modeled Generators | MMS | 
Group 6
Item | Description | Impact category 1 | Impact category 2
NPRR 44 | Corrections to Section 6, Adjustment Period and Real-Time Operations |  | EIP
NPRR TBD (CR 64) | Trade Validation by Matching Identical Trade Submissions | EIP | 
NPRR 31 | Correction of Voltage Support Bill Determinants |  | 
NPRR 32 | Correction of Black Start Bill Determinants |  | 
Group 7
Item | Description | Impact category 1 | Impact category 2
NPRR 33 | Settlement of CRRs When DAM Does Not Execute |  | COMS, MMS
NPRR 34 | Correction to Nodal Section 10 |  | MIS
Item | Description | Impact category 1 | Impact category 2
NPRR 42 | "Corrections to Section 5, Transmission Security Analysis and RUC" |  | NMMS, MMS
Group 8
Group 9

## Slide 23: This bucket was based on items that were identified as to be kept separate…
Group 10
Item | Description | Impact category 1 | Impact category 2
NPRR 008 | PRR307 Inclusion in Nodal | EMS, MMS & NMMS | EIP & IDA
Group 11
Item | Description | Impact category 1 | Impact category 2
NPRR 029 | Network Model Testing Clarification | MOTE |