Texas Nodal Market

Readiness Metric Inventory

Version 0.14

May 9, 2007

Table of Contents

Introduction	3

Market Participant Metrics	5

MP1 - MP Engagement	5

MP2 - Connectivity to Test Environment	6

MP3 - Upload SCED Offers to EDS 	6

MP4 - MP Test Digital Certificates Obtained	7

MP5 - Point to Point Telemetry Test	7

MP6 - MP Telemetry/ICCP System Availability	9

MP7 - MP Use of MIS	9

MP8 - MP AP & RTM Transactions	11

MP9 - MP DAM Transactions	11

MP10 - Mapping of Resources to Resource Nodes and Resources to Revenue Quality Meters is Complete	13

MP11 - MP Registration Activities	13

MP12 - MP Completes EDS-3 Related Training	14

MP13 - MP Completes EDS-4 Related Training	15

MP14 - MP EDS-2 Trials Participation	16

MP15 - MP EDS-3 Trials Participation	16

MP16 - MP EDS-4 Trials Participation	17

MP17 - MP Qualification Activities	17

Commercial Operations Metrics	18

CO1 - Settle Market for 7 Days and provide appropriate extracts	18

CO2 - Verify Dispute Process of 168 Hour Test	18

CO3 - Verify DAM Settlement Statements	20

CO4 - Zonal/Nodal Coordinated Settlement Operations	20

CO5 - Verify RTM Settlement Statements	21

CO6 - Verify RTM Settlement Invoices	22

CO7 - Verify DAM Invoices	23

CO8 - Verify CRR Auction Invoices	23

CO9 - Verify Financial Transfer and Processing	24

CO10 - Verify Credit Calculations	24

Congestion Revenue Rights Metrics	26

CRR1 - Develop CRR Test Plan	26

CRR2 - Develop TCR to CRR Transition Plan	26

CRR3 - Trial Operation of Monthly CRR Auction	27

CRR4 - Trial Operation of Annual CRR Auction during Trials	27

CRR5 - Execute & Settle Annual CRR Market during Trials	28

ERCOT Internal Metrics	29

E1 - ERCOT Staff Completes Training	29

E2 - Verify ERCOT Performance Monitoring Test Plan	29

E3 - Validate Telemetry/SE EDW/MIS Access & Data Accuracy	30

E4 - Price Protection Mechanisms	30

E5 - Nodal SAS 70 Preparedness	31

E6 - Develop Nodal Operating Guides	31

E7 - Validate EDW WEMM Access & Accuracy	32

E8 - ERCOT Staffed for Texas Nodal Operations	32

E9 - Develop TN Procedures	33

E10 - Validate EDW Commercial Systems Access & Accuracy	33

E11 - Validate EDW Compliance Data Access	34

E12 - MIS Compliance Test	34

E13 - Standard Form Agreements Executed	35

E14 - Verify QSE Performance Monitoring Test Plan	35

E15 - Verify TSP Performance Monitoring Test Plan	36

Energy Management Operations Metrics	37

EMO1 - Network Security Analysis & Transmission Constraint Management	37

EMO2 - Verify Voltage Support Functionality	38

EMO3 - Verify Outage Evaluation System Functionality	39

EMO4 - Run 7 Day Stability Test	39

EMO5 - Verify ACE Performance	40

EMO6 - QSE Response to Dispatch	40

EMO7 - Verify Load Forecast Accuracy	41

EMO8 - Conduct EECP Test	41

EMO9 - Validate Zonal and Nodal Common Constraints	42

Network Model Management Metrics	43

N1 - ERCOT Telemetry Alarm Processing	43

N2 - ERCOT Telemetry/ICCP System Failover	43

N3 - Validate SE Performance and Accuracy	44

Market Operations Metric	45

MO1 - Operate DA Market for 7 Days	45

MO2 - Operate 7 Day market with RUC	46

MO3 - Verify Supplemental Ancillary Services Market (SASM)	46

MO4 - Verify Base Point Generation	47

MO5 - Generate LMPs for 6 months	47

MO6 - Verify DAM Ancillary Services	48

Contingency Metrics	49

C1 - Contingency Plan for Weekly, Daily and Hourly RUC Failure	49

C2 - Contingency Plan for DAM / LMP Failure	49

C3 - Contingency Plan for ICCP Data Failure	50

C4 - Contingency Plan for SCED Failure	50

C5 - Contingency Plans for Key Settlement and Financial Transfer Processes	51

C6 - Develop Plan for SE Failure	51

C7 - Contingency Plan for a Backup Facility	52

C8 - Contingency Plan for Portal/API Failure	52

C9 - Contingency Plan for Site Unavailability	53

C10 - Verify Single Point of Failure Recovery EMS/MMS/NMMS/CRR	53

IMM Metrics	54

IMM1 - Market Monitor Systems Capability	54

Overall Readiness Metrics	55

R1 - Nodal Readiness Declaration	55

R2 - Develop Texas Nodal Market Launch Plan	55

General Comments:

- Better coordiantion between this document and the EDS Handbooks that describe the EDS test sequences is required.  For example, with regard to the Market Participant Section – TXU recommends that the MP Metrics be grouped by early delivery system (i.e. EDS 1, 2, 3 and 4), where applicable, leaving those that apply across all of the EDS or are strictly contingent on market open as a final category.

- When grouping within the EDS test sequence, the metric should be specific to the EDS test handbook test functions that are designated for inclsion in the EDS releases.  Criteria should be based on: the population of Market Particpants that are affected, the number of MP actually particpating, and the number that have successfully completed the testing (i.e. the idea here is that all participating MP have achieved the requested performance by the end date of the test).  The function of the readiness project is to report these numbers - strict pass/fail percentages are not required for the MP metrics.  Value judgements regarding the each metric by ERCOT, TPTF, TAC and the Board (as required by the Transition Plan ) are sufficient.  Perhaps a check-off box for each entity making the value judgement is a good approach.  These same comment applies, as appropriate, to the other ot general category of MP metrics.

- Reporting Data Sources should be expanded to include the responsible ERCOT group that will make any determination (i.e. the EDS Test Team, ERCOT Compliance, etc.).

- The only time the term Market Particpant should be used in the name of a criteria is when the readiness criteria applies to all market particpants.  Otherwise, the name should explicitly reference the target MP.  For example, it may be appropriate to use MP in the name of MP1 but not in MP3 which is specific to QSEs with Resources.  This is a general comment that should be applied throughout the document.  TXU’s suggested changes in this regard are not meant to be all inclusive but, rather are examples.

- Target Completion dates need clarification – if you continue to use the milestone reference +/- x days, please also include a reference date xx/xx/xx based on the current project schedule.

- The following reflects detailed markups in the MP section of the document.  The genral comments identified above are meant to apply to all sections of the document and the lack of detailed comment does not represent the acceptability of the presentation or acceptability of the metric.  It mey be useful to have workshops that envolve TPTF and the PMO office before going final with this document.  As a first priority, the project We should at least finalize the metrics that relate to EDS 1 and 2.  The remaining metrics can follow later.

- Introduction

The Readiness Metric Inventory is a detailed report of all readiness metrics.  The following table outlines the information provided per metric.

Metric Number – Metric Name

| Reported By: Indicates if the metric is discoverable by ERCOT, Market Participants, WEMM or any combination thereof. |  |  | EDS: Indicates the related Early Delivery System, if applicable. |
| --- | --- | --- | --- |
| Target Completion: Indicates the time period that the metric result will be published. |  |  |  |
| Metric Description: Provides a description of the metric. |  |  |  |
| Background: Indicates the intent of the metric. |  |  |  |
| Criteria: Outlines the criteria used to determine if the metric has been successfully completed. Provides a concrete measurement standard to evaluate the metric against |  |  |  |
| Reporting Data Sources: Indicates the source of the data to be used when evaluating the measurement standard. |  |  |  |
| References | TP: Cross reference to the Transition Plan | TNP: Cross reference to the Texas Nodal Protocols |  |

The Metric Map is a time based graphical representation of the Metrics.

Sample Metric Map

# Market Participant Metrics

### MP1 - MP Engagement

| Reported By: MP & ERCOT |  |  | EDS: Registration |
| --- | --- | --- | --- |
| Target Completion: Periodic: June 1, TBD, TBD |  |  |  |
| Metric Description: MP are actively participating in Nodal preparation to include the assignment of an Accountable Executive, a Program Manager,the allocation of a budget, Program Charter and have indicated an intent to participate in the Nodal Market. |  |  |  |
| Background: The intent of this metric is to ensure that Market Participants are engaged in Nodal preparations. |  |  |  |
| Criteria: The Readiness Team will review self reporting from each Market Participant indicating their level of engagement in Nodal preparation, mobilization and delivery. Readiness will be achieved when MP Accountable Executives have submitted Completion Review Documents outlining their status related to defined activities. Target Preparation – AE Response Accountable Exec Nominated Project Manager Assigned Project Budget Allocated Target Mobilization Response Project Staffed and mobilized to meet the EDS Testing Resquriements Training Plan completed Training Budget allocated Testing Plan completed Business Impact Assessment Completed Aggregation - % MP >= 95% The target items deleted are internal business processes for the market particpants and are confidential information. There is no need for ERCOT to track internal MP Business Processes. ERCOT’s scope of readiness monitoring extends only to its interfaces with MP for commmunications and inforamtion that MP are requried to provide to ERCOT in accordance with approved protocols. |  |  |  |
| Reporting Data Sources: MP Self Reported |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### MP2 – QSE with Resources Connectivity to ERCOT

| Reported By: QSE with Resources & ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: 6-month LMP posting major milestone less 45 days |  |  |  |
| Metric Description: QSEs with resources have confirmed their ability to connect to the MIS and/or an External Web Service in the early Early Delivery System 1, 2 and 3 environments. |  |  |  |
| Background: The intent of this metric is to ensure that QSEs with Resources can successfully connect to ERCOT. |  |  |  |
| Criteria: The Readiness Team will review documentation providing connectivity statistics by Market Participant. Readiness will be met when the QSE successfully submits a transaction (at least one? At least one of each of a list of transaction types?) that is logged in the Enterprise Integration Framework (EIF) transaction database as successfully passing the proxy server. EIF entry per MP >=1 Connectivity is too broad a criterion. Connectivity involves links over ICCP, the MIS Portal and the external Web Service API. All QSEs, with or without physical resources, CRR Account Holders, and TSPs may use any or all of the connectivity links identified above. If you desire to split all of the connectivity into individual metrics, then the metric names need to reflect the connectivity being tested. |  |  |  |
| Reporting Data Sources: EIF log table entry in EDS |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### MP3 – QSE with Resources Upload of SCED Offers to ERCOT

| Reported By: QSE with Resources & ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: 6-month LMP posting major milestone less 45 days see genral note 1 |  |  |  |
| Metric Description: QSEs with Resources shall demonstrate their ability to successfully submit energy offer curves within a three part offer context to the MIS and/or an External Web Service in the Early Delivery System (EDS) environment. |  |  |  |
| Background: The intent of this metric is to ensure that QSEs with Resources can successfully submit a 3-part offer (output schedule?) to the ERCOT. |  |  |  |
| Criteria: The Readiness Team will review documentation providing transaction statistics by Market Participant. Readiness will be met when the MP successfully submits a request that is logged in the Enterprise Integration Framework (EIF) transaction database. (same comments as for MP2 Criteria) EIF entry with transaction status of Passed per MP >=1 |  |  |  |
| Reporting Data Sources: EIF log table entry in EDS |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### MP4 - QSE Test Digital Certificates Obtained

| Reported By: QSE & ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: 6-month LMP posting major milestone less 60 days – This completion date seems late – will test digital certificates be needed earlier in the EDS 3 test sequence? |  |  |  |
| Metric Description: MPs have submitted a request and a Nodal Testing environment digital certificate has been mailed to the MP. |  |  |  |
| Background: The intent of this metric is to ensure that Market Participants have digital certificates for the Nodal Testing environment {What about the production environment?} |  |  |  |
| Criteria: Readiness Team will review documentation reporting upon the issuance of digital certificates to Market Participants. Readiness will be met when a Nodal test environment digital certificate has been mailed to a registered / qualified MP. Which ERCOT organization is responsible for this activity and is there a concurrent ERCOT readiness criterion? Nodal Digital Certificate Mailed to MPs |  |  |  |
| Reporting Data Sources: ERCOT LRAA / email confirmation from MP to ERCOT indicating receipt of the certificate. |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### MP5 – ICCP Point to Point Telemetry Test

| Reported By: TSP and QSE & ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: EDS 1 - Release 2 Complete plus 14 days |  |  |  |
| Metric Description: ERCOT shall coordinate a test with TSPs and QSEs to verify that the equipment point mapping, value, and status are correctly transmitted within an acceptable scan rate. |  |  |  |
| Background: The intent of this metric is to ensure that TSP, QSE and ERCOT telemetry ICCP representations are in synch with one another. |  |  |  |
| Criteria: The Readiness Team will review documentation ( what documentation and whose documentation?) that verifies the accuracy of telemetry points mapping, values and status within an acceptable scan rate. Readiness will be achieved when TSPs, QSEs and ERCOT have mapped all required points to meet Nodal Protocols, Point to Point Verification has occurred, and all Telemetry issues have been documented and communicated to MPs, when ERCOT has ICCP database under change control and service requests needed to resolve ICCP issues have been submitted. See general comment 2. |  |  |  |
| Reporting Data Sources: ICCP Database / Network Operations Model |  |  |  |
| References | TP: 5.4.1 (2)(a) | TNP: 3.10.7, 6.5.7.6.1(8) & 8.1.2.2(6)(b) |  |

### MP6 – QSE and TSP Telemetry/ICCP System Availability

| Reported By: QSE and TSP & ERCOT |  |  | EDS: 1,2 |
| --- | --- | --- | --- |
| Target Completion: EDS 2 – Release 3 plus 14 days |  |  |  |
| Metric Description: Verify that all MP telemetry availability criteria are met. |  |  |  |
| Background: The intent of this metric is to ensure that MP telemetry systems are stable in a redundant state and meet TAC approved telemetry data standards. |  |  |  |
| Criteria: The Readiness Team will verify that telemetry failover thresholds and data availability standards are met by MPs. Readiness will be achieved when the MPs have passed a simulated failover test and proven data availability. What do these mean? Also see general comment 2. |  |  |  |
| Reporting Data Sources: ERCOT ICCP EMS Logs / PI Historian |  |  |  |
| References | TP: 5.4.1 (2)(k) | TNP: 3.10.7.4, 6.4.5, 6.5.5, 8.1.2 |  |

### MP7 - MP Use of MIS

| Reported By: MP & ERCOT |  |  | EDS: 3,4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 9 Complete |  |  |  |
| Metric Description: This metric will measure Market Participant hits to the Nodal MIS of specified functions as part of the QSE qualification activities, limited to MIS Secure Area and MIS Certified Area.{This seems pointless – MIS comes in two flavors, it can be used to flow information to ERCOT (i.e. 3-part offers) and to retrive information from ERCOT (i.e. LMPs ). The EDS test sequences should validate each of these functionalities. QSE use of the MIS portlets to provide information to ERCOT should be validated in each EDS test sequence. On the other hand, ERCOT can validate that the MIS portlets include all of the inforamtion described in the MIS spec. It is up to the MP to assure its own ability to retrive information from MIS. No rediness criteria for inforamation retrival by MP is necessary.} |  |  |  |
| Background: It is the intent of this metric to ensure that an adequate volume of transactions has passed through the MIS on through to the MMS to adequately represent market conditions as confirmation of unit testing. If this is desired then a specific test should be accomplished by ERCOT to stress the volumetric capacity of the MIS and associated broadband communications channels to meet the MIS specification for market information submission and retrival. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that an adequate number of market participants have sent and received information through the MIS during EDS activities. Readiness will be met when an adequate number of transactions occurs. T In other words you want at least 75% of the MPs to each submit 100 transactions? In what time period? This criterion needs better definition. Also see general comment 2. |  |  |  |
| Reporting Data Sources: MOTE Extract of volumes by MP |  |  |  |
| References | TP: 5.4.4 & 5.4.7 | TNP: 4.4.7, 9.1.3, 9.2.7 |  |

### MP8 - QSE AP & RTM Transactions

| Reported By: QSEs & ERCOT |  |  | EDS: 3,4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release – 24*7 Operations |  |  |  |
| Metric Description: ERCOT shall verify the ability of QSE to send transactions associated with the Adjustment Period (AP) and Real Time Market (RTM). Note in the AP and Real time QSEs will exchange data with ERCOt via ICCP and the messenging system which presumably will be accomplished by ICCP and a web service. Is this criteria addressing both ICCP and the web service? |  |  |  |
| Background: The intent of this metric is to ensure that QSEs have the ability to participate in the real time market. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that market participants can and have successfully sent test real time transactions. Readiness will be met when ERCOT has observed Market Participants successfully sending test real time transactions. MP Transactions Sent = MP Transactions Received at ERCOT What does this criterion mean? In each of the EDSD test sequences there needs to be a milestone that address this criteria. This milestone should be sufficiently far into the test sequence such that errors that occur early in the test sequence are identified, corrected and retested. Is the successful completion of the test sequence the culminating event that determines acceptance? We believe that all QSEs who are to do business in the nodal market must agree to their capability to perform. |  |  |  |
| Reporting Data Sources: MMS Data Extract |  |  |  |
| References | TP: 5.4.4 & 5.4.7 | TNP: 3.9, 4.3(1), 5.4, 6.4.6 |  |

### MP9 - QSE DAM Transactions

| Reported By: QSE & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 9 – 24*7 Operations |  |  |  |
| Metric Description: ERCOT shall verify the ability of QSE to submit transactions associated with the Day Ahead Market. Is this a sufficient description? What is if interest may be that QSEs are capable of submitting all information requried by the Nodal Protocols that is necessary for the successful functioning of DAM optimization engine. Will the EDS test sequence demonstrate this on a QSE by QSE basis? |  |  |  |
| Background: The intent of this metric is to ensure that QSEs have the ability to participate in the Day Ahead Market. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that the market participants can and have successfully sent test DA Transactions. Readiness will be met when ERCOT has observed Market Participants successfully sending test DA transactions. MP Transactions Sent = MP Transactions Received at ERCOT See comment under Criteria in MP8 above. |  |  |  |
| Reporting Data Sources: MMS Data Extract |  |  |  |
| References | TP: 5.4.6 (1) | TNP: 4.3, 4.4, 4.5 |  |

### MP10 - Mapping of Resources to Resource Nodes and Resources to Revenue Quality Meters is Complete

| Reported By: MP & ERCOT This is an ERCOT driven activity |  |  | EDS: Registration |
| --- | --- | --- | --- |
| Target Completion: Start Go Live Activities less 120 days |  |  |  |
| Metric Description: ERCOT shall ensure that all participating resources in the TN Market have completed their mapping of Resources to Resource Nodes and Resources to Revenue Quality Meters. |  |  |  |
| Background: It is the intent of this metric to ensure that the settlement of resources involved in a net metering configuration can be executed as specified by the Nodal Protocols. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that all participating resources in the TN Market have completed their mapping of Resources to Resource Nodes and Resources to Revenue Quality Meters. Readiness will be achieved when each resource has either mapped their Resources or have accepted the existing default configuration. Resources to Resource Node Mapping = 100% Resources to Revenue Quality Meters Mapping = 100% |  |  |  |
| Reporting Data Sources: Extract from Registration |  |  |  |
| References | TP: N/A | TNP: 16.2.3.2(2) |  |

### MP11 - MP Registration Activities

| Reported By: MP & ERCOT |  |  | EDS: Registration |
| --- | --- | --- | --- |
| Target Completion: EDS 3 - Registration EDS Trial Preparation Milestone plus 14 days |  |  |  |
| Metric Description: This metric shall measure whether Market Participants have performed the tasks outlined in the Registration & Qualification Guide . |  |  |  |
| Background: The intent of this metric is that ERCOT has all registration related data for all market participants intending to participate in the Nodal Market on record. |  |  |  |
| Criteria: The Readiness Team will review data provided by the Registration and Qualification Coordinator tracking the ERCOT/MP registration activities. MP Readiness will be achieved when the Registration checklist is completed by Client Services and the market participant Accountable Executive and Authorized Representative are notified by ERCOT via email. MP Registration Checklists Completed = Number of MPs Intending to Participate in Nodal Market |  |  |  |
| Reporting Data Sources: Registration Checklists |  |  |  |
| References | TP: N/A | TNP: 16.2 thru 16.8 & 3.7.1 |  |

### MP12 - MP Completes EDS-3 Related Training

| Reported By: ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: First - EDS 3 - 6 Month LMP Posting Major Milestone less 30 days Second - Market Open less 30 Days |  |  |  |
| Metric Description: Market Participants complete the applicable training modules associated with EDS-3. |  |  |  |
| Background: The intent of this metric is to ensure that Market Participants participating in EDS-3 and market open have adequate knowledge of the Nodal Market to participate . |  |  |  |
| Criteria: ERCOT Training will dashboard MP training progress against the commitments provided by each Accountable Executive. Progress will be reported to the Accountable Executive and the readiness evaluators (TPTF, TAC, and the ERCOT Board). Metric Completion Document Completed and Signed Off by Accountable Executive in accordance with the Market Participant Training Readiness Document |
| Reporting Data Sources: Accountable Executive Metric Signoff Document /Training Readiness Document |  |  |  |
| References | TP: 6.1(f) | TNP: N/A |  |

### MP13 - MP Completes EDS-4 Related Training

| Reported By: MP & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: First - EDS 4 - Full Nodal Functionality 24*7 Operations less 20 days Second - Market Open less 30 Days |  |  |  |
| Metric Description: Market Participants complete the applicable training modules associated with EDS-4. |  |  |  |
| Background: The intent of this metric is to ensure that Market Participants participating in EDS-4 and market open have adequate knowledge of the Nodal Market to participate . |  |  |  |
| Criteria: : Same comment as for MP-12 above Metric Completion Document Completed and Signed Off by Accountable Executive in accordance with the Market Participant Training Readiness Document |
| Reporting Data Sources: Accountable Executive Metric Signoff Document / Training Readiness Document |  |  |  |
| References | TP: 6.1(f) | TNP: N/A |  |

### MP14 - MP EDS-2 Trials Participation

| Reported By: MP & ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: EDS 2 – Start of Release 4 plus 14 days |  |  |  |
| Metric Description: This metric evaluates the level of TSP and QSE market participant participation in the EDS 2 Trial. |  |  |  |
| Background: The intent of this metric is to ensure that Market Participants have the ability to access telemetry and State Estimator performance reports and are actively participating in the NOMCR process. |  |  |  |
| Criteria: The Readiness Team will review documentation that an adequate number of MPs by market segment have reviewed performance reports on MIS and confirmed ability to access those reports and submitted modifications through the NOMCR process See general comment 2 |  |  |  |
| Reporting Data Sources: EDS 2 Trials Log |  |  |  |
| References | TP: 5.4.1 | TNP: 3.10.8, 3.3.2.1, 3.10.7 |  |

### MP15 - MP EDS-3 Trials Participation

| Reported By: MP & ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: EDS 3 Trials Start plus 14 days |  |  |  |
| Metric Description: This metric evaluates the level of QSE and CRR market participant participation in the EDS 3 Trial. |  |  |  |
| Background: The intent of this metric is to ensure that SCED, LFC and CRR are functional at the market level. |  |  |  |
| Criteria: The Readiness Team will review documentation that an adequate number of MPs by market segment have submitted output schedules and three-part supply offer curves, have participated in the CRR auction (? Is this an EDS 3 activity?) and have participated in LFC Testing. See general comment 2 |  |  |  |
| Reporting Data Sources: EDS 3 Trials Log |  |  |  |
| References | TP: 5.4.8 | TNP: 6.4.4, 6.5.7.1.12, 6.5.7.1.13 |  |

### MP16 - MP EDS-4 Trials Participation

| Reported By: MP & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS 4 Release 9 – DAM, RUC, SASM less 14 days |  |  |  |
| Metric Description: This metric evaluates the level of market participant participation in the EDS 4 Trial. |  |  |  |
| Background: The intent of this metric is to ensure adequate participation in the testing of Full Nodal Market Functionality. |  |  |  |
| Criteria: Market Participants are participating in each of the activities outlined in the EDS 4 Trails Handbook. The Readiness Team will review documentation that an adequate number of MPs by market segment have participated. See general comment 2 |  |  |  |
| Reporting Data Sources: EDS 4 Trials Log |  |  |  |
| References | TP: 5.4.1 | TNP: 3.9, 3.16-18, 9.2.7-8 |  |

### MP17 - MP Qualification Activities

| Reported By: MP & ERCOT |  |  | EDS: Registration |
| --- | --- | --- | --- |
| Target Completion: EDS 4 168 Hour Test Major Milestone less 90 days, less 30 days, less 14 days |  |  |  |
| Metric Description: This metric will measure the completion of specified qualification requirements to support market trials. |  |  |  |
| Background: The intent of this metric is to measure Market Participant ability to perform specific market and operational functions required for qualification. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that market participants are qualified to engage in the market. Target 1; Target 2; Target 3. 50%; 80%; 95%. MP Qualification Checklist Complete = Target % of MPs Intending to Participate in the market See general comemnt 2 |
| Reporting Data Sources: Qualification Checklists/ Siebel Entry |  |  |  |
| References | TP: N/A | TNP: 16.1, 16.2 |  |

# Commercial Operations Metrics

### CO1 - Settle Market for 7 Days and provide appropriate extracts

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 9 Complete |  |  |  |
| Metric Description: ERCOT will issue to eligible market participants test DAM settlement statements, test RTM settlement statements, test DAM settlement invoice(s), and test RTM settlement invoice(s) and provide appropriate extracts for consecutive 7 Operating Days consistent with the 168-Hour Test. |  |  |  |
| Background: The intent of this metric is to prove ERCOT's ability to settle the DAM and the RTM for 7 consecutive days. |  |  |  |
| Criteria: The Readiness Team will confirm settlement statements and invoices and confirm appropriate extracts were posted for each eligible market participant for the seven day period. Readiness will be met when the posting of the seven settlement statements and the weekly invoice occurs. Posted Statements for each Eligible MP =7 Posted DAM Invoices for each Eligible MP = 7 Posted RT Invoices for each Eligible MP = `1 Missing (critical) data extracts = 0 |  |  |  |
| Reporting Data Sources: MIS Posted Settlement Statements and Invoices |  |  |  |
| References | TP: 5.4.6 (4), 6.1(g) | TNP: |  |

### CO2 - Verify Dispute Process of 168 Hour Test

| Reported By: MP & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 9 Complete |  |  |  |
| Metric Description: ERCOT shall provide settlement dispute resolution service for all MPs submitting a dispute. The dispute resolution metric is dependent upon Market Participants ability to receive statements, invoices and data extracts and submit disputes via the MIS. |  |  |  |
| Background: The intent of this metric is to ensure that dispute management process is functioning, allowing for Market Participants to log and ERCOT to facilitate the resolution of disputes. |  |  |  |
| Criteria: The Readiness Team will review documentation that settlements disputes have been addressed in accordance with ERCOT's dispute resolution process. The Readiness Team will evaluate that the settlement dispute process can process a dispute through to resolution. # of unprocessed Disputes that were logged during the 168 hour test = 0 Invoice and Settlement Dispute Logged >=1 per QSE and CRR Account Holder Completed Simulated Dispute within Dispute Tracking System >=10 Does this mean that ERCOT will request each MP submit a dispute? |  |  |  |
| Reporting Data Sources: Publicly Posted Dispute Process / 168 Hour Test Dispute Tracking Log/Tool |  |  |  |
| References | TP: 5.4.9 (2) | TNP: |  |

### CO3 - Verify DAM Settlement Statements

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Full Nodal Functionality Major Milestone plus 30 days |  |  |  |
| Metric Description: ERCOT will test DAM settlement statements by independent calculation and verify appropriate statement posting to the MIS. |  |  |  |
| Background: The intent of this metric to verify the accuracy and appropriate posting of Day Ahead Settlement Statements. Day Ahead settlements use Day Ahead Settlement Point Prices (DASPP) that are calculated for Resource Nodes, Load Zones, and Hubs. |  |  |  |
| Criteria: The Readiness Team will confirm that the DAM settlement calculations were validated and statements posted for each eligible participant. The validation will be accomplished by comparing Day Ahead Settlement Statements generated by the system to calculations independently generated using common input data. A statement sampling representing all applicable charge types shall be used. Readiness will be met when the dollar difference between the system generated Day Ahead Settlement Statement and the independently generated calculations equals zero for the sample set. Readiness will be met when all Day Ahead Settlemement Statements are posted in the appropriate area of the MIS. For the sample set: System Generated DA Statement Dollars - Independently Generated DA Calculation Dollars =$0 System? Generated DA Statements not posted = 0 |  |  |  |
| Reporting Data Sources: System Generated DA Statements/ DA Settlement Determinants / Independently Generated DA Calculations |  |  |  |
| References | TP: 5.4.7 (3) | TNP: |  |

### CO4 - Zonal/Nodal Coordinated Settlement Operations

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS 4 168 Hour Test Major Milestone |  |  |  |
| Metric Description: ERCOT shall run both Zonal and Nodal settlement processes in a coordinated manner. (Note: Only the Zonal statements shall be binding) |  |  |  |
| Background: The intent of this metric is to ensure ERCOT's ability to process settlements for both Zonal and Nodal markets for the transition period where Zonal and Nodal market settlement will overlap. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that Zonal and nodal coordinated settlements have been implemented prior to Texas Nodal Market Launch. Readiness will be met when statements have been produced for both Nodal and Zonal at the threshold defined below. During a planned 24 hour period: Zonal Settlements Run >=3 and Nodal Settlements Run >= 3 Zonal/Nodal Settlements Process(es) documented to support >= 6 Settlement Runs |  |  |  |
| Reporting Data Sources: Settlement Statement Completion Statistics from Job Scheduler for Zonal and Nodal Settlements Runs |  |  |  |
| References | TP: 6.1 (j) | TNP: |  |

### CO5 - Verify RTM Settlement Statements

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 8 complete plus 14 days |  |  |  |
| Metric Description: ERCOT will test RTM Settlement Statements by independent calculation and verification of the appropriate posting to the MIS. |  |  |  |
| Background: The intent of this metric is to verify the accuracy and appropriate posting of RTM Settlement Statements. |  |  |  |
| Criteria: The Readiness Team will confirm that the RTM settlement calculations were validated and statements posted for each eligible participant. The validation will be accomplished by comparing Real Time Settlement Statements generated by the system to calculations independently generated using common input data. A statement sampling representing all applicable charge types shall be used. Readiness will be met when the dollar difference between the system generated Real Time Settlement Statement and the independently generated calculations equals zero for the sample set. Readiness will be met when all Real Time Settlemement Statements are posted in the appropriate area of the MIS. For the sample set: System Generated RT Statement Dollars- Independently Generated RT Calculation Dollars =$0 System Generated RT Statements not posted = 0 |  |  |  |
| Reporting Data Sources: System Generated RT Statements/ RT Settlement Determinants/ Independently Generated RT Calculations |  |  |  |
| References | TP: 5.4.7 (3) | TNP: |  |

### CO6 - Verify RTM Settlement Invoices

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 8 complete plus 14 days |  |  |  |
| Metric Description: ERCOT will test RTM Settlement Invoices by independent calculation and verification of the appropriate posting to the MIS. |  |  |  |
| Background: The intent of this metric is to verify the accuracy and appropriate posting of Real Time Market Settlement Invoices. |  |  |  |
| Criteria: The Readiness Team will review documentation and data that verifies that the RTM Settlement invoices were issued according to ERCOT processes and that calculations summing distinct statements are correct. An invoice sampling of all applicable charge types shall be used. (Sample set from CO5 may be used). Readiness will be met when the dollar difference between the system generated Real Time Settlement Invoice and the one independently generated calculations equals zero for the sample set. Readiness will be met when all RTM Settlement Invoices are posted in the appropriate area of the MIS. For the sample set: System Generated RT Invoice Dollars - Independently Generated RT Calculation Dollars = $0 System Generated RT Invoices not posted = 0 |  |  |  |
| Reporting Data Sources: System Generated RTM Invoices/ System Generated RTM Statements/ Independently Generated RT Calculations |  |  |  |
| References | TP: N/A | TNP: |  |

### CO7 - Verify DAM Invoices

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Full Nodal Functionality Major Milestone plus 30 days |  |  |  |
| Metric Description: ERCOT will test DAM settlement section of the invoices by independent calculation and verification of the appropriate posting to the MIS. |  |  |  |
| Background: The intent of this metric is to verify the accuracy and appropriate posting of DAM Settlement Invoices. |  |  |  |
| Criteria: The Readiness Team will review documentation and data that verifies that the DAM Settlement invoices were issued according to ERCOT processes and that calculations summing distinct statements are correct. An invoice sampling of all applicable charge types shall be used. (Sample set from CO3 may be used). Readiness will be met when the dollar difference between the system generated Day Ahead Settlement Invoice and the one independently generated equals zero for the sample set. Readiness will be met when verified DAM Invoices are posted in the appropriate area of the MIS. For each invoice in the sample: System Generated DAM Invoice Dollars - Independently Generated DAM Invoice Dollars = $0 System Generated DAM Invoices not posted = 0 |  |  |  |
| Reporting Data Sources: System Generated DAM Invoices/ System Generated DA Statements / Independently Generated DAM Calculations |  |  |  |
| References | TP: N/A | TNP: |  |

### CO8 - Verify CRR Auction Invoices

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-3 End of Trial Operations of CRR Major Milestone plus 30 days |  |  |  |
| Metric Description: ERCOT will test CRR Auction invoices by independent calculation and verify appropriate posting to the MIS. |  |  |  |
| Background: The intent of this metric to verify the accuracy and appropriate posting of CRR Auction Invoices. |  |  |  |
| Criteria: The Readiness Team will verify that the CRR Auction Invoices were generated for the eligible CRR Account Holders accordingly to ERCOT processes. The Readiness Team will review documentation that ERCOT has verified the CRR Auction Invoices are consistent with the CRR Auction results. CRR Auction Invoices will be posted for each eligible CRR Account Holder. Readiness will be met when the dollar difference between the CRR Auction Results and the CRR Auction Invoice equals zero. Readiness will be met when all CRR Auction Invoices are posted in the appropriate area of the MIS. CRR Auction Result for MPn - CRR Auction Invoice for MPn = $0 - These may not be one to one System Generated CRR Auction Invoices not posted = 0 |  |  |  |
| Reporting Data Sources: CRR Auction Results / CRR Auction Invoices |  |  |  |
| References | TP: N/A | TNP: |  |

### CO9 - Verify Financial Transfer and Processing

| Reported By: MP & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Full Nodal Functionality Major Milestone |  |  |  |
| Metric Description: ERCOT will perform a "Penny Test" with applicable registered market participants. |  |  |  |
| Background: The intent of this metric is to verify that the financial transfer process is functioning between ERCOT and applicable registered Market Participants. |  |  |  |
| Criteria: The Readiness Team will review the results of the "Penny Test" to confirm that ERCOT can transfer funds to Registered Market Participants and that Market Participants can transfer funds to ERCOT. Readiness will be met when $0.01 has been successfully transferred from ERCOT to each registered Market Participant. Readiness will be met when $0.01 has been successfully transferred from registered Market Participant to each ERCOT. Number of unsuccessful transfers to registered MPs = 0 Number of unsuccessful transfers to ERCOT = 0 If a QSE in the zonal market is responding with the transfer of funds, what more is needed? Does this apply to CRR auction settlement? |  |  |  |
| Reporting Data Sources: Results of the Penny Test |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### CO10 - Verify Credit Calculations

| Reported By: MP & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 168-Hour Test Major Milestone less 14 days |  |  |  |
| Metric Description: ERCOT will calculate and monitor the available credit limit of market participants. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to monitor that Market Participants are operating within proscribed credit limitations based upon their credit exposure and financial security. |  |  |  |
| Criteria: The issue of credit and credit worthiness should be handled internally at ERCOT and is the responsibility of the ERCOT organizations responsible for this activity in today’s zonal market. These groups should be required to provide a dashboard that shows progress in establishing a credit relationship with new market participants (e.g. CRR Account Holders) and, if necessary in their opinion, existing market participants. |  |  |  |
| Reporting Data Sources: (Credit Management and Monitoring )CMM Database / MIS |  |  |  |
| References | TP: 6.1 (l) | TNP: 16.11 & 4.4.10 |  |

# Congestion Revenue Rights Metrics

### CRR1 - Develop CRR Test Plan

| Reported By: ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: EDS 3 - CRR Data Validation EDS Trial Preparation Milestone less 14 days |  |  |  |
| Metric Description: ERCOT will provide detailed CRR test plan. |  |  |  |
| Background: The intent of this metric is to ensure that the test strategy for the CRR process is comprehensive in nature. |  |  |  |
| Criteria: The Readiness Team will receive notification from the EDS 3 PM of concurrence by TPTF with the CRR Test Plan. Readiness will be met upon receipt of the notification from the EDS 3 PM or review of TPTF minutes. TPTF Concurence Received |  |  |  |
| Reporting Data Sources: CRR Test Plan |  |  |  |
| References | TP: 5.4.5 (1) | TNP: |  |

### CRR2 - Develop TCR to CRR Transition Plan

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 270 days |  |  |  |
| Metric Description: ERCOT will provide detailed TCR to CRR plan describing each step of the transition. |  |  |  |
| Background: The intent of this metric is to verify the existence and publication of the TCR to CRR transition Plan. |  |  |  |
| Criteria: The Readiness Team will review, from a public source, the TCR to CRR transition plan including rebate, timing and other CRR details of interest. Readiness will be achieved when the Readiness Team will be provided with documentation that verifies that the TCR to CRR transition plan has been created. TCR to CRR Transition Plan exists |  |  |  |
| Reporting Data Sources: TCR to CRR Transition Plan |  |  |  |
| References | TP: N/A | TNP: |  |

### CRR3 – Trial Operation of Monthly CRR Auction

| Reported By: ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: EDS-3 - Release 7 complete milestone |  |  |  |
| Metric Description: ERCOT shall execute a trial monthly allocation and auction of Congestion Revenue Rights for market participants prior to Nodal market launch during Market Trials. |  |  |  |
| Background: This intent of this metric is to verify ERCOT's ability to facilitate, execute and report on a Monthly CRR Auction. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that a Congestion Revenue Rights Monthly auction produced a solution, allocated revenue rights to potential CRR account holders and produced results for participants. Readiness will be met when the CRR Monthly auction solves within accetable timelines. Readiness will be met when Monthly CRRs results are distributed to applicable account holders. Monthly CRR Auction Solves within = TBD Monthly CRR Trial Results distributed to participants = 100% |  |  |  |
| Reporting Data Sources: Extract from CRR Database |  |  |  |
| References | TP: 5.4.5 (1) | TNP: (Leave Out) |  |

### CRR4 - Implement TCR to CRR Transition Plan

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 120 days |  |  |  |
| Metric Description: ERCOT shall Implement the approved TCR to CRR Transition Plan to assign rights for the Nodal Market Go-Live. |  |  |  |
| Background: The intent of this metric is to ensure that there is an acceptable TCR to CRR Transition Plan. |  |  |  |
| Criteria: The Readiness Team will be notified of the implementation of the approved TCR to CRR Transition Plan. Readiness will be achieved when the Readiness Team is provided with documentation that verifies that the TCR to CRR transition plan previously described in Metric CRR2, "Develop TCR to CRR TransitionPlan" has been implemented. TCR to CRR Transition Plan implemented |  |  |  |
| Reporting Data Sources: Notification of the TCR to CRR Transition Plan Implementation |  |  |  |
| References | TP: 6.1 (i) | TNP: |  |

### CRR5 - Trial Operation of Annual CRR Auction during Trials

| Reported By: ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: EDS-3 – Release 7 Completion |  |  |  |
| Metric Description: ERCOT shall execute an annual allocation and auction of Congestion Revenue Rights for market participants prior to Nodal market launch during Market Trials. |  |  |  |
| Background: This intent of this metric is to prove ERCOT's ability to facilitate, execute and report on an Annual CRR Auction. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that a Congestion Revenue Rights Annual auction produced a solution, allocated revenue rights to potential CRR account holders and produced results for participants. . Readiness will be met when the CRR Annual Auction solves within acceptable timelines. Readiness will be met when Annual CRRs results are distributed to applicable account holders. Annual CRR Auction Solves within = TBD Monthly CRR Trial Results distributed to participants = 100% |  |  |  |
| Reporting Data Sources: Extract from CRR Database |  |  |  |
| References | TP: 5.4.5 (1) | TNP: |  |

# ERCOT Internal Metrics

### E1 - ERCOT Staff Completes Training

| Reported By: ERCOT |  |  | EDS: 2,3,4 |
| --- | --- | --- | --- |
| Target Completion: Start of EDS 2,3,4, Go Live Activities less 14 days |  |  |  |
| Metric Description: ERCOT Staff Completes required training modules by area of expertise and job responsibilities. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT staff has the ability to facilitate the Nodal Market. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that ERCOT Staff have completed the required training. Readiness will be achieved when ERCOT staff have completed required training. Actual Passing Participation by Course for Required Training by EDS/Go Live = 100% |  |  |  |
| Reporting Data Sources: Learning Management System |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E2 - Verify ERCOT Performance Monitoring Test Plan

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: EDS 4 - 168 Hour Test Major Milestone less 30 days |  |  |  |
| Metric Description: ERCOT shall develop a detailed test plan to ensure adherence to the ERCOT Performance Monitoring Compliance standard.. |  |  |  |
| Background: It is the intent of this metric to ensure that the systems, access and capabilities are in place to monitor ERCOT performance in the Nodal Market. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that ERCOT is ready to begin the compliance activities as specified in Section 8.2: Performance Monitoring and Compliance. Readiness will be achieved when the ERCOT Performance Monitoring plan is posted. ERCOT Performance Monitoring Test Plan Exists |  |  |  |
| Reporting Data Sources: Notification of Capability to Monitor ERCOT Compliance |  |  |  |
| References | TP: 5.4.12 | TNP: 8.2 |  |

### E3 - Validate Telemetry/SE EDW/MIS Access & Data Accuracy

| Reported By: MP & ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: EDS 2 – Release 3 complete |  |  |  |
| Metric Description: ERCOT shall provide access to accurate operational data via the EDW for both ERCOT Operations and Market Participant. |  |  |  |
| Background: The intent of this metric is to ensure access to accurate data via the EDW. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that operations data access is available via the data warehouse. Readiness will be achieved when source system data is accurately represented in the EDW and is accessible by ERCOT Operations and Market Participants. Integration Testing Team attests to the successful completion of those test scripts related to the Operations component of the EDW. Operations confirms ability to access EDW Market Participants confirm ability to access EDW/MIS |  |  |  |
| Reporting Data Sources: Notification from Integration Test Team Attesting to EDW accuracy / Notification from Operations Attesting EDW Access |  |  |  |
| References | TP: N/A | TNP: 17.3.2 |  |

### E4 - Price Protection Mechanisms

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 90 days |  |  |  |
| Metric Description: ERCOT and the Market Participants shall develop protection mechanisms to be implemented for a limited period after market opening. |  |  |  |
| Background: It is the intent of this metric to ensure that a plan for price protection mechanisms for use during the early stages of market start-up has been created to ensure against price excursions that may occur as a result of computer system or market design limitations. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that the development of protection mechanisms by ERCOT has occurred. Readiness will be achieved when the approved price protection plan is published. Price Protection Plan is published |  |  |  |
| Reporting Data Sources: Price Protection Plan |  |  |  |
| References | TP: 6.1 (m) | TNP: N/A |  |

### E5 - Nodal SAS 70 Preparedness

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 45 days |  |  |  |
| Metric Description: ERCOT shall prepare for the transition from current to nodal SAS 70 requirements by identifying those control objectives which must be changed or modified. |  |  |  |
| Background: It is the intent of this metric to ensure that SAS 70 Audits can be accomplished in the Nodal Market by revising the control objectives for Nodal operations. |  |  |  |
| Criteria: The Readiness Team will review documentation that the current to nodal transition SAS 70 control objectives have been updated for nodal operations. Control Objectives Updated = 100% of Control Objectives identified as requiring a Nodal update |  |  |  |
| Reporting Data Sources: Control Objectives Log revision history |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E6 - Develop Nodal Operating Guides

| Reported By: ERCOT |  |  | EDS: 3,4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Less 360 days |  |  |  |
| Metric Description: ERCOT shall develop Nodal Operating Guides to direct Market Participants on the daily operation of the Texas Nodal Market and Grid. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has provided the Market Participants with the information required to operate the Texas Nodal Market and Grid. |  |  |  |
| Criteria: The Readiness Team will receive documentation that the creation and posting of approved Nodal Operating Guides has occurred. Readiness will be met when the Operating Guides have been posted to the MIS and approved by ROS and TAC. Operating Guides posted |  |  |  |
| Reporting Data Sources: Operating Guides |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E7 - Validate EDW WEMM Access & Accuracy

| Reported By: WEMM & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDW 6 FAT Milestone plus 90 days |  |  |  |
| Metric Description: ERCOT shall provide access to accurate WEMM Related data via the EDW. |  |  |  |
| Background: The intent of this metric is to ensure access to accurate data via the EDW. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that data access is available to the WEMM via the data warehouse. Readiness will be met when source system data is accurately represented in the EDW and is accessible by the WEMM. Integration Testing Team attests to the successful completion of those the testing of the WEMM component of the EDW. WEMM confirms ability to access EDW |  |  |  |
| Reporting Data Sources: Notification from Integration Test Team Attesting to EDW accuracy / Notification from WEMM Attesting EDW Access |  |  |  |
| References | TP: N/A | TNP: 17.3.2 |  |

### E8 - ERCOT Staffed for Texas Nodal Operations

| Reported By: ERCOT |  |  | EDS: N/A |
| --- | --- | --- | --- |
| Target Completion: EDS 4 - Full Nodal Functionality 24*7 Operations Major Milestone less 60 days |  |  |  |
| Metric Description: ERCOT will ensure the appropriate staffing levels required to execute the nodal market. In addition, the roles and responsibilities have been appropriately defined for nodal personnel. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT is appropriately staffed to support Nodal Operations as approved by the PUCT. |  |  |  |
| Criteria: Each impacted Director or VP is responsible for conducting a sizing and alignment analyses for their area as a part of the overall IRT project. Each department will develop their respective supporting documentation and readiness assessment. The Readiness Team will view the analysis results for each department and verify completion of the sizing and alignment analysis and the development of the corresponding staffing plan. Readiness will be achieved upon the completion of Sizing and Alignment Analysis for each Department and Departmental Staffing Plans and the execution of those plans. Sizing and Alignment Analysis completed for each impacted department Staffing plan completed for each impacted department Staffing plan executed for each impacted department |  |  |  |
| Reporting Data Sources: Sizing and Alignment Analysis for each Department / Departmental Staffing Plans |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E9 - Develop TN Procedures

| Reported By: ERCOT |  |  | EDS: 2,3,4 |
| --- | --- | --- | --- |
| Target Completion: Go-Live less 60 days |  |  |  |
| Metric Description: ERCOT shall develop it’s internal procedures supporting the Texas Nodal Market. |  |  |  |
| Background: It is the intent of this metric to have ensure that the processes necessary to run the Nodal market are in place. |  |  |  |
| Criteria: The Readiness Team will review documentation that ERCOT has created the processes necessary for operating the Texas Nodal Market. Readiness will be achieved when the processes supporting the Nodal Market have been completed. ERCOT Critical Nodal Market Processes Complete |  |  |  |
| Reporting Data Sources: ERCOT Process/ Procedure Inventory |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### E10 - Validate EDW Commercial Systems Access & Accuracy

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDW 6 FAT Milestone plus 90 days |  |  |  |
| Metric Description: ERCOT shall provide access to accurate Commercial data via the EDW. |  |  |  |
| Background: The intent of this metric is to ensure access to accurate data via the EDW. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that commercial data access is available via the data warehouse. Readiness will be met when source system data is accurately represented in the EDW and is accessible by ERCOT Commercial Operations. Integration Team verifies consistency of EDW data compared to respective source systems ERCOT Commercial Operations confirms ability to access data within the EDW |  |  |  |
| Reporting Data Sources: Notification from Integration Test Team verifying accuracy of EDW data / Notification from Commercial Operations Attesting EDW Access |  |  |  |
| References | TP: N/A | TNP: 17.3.2 |  |

### E11 - Validate EDW Compliance Data Access

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDW 6 FAT Milestone plus 90 days |  |  |  |
| Metric Description: ERCOT shall provide access to accurate Compliance Related data via the EDW. |  |  |  |
| Background: The intent of this metric is to ensure access to accurate data via the EDW. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that Compliance Dept. data access is available via the data warehouse. Readiness will be met when source system data is accurately represented in the EDW and is accessible by ERCOT Compliance. Integration Testing Team verifying the successful completion of those test scripts related to the Compliance component of the EDW. Compliance confirms ability to access EDW |  |  |  |
| Reporting Data Sources: Notification from Integration Test Team Verifying Accuracy of EDW data / Notification from Compliance verifying EDW Access |  |  |  |
| References | TP: N/A | TNP: |  |

### E12 - MIS Compliance Test

| Reported By: ERCOT |  |  | EDS: |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Full Nodal Functionality Major Milestone plus 30 |  |  |  |
| Metric Description: This metric will measure the completion and implementation of a compliance plan to verify the degree to which protocol requirements for MIS Public, Secure, and Certified areas are met. |  |  |  |
| Background: It is the intent of this metric to ensure the functionality and operability of the Secure, Public and Certified areas of the Market Information System. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that ERCOT has successfully completed a MIS Compliance Test. Readiness will be met when the completion of the MIS Compliance Test has been accomplished. MIS Compliance Test Successfully Passed |  |  |  |
| Reporting Data Sources: MIS Compliance Test Plan / MIS Compliance Test Results |  |  |  |
| References | TP: 5.4.13 | TNP: 12 & 4.4 & 9.1.3 |  |

### E13 - Standard Form Agreements Executed

| Reported By: ERCOT |  |  | EDS: Registration |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 120 days |  |  |  |
| Metric Description: ERCOT shall have each Market Participant execute a Standard Form Agreement prior to participation in the Market. |  |  |  |
| Background: It is the intent of this metric to ensure that each ERCOT Participant has executed the new Standard Form Agreement |  |  |  |
| Criteria: The Readiness Team will review documentation that all Market Participants planning to engage in the Texas Nodal Market have executed a Standard Form Agreement. Readiness will be achieved when those MPs intending to participate in the Nodal Market have executed the new Standard Form Agreement. Standard Form Agreement executed for all Market Participants |  |  |  |
| Reporting Data Sources: Standard Form Agreement Register in Legal Department / MP Self Report line item expressing the intent to participate in the Nodal Market |  |  |  |
| References | TP: 6.1 (k) | TNP: 16.8.1 & 16.8.2 |  |

### E14 - Verify QSE Performance Monitoring Test Plan

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: EDS 4 - 168 Hour Test Major Milestone less 30 days |  |  |  |
| Metric Description: ERCOT shall develop a TAC-approved QSE/Resource monitoring Program to be included in the Operating Guides. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has developed a program to monitor Generating Resource Governor Response Deployment Compliance for Frequency Disturbances and QSE Ancillary Service Performance Standards. |  |  |  |
| Criteria: The Readiness Team will verify that a QSE/Resource monitoring Program is documented and approved within the ERCOT Operating Guides and that a corresponding test plan has been successfully executed. QSE Performance Monitoring Test Plan successfully executed |  |  |  |
| Reporting Data Sources: QSE Performance Monitoring Plan |  |  |  |
| References | TP: 5.4.12 | TNP: 8.1 |  |

### E15 - Verify TSP Performance Monitoring Test Plan

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: EDS 4 - 168 Hour Test Major Milestone less 30 days |  |  |  |
| Metric Description: ERCOT shall develop a detailed test plan to ensure compliance with TSP Performance Monitoring Standard. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has developed a plan to monitor the following: - Transmission Element Rating Calculations - Real Time Data Meeting Telemetry Standards - Communications System Availability - Outage Scheduling Coordination - Written Black Start Procedures - Back Up Control Plan - Compliance with Dispatch Instructions - Voltage and Reactive Control Performance - NERC Standards |  |  |  |
| Criteria: The Readiness Team will verify that a TSP monitoring Program is documented and approved within the ERCOT Operating Guides and that a corresponding test plan has been successfully executed. QSE Performance Monitoring Test Plan successfully executed |  |  |  |
| Reporting Data Sources: TSP Performance Monitoring Plan |  |  |  |
| References | TP: 5.4.12 | TNP: 8.3 |  |

# Energy Management Operations Metrics

### EMO1 - Network Security Analysis & Transmission Constraint Management

| Reported By: ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: EDS 2 - Release 3 complete plus 60 days |  |  |  |
| Metric Description: ERCOT shall Validate Transmission Constraint Management Functions to include the accurate identification of constraints, the Network Security Analysis Process, the security analysis sequence, operation of Dynamic Ratings processor, Special Protection Scheme (SPS), Remedial Action Plans (RAPs), and Load Rollover. |  |  |  |
| Background: The intent of this metric is to verify the ability of ERCOT manage constraints in a reliable economical manner. |  |  |  |
| Criteria: The Readiness Team shall review documentation that the transmission constraint management functions include the accurate identification of constraints, the Network Security Analysis process, the security analysis sequence and the operation of Dynamic Ratings processor, Special Protection Scheme (SPS), Remedial Action Plans (RAPs), and Load Rollover. Readiness will be achieved when the number of Over Load and Voltage limit alarms are equivalent to the number of actual Over Load and Voltage violations. Readiness will be achieved with the RTCA has been run for every element in system. Number of n-1 contingency violations = Number of Load & Voltage Limit Alarms Sum of N-1 Analyzed = Sum of Elements |  |  |  |
| Reporting Data Sources: SCADA Extract/ EMS Extract / Limit Alarm Log / Extract from Real Time Contingency Analysis Engine (RTCA) |  |  |  |
| References | TP: 5.4.3 | TNP: 6.5.7.1 |  |

### EMO2 - Verify Voltage Support Functionality

| Reported By: MP & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Full Nodal Functionality Milestone |  |  |  |
| Metric Description: This metric will verify that ERCOT has a functioning process to manage Voltage Support Services (VSS) in the Nodal Market. |  |  |  |
| Background: It is the intent of this metric to ensure that ERCOT can control the voltage of the system in the Nodal Market through the use of communicating voltage profiles to QSEs and TSPs and monitoring of voltages to assure compliance to Protocol Standards. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the proper functionality of the Voltage Support Service. Readiness will be met when a test of the Voltage Support Service has been completed. Voltage Profiles are created and communicated to QSEs & TSPs (Voltage Profile Bus Voltage – Actual Bus Voltage) * 100 / Voltage Profile Bus Voltage <= 2% |  |  |  |
| Reporting Data Sources: Voltage Profiles by QSE and TSP / EMS Extract of Voltage Telemetry Values corresponding to Voltage Profile Locations |  |  |  |
| References | TP: N/A | TNP: 3.15(2) |  |

### EMO3 - Verify Outage Evaluation System Functionality

| Reported By: MP & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 9 Complete |  |  |  |
| Metric Description: This metric will measure the ability of ERCOT to manage the Outage Management Process to include the use by Market Participants and also include an Outage Minimization Plan for initial Nodal Market start-up. |  |  |  |
| Background: It is the intent of this metric to ensure that Market Participants can schedule, change and receive outage notifications, that the Operators can distinguish between forced and scheduled outages and that an Outage Minimization Plan is created for Nodal Market Start-up. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that ERCOT developed an approved Outage Management System capable of efficiently managing outages. Readiness will be met when the Outage Minimization plan is published. Readiness will be met when the Outage Management Test has been successfully completed. An approved Outage Minimization Plan is published A test of the Outage Management Process is completed |  |  |  |
| Reporting Data Sources: Outage Minimization Plan/ Test results of Outage Management Test |  |  |  |
| References | TP: 5.4.10 (1) | TNP: |  |

### EMO4 - Run 7 Day Stability Test

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Less 30 days |  |  |  |
| Metric Description: The EDS will support SCADA, Network Security Analysis, Transmission Constraint Management, SCED, RUC AND LFC for 168 continuous hours. |  |  |  |
| Background: The intent of this metric is to ensure that the EMS runs in a stable manner for a prolonged period of time. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the EDS successfully supported SCADA, Network Security Analysis, Transmission Constraint Management, SCED, RUC and LFC for 168 continuous hours. Readiness will be met when the EMS successfully supports SCADA, Network Security Analysis, Transmission Constraint Management, SCED, RUC and LFC for 168 continuous hours. Runtime >= 168 hours without significant errors |  |  |  |
| Reporting Data Sources: System Logs |  |  |  |
| References | TP: 5.4.9 (1) | TNP: N/A |  |

### EMO5 - Verify ACE Performance

| Reported By: ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: EDS-3 LFC Major Milestone Start + 30 days |  |  |  |
| Metric Description: This metric will measure the comparison of the Area Control Error (ACE) calculation between the Nodal control system and existing control system, for accuracy for seven days. |  |  |  |
| Background: It is the intent of this metric to verify that the Nodal ACE Calculation is accurate by comparing it to the existing calculation tool in order to comply with NERC standards. |  |  |  |
| Criteria: The Readiness Team will review documentation that the accuracy of calculation of ACE in the TXMACS has been verified. Readiness will be met when the comparison of the Nodal generated ACE tracks with the existing ACE for seven consecutive days. TXMACS ACE =Current Operations ACE for seven consecutive days |  |  |  |
| Reporting Data Sources: EMS Extract of existing ACE and Nodal Ace |  |  |  |
| References | TP: 5.4.8 (2) | TNP: 6.5.7.6.1 |  |

### EMO6 - QSE Response to Dispatch

| Reported By: MP & ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: EDS-3 Major Milestone LFC Testing + 60 days |  |  |  |
| Metric Description: This metric will ensure that ERCOT can send dispatch instructions to QSEs to verify load frequency control, verify that QSEs can receive control signals from LFC for Regulation and that each QSE can respond to dispatch signals and run independently on frequency control. |  |  |  |
| Background: It is the intent of this metric that all resources can receive and respond to dispatch instruction as well as run on Load Frequency Control in order to maintain grid reliability. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that ERCOT can send dispatch instructions to QSEs to verify Load-Frequency Control, LFC can maintain system frequency by balancing resources to the load and that each QSE can respond to dispatch signals and run independently on frequency control. Readiness will be met when the LFC Test is complete. Readiness will be met when the Resource Response Test is complete in accordance with the test plan success criteria. LFC Test results in stable frequency Resource responds to base point signals within specified requirements Resource runs on frequency control |  |  |  |
| Reporting Data Sources: Results of LFC Test / Results of Resource Base Point Response Test / Resource Frequency Run Test |  |  |  |
| References | TP: 5.4.8 (2) | TNP: 6.5.7.6 & 8.1 |  |

### EMO7 - Verify Load Forecast Accuracy

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 9 Start + 120 days |  |  |  |
| Metric Description: This metric will determine the ability of the Short Term Load Forecast(STLF) and Medium Term Load Forecast(MTLF) to meet accuracy standards. |  |  |  |
| Background: It is the intent of this metric to ensure that the STLF and MTLF meet standard accuracy performance measures in order to determine the amount of required generation. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that STLF and MTLF Load Forecast Accuracy is within prescribed limits during market trials. Readiness will be met when the STLF is operating to existing standards. Readiness will be met when the MTLF is operating to existing standards. STLF is within STLF accuracy limit of actual load MTLF is within MTLF accuracy limit of actual load |  |  |  |
| Reporting Data Sources: EMS extract of Actual Load/ EMS extract of STLF / EMS extract of MTLF |  |  |  |
| References | TP: 5.4.2(2) | TNP: 3.12, 3.13, 4.2.2 & 8.2(2)© |  |

### EMO8 - Conduct EECP Test

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS 4 - 168 Hour Test Major Milestone less 30 days |  |  |  |
| Metric Description: ERCOT shall conduct a test of the Emergency Electric Curtailment Plan (EECP). |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT can reduce system demand in a temporary manner to match a decrease in supply. There must be an orderly, predetermined procedure for curtailing demand during such emergencies, ERCOT shall initiate and coordinate the implementation of EECP. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that ERCOT conducted a test of the Emergency Electric Curtailment Plan (EECP). Readiness will be achieved when Control Room procedures have been deployed and the EECP test was conducted. EECP Procedures Published EECP Test Completed Successfully as Defined in the EECP Test Plan |  |  |  |
| Reporting Data Sources: Documentation and Control Room Desk Procedures. All procedures are also posted at www.ercot.com. EDS 4 Notification of EECP Test Complete |  |  |  |
| References | TP: 5.4.16 | TNP: 6.5.9.4 |  |

### EMO9 - Validate Zonal and Nodal Common Constraints

| Reported By: ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: First: EDS 3 - SCED Testing EDS Trial Preparation Milestone Go Live Activities less 60 days |  |  |  |
| Metric Description: Verify that common constraints between the Zonal and Nodal System are consistent with one another. |  |  |  |
| Background: The intent of this metric is to provide a litmus test of the Nodal Systems constraint observation capability. |  |  |  |
| Criteria: The Readiness Team will verify that Zonal and Nodal common constraints are consistent with reasonably comparable results. Readiness will be achieved when constraints are comparable. The set of Zonal Constraints = The set of Nodal Constraints Zonal and Nodal Element Overloads, Voltage Violations & Associated Shift Factors are within 10% of one another |  |  |  |
| Reporting Data Sources: SCED / Transmission Constraint Manager (TCM) |  |  |  |
| References | TP: 5.4.1 (2)(b) | TNP: N/A |  |

# Network Model Management Metrics

### N1 - ERCOT Telemetry Alarm Processing

| Reported By: MP & ERCOT |  |  | EDS: 1 |
| --- | --- | --- | --- |
| Target Completion: EDS 1 - Release 1 plus 14 days |  |  |  |
| Metric Description: ERCOT initiates alarms for Limit Violations,& Status Changes. |  |  |  |
| Background: The intent of this metric is to ensure that control operators are aware of relevant EMS alarms. |  |  |  |
| Criteria: The Readiness Team will review the results of the Limit, Status and other EMS Alarm Tests. Readiness will be achieved when alarms are generated from the Limit, Status and other EMS Tests. Load / Rating > Alarm set point Change of Status inititiates a Status Alarm |  |  |  |
| Reporting Data Sources: Alarm Log |  |  |  |
| References | TP: 5.4.1 (2)(f),(g) | TNP: 8.1.2.2(6)(b) |  |

### N2 - ERCOT Telemetry/ICCP System Failover

| Reported By: MP & ERCOT |  |  | EDS: 1 |
| --- | --- | --- | --- |
| Target Completion: EDS 1 - Release 2 plus 14 days |  |  |  |
| Metric Description: Verify that all ERCOT telemetry failover criteria are met. |  |  |  |
| Background: The intent of this metric is to ensure that the ERCOT telemetry system is stable in a redundant state. |  |  |  |
| Criteria: The Readiness Team will verify that telemetry failover thresholds are met by ERCOT. Readiness will be achieved when the ERCOT has passed a simulated failover test. Server Fail Over <=5 Mines Com Link Failover <= 30 Seconds |  |  |  |
| Reporting Data Sources: EDS-1 Dashboard Report / ERCOT ICCP EMS Logs |  |  |  |
| References | TP: 5.4.1 (2)(k) | TNP: 3.10.7.4, 6.4.5(1) & 8.1.2 |  |

### N3 - Validate SE Performance and Accuracy

| Reported By: ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: EDS 2 – Release 3 complete |  |  |  |
| Metric Description: Validate State Estimator performance as the time to reach a valid solution and availability as the percent of time the SE is capable of reaching a solution within accuracy limits defined by TAC approved SE standard. |  |  |  |
| Background: The intent of this metric is to prove the State Estimator meets stated performance criteria for Cold Start and Tracking mode and maintains a sufficient level of availability so as to provide rapid response to changing system conditions. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that the solution time and availability of the state estimator each pass a threshold value. Monthly Convergence = 97% SE - Power Flow <= ¦3%¦ on 95% of Samples for Elements Identified as causing 80% of Congestion Cost for one month SE - Telemetry <= ¦3%¦ on 95% of Samples for Elements Identified as causing 80% of Congestion Cost for one month SE - Telemetry <= ¦2%¦ on 95% of Samples for 20 critical bus voltages for one month SE - Telemetry <= ¦10%¦ on 99.5% of all elements > 100kV |  |  |  |
| Reporting Data Sources: State Estimator Statistics from MIS Secure Area |  |  |  |
| References | TP: 5.4.2 (2) | TNP: 3.10.9.1, 3.10.9.2 & 8.2(2)(a)(vi) |  |

# Market Operations Metrics

### MO1 - Operate DA Market for 7 Days

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Full Nodal Functionality 24*7 Operations plus 60 days |  |  |  |
| Metric Description: ERCOT shall facilitate a 168 hour test of the DAM. The test will verify the function of supporting systems and the ability of market participants to successfully participate in the test resulting in a DA Market solution and the generation of Settlement Determinants. |  |  |  |
| Background: The intent of this metric is to develop confidence in the ability for the DAM to solve. |  |  |  |
| Criteria: The Readiness Team will verify that the DAM Solves, Settlement Determinants are created and adequate load is represented in the test to represent a functioning market. The Readiness Team will evaluate the success of the DAM 168 test by reviewing DAM Daily Scorecard for compliance to the success thresholds. DAM Market Solves = 100% Settlement Determinants Generated = 100% Load of DAM Participants >= 50% Missing (critical) Settlement Determinants = 0 |  |  |  |
| Reporting Data Sources: DAM Daily Scorecard Comprised of: 1. DAM Market Solution Timestamp; 2. Missing Settlement Determinant Inventory Time stamped 3. Load of DAM Participants |  |  |  |
| References | TP: 5.4.6 (3), ^.1(h) | TNP: |  |

### MO2 - Operate 7 Day market with RUC

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Full Nodal Functionality 24*7 Operations plus 60 days |  |  |  |
| Metric Description: ERCOT shall operate RUC in parallel with DAM per the Transition Plan 5.4.7(1) and have the capability of running multiple RUCs simultaneously and provide the appropriate Settlement Bill Determinants.. |  |  |  |
| Background: The intent of this metric is to prove the ability to process the RUC under multiple scenarios. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that the RUC Process runs successfully in parallel with the DA Market and multiple RUCs can run in the same time frame. Readiness will be met when it is determined that a RUC Process can be run while the DAM is solving. Both RUC and DAM must solve. Readiness will be met when it is determined that a multiple RUC scenarios can be run simultaneously. All RUC scenarios must solve. All appropriate Settlement Bill Determinants are generated accurately. RUC Start > DAM Start and RUC End < DAM End RUC1 Start=RUC2 Start=RUC3 Start Missing (critical) Settlement Determinants = 0 |  |  |  |
| Reporting Data Sources: DAM and RUC Job Timestamps from Job Scheduler / RUC 1,2,3 Timestamps from Job Scheduler |  |  |  |
| References | TP: 6.1(d) | TNP: 5 |  |

### MO3 - Verify Supplemental Ancillary Services Market (SASM)

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Full Nodal Functionality 24*7 Operations |  |  |  |
| Metric Description: ERCOT shall test Supplemental Ancillary Services Market Functionality and Procedures. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT can procure additional ancillary services to meet regulation and responsive reserve requirements during the operating day and to ensure that they are within a band of adequacy. |  |  |  |
| Criteria: The Readiness Team will review MMS data indicating that supplemental ancillary services are defined by the output of the real time market. Readiness will be met when the RT ancillary services requirement is defined and within 10% of the zonal ancillary services requirement. RT Nodal Calculated Regulation Service +/- 10% of RT Zonal Calculated Regular Service RT Nodal Calculated Responsive Reserve Service +/- 10% of Zonal Calculated Responsive Reserve Service RT Nodal Calculated Non Spinning Reserve Service +/- 10% of RT Zonal Calculated Non Spinning Reserve Service |  |  |  |
| Reporting Data Sources: Nodal MMS Data Extract of RT / Zonal MMS Data Extract of RT |  |  |  |
| References | TP: 5.4.14 | TNP: 6.4.8.2 – 6.4.8.2.3 |  |

### MO4 - Verify Base Point Generation

| Reported By: ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: 6 Month LMP Posting plus 14 days |  |  |  |
| Metric Description: ERCOT will calculate resource base points and generate reasonable LMPs from the correct operation of SCED using offer curves and constraints to determine the most economical targets for individual resources. |  |  |  |
| Background: The intent of this metric is to ensure that the SCED generates appropriate signals to resources in response to market conditions. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies generation of SCED base points. Readiness will be met when the next megawatt of load is supplied by the marginal resource on an unconstrained system. Sum of Base Points = Forecast Load of next dispatch interval Reasonable LMP = Offer of the Marginal Resource at the Marginal Resource Location |  |  |  |
| Reporting Data Sources: Forecast Load / Sum of Base Points / LMPs / Offers of Marginal Resource |  |  |  |
| References | TP: 6.1(c.) | TNP: 6.5.7.1.12, 6.5.7.1.13 |  |

### MO5 - Generate LMPs for 6 months

| Reported By: ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: Test 1 - 6 Month LMP Posting minus 90 days Test 2 - 6 Month LMP Posting minus 30 days First - 6 Month LMP Posting plus 14 days Second- 6 Month LMP Posting plus 45 days Third- 6 Month LMP Posting plus 90 days Fourth - 6 Month LMP Posting plus 135 days Fifth – 6 Month LMP Posting plus 180 days |  |  |  |
| Metric Description: Generate LMPs for a six month period. The six month period commences on ERCOT declaring LMPs to be reasonable. LMPs should be calculated daily for each node and posted for Market Participant Access. |  |  |  |
| Background: The intent of this metric is to allow Market Participants and ERCOT to develop experience in the trending, magnitudes and timing of Locational Marginal, Hub, and Zone Prices. |  |  |  |
| Criteria: The Readiness Team will review Publicly posted documentation that demonstrates that ERCOT has generated reasonable Nodal LMPs on a daily basis for a period of six months. Readiness will be met when LMPs are produced and posted at regular intervals during the 6-month LMP posting period during EDS 3. Number of LMPs Calculated per Day / Number of Nodes >=95% of Number of Intervals (.95 * 288) Metric Calculation 1 >=95% of Number of Intervals (.95 * 288) for 180 Consecutive Days Consecutive Non Solves per day <=10 |  |  |  |
| Reporting Data Sources: EDS 3 Reporting (Extract from LMP results Database) |  |  |  |
| References | TP: 5.1(4) | TNP: N/A |  |

### MO6 - Verify DAM Ancillary Services

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Full Nodal Functionality 24*7 Operations plus 60 days |  |  |  |
| Metric Description: ERCOT will during the 168 hour test use DAM to procure adequate ancillary services utilizing test offers from Market Participants |  |  |  |
| Background: The intent of this metric is to ensure that the Nodal Market System can meet regulation and responsive reserve requirements for the operating day governed by the Day Ahead Market and to ensure that they are within a band of adequacy. Also, all appropriate Settlement Bill Determinants are generated accurately. |  |  |  |
| Criteria: The Readiness Team will review MMS data indicating that ancillary services are defined by the output of the Day Ahead Market. Readiness will be met when the DAM ancillary services requirement is defined and within 10% of the zonal ancillary services requirement. DA Nodal Calculated Regulation Service +/- 10% of the RT Operating Requirements DA Nodal Calculated Responsive Reserve Service +/- 10% of RT Operating Requirements DA Nodal Calculated Non Spinning Reserve Service +/- 10% of RT Operating Requirements Missing (critical) Settlement Determinants = 0 |  |  |  |
| Reporting Data Sources: Nodal MMS Data Extract of DAM / Nodal MMS Data Extract of RT |  |  |  |
| References | TP: 6.1 (b) - 5.4.6 (2) | TNP: 3.16, 3.17, 3.18 |  |

# Contingency Metrics

### C1 - Contingency Plan for Weekly, Daily and Hourly RUC Failure

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test a Contingency Plan for RUC Failure. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to execute Unit Commitment when the primary RUC system is not available. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence and test of a contingency plan document for RUC failure. Readiness will be achieved when the RUC Contingency has been successfully tested. RUC Contingency Plan Exists RUC Contingency Plan Successfully Executed |  |  |  |
| Reporting Data Sources: RUC Contingency Plan / RUC Contingency Plan Test Log / / |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C2 - Contingency Plan for DAM / LMP Failure

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test a Contingency Plan for DAM / LMP Failure. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to execute Unit Commitment and generate LMPs in the day ahead when the primary system is not available. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence of a contingency plan document for DAM / LMP failure. Readiness will be achieved when the DAM / LMP Contingency has been successfully tested. DAM / LMP Contingency Plan Exists DAM / LMP Contingency Plan Successfully Executed |  |  |  |
| Reporting Data Sources: DAM LMP Contingency Plan / DAM / LMP Contingency Plan Test Log |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C3 - Contingency Plan for ICCP Data Failure

| Reported By: ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test a Contingency Plan for ICCP Data Failure. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to operate the nodal market during the loss of ICCP links. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence of a contingency plan document for ICCP failure. Readiness will be achieved when the ICCP Contingency has been successfully tested. ICCP Contingency Plan Exists ICCP Contingency Plan Successfully Executed |  |  |  |
| Reporting Data Sources: ICCP Contingency Plan / ICCP Contingency Plan Test Log / / |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C4 - Contingency Plan for SCED Failure

| Reported By: ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test a Contingency Plan for SCED/LMP Failure. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to control generation and generate LMPs in the real time when the SCED system is not available. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence and test of a contingency plan document for SCED/LMP failure. Readiness will be achieved when the SCED/LMP Contingency has been successfully tested. SCED/LMP Contingency Plan Exists SCED/LMP Contingency Plan Successfully Executed |  |  |  |
| Reporting Data Sources: SCED/LMP Contingency Plan / SCED/LMP Contingency Plan Test Log / / |  |  |  |
| References | TP: N/A | TNP: 6.5.9.2 |  |

### C5 - Contingency Plans for Key Settlement and Financial Transfer Processes

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test a Contingency Plan for the various Settlement and Financial processes that must be performed in order to settle the market in a timely manner. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has tested contingency plans in place to overcome (in a timely manner) failures of key components of the Settlement and Billing System and Financial Transfer System. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence and test of a contingency plan document for Settlement and Financial processes. Readiness will be achieved when the Settlement and Financial processes Contingency has been successfully tested. Settlement and Financial processes Contingency Plan Exists Settlement and Financial processes Contingency Plan Successfully Executed |  |  |  |
| Reporting Data Sources: Settlement and Financial processes Contingency Plan / Settlement and Financial processes Contingency Plan Test Log / / |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C6 - Develop Plan for SE Failure

| Reported By: ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test a Contingency Plan for SE Failure. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to maintain system reliability when the SE system is not available. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence of a contingency plan document for SE failure. Readiness will be achieved when the SE Contingency has been successfully tested. SE Contingency Plan Exists SE Contingency Plan Successfully Executed |  |  |  |
| Reporting Data Sources: SE Contingency Plan / SE Contingency Plan Test Log / / |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C7 - Contingency Plan for a Backup Facility

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop a Contingency Plan for a Loss of the Primary Control Room. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to maintain control of the system when the Primary Control Room becomes unavailable. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence of a contingency plan document for the Primary Control Room. Readiness will be achieved when the Primary Control Room Contingency has been successfully tested. Primary Control Room Contingency Plan Exists Primary Control Room Contingency Plan Successfully Executed |  |  |  |
| Reporting Data Sources: Primary Control Room Contingency Plan / Primary Control Room Contingency Plan Test Log / / |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C8 - Contingency Plan for Portal/API Failure

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop a Contingency Plan for a Portal/API Failure. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to receive data from market participants when the API / Portal becomes unavailable. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence of a contingency plan document for a API / Portal Failure. Readiness will be achieved when the API / Portal Contingency has been successfully tested. API / Portal Contingency Plan Exists API / Portal Contingency Plan Successfully Executed |  |  |  |
| Reporting Data Sources: API/Portal Contingency Plan / API/Portal Contingency Plan Test Log / / |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C9 - Contingency Plan for Site Unavailability

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test a contingency plan for the event of normal site unavailability. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to facilitate the Nodal Market from the backup site. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence of a contingency plan document for normal site unavailability. Readiness will be achieved when the normal site unavailability Contingency has been successfully tested. Normal site unavailability Contingency Plan Exists Normal site unavailability Contingency Plan Successfully Executed |  |  |  |
| Reporting Data Sources: Normal Site Unavailability Contingency Plan / Normal Site Unavailability Contingency Plan Test Log / / |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C10 - Verify Single Point of Failure Recovery EMS/MMS/NMMS/CRR/COMS

| Reported By: ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall test that a recovery to full functionality occurs for a single point of failure in EMS, MMS, NMMS and CRR and COMS applications. |  |  |  |
| Background: The intent of this metric is to ensure that systems functionality is not lost due to any single point of failure. |  |  |  |
| Criteria: The Readiness Team shall review documentation that ERCOT tested that a continuation of full functionality occurred during any single point of failure in EMS, MMS, NMMS and CRR and COMS applications. Readiness will be achieved when the Single Point of Failure test has been successfully executed. Single Point of Failure Test Plan Exists Single Point of Failure Test Plan Successfully Executed |  |  |  |
| Reporting Data Sources: Single Point of Failure Test Plan / Single Point of Failure Test Log / / |  |  |  |
| References | TP: N/A | TNP: N/A |  |

# IMM Metrics

### IMM1 - Market Monitor Systems Capability

| Reported By: WEMM |  |  | EDS: N/A |
| --- | --- | --- | --- |
| Target Completion: EDS 4 – Release 9 Complete |  |  |  |
| Metric Description: Verify Market Monitor Systems Capability. |  |  |  |
| Background: The intent of this metric is to validate that the PUC and the Wholesale Electric Market Monitor (WEMM) can access all data deemed necessary by the PUCT staff and WEMM to perform their market oversite activities. |  |  |  |
| Criteria: The Readiness Team will receive notification from the WEMM that Market Monitor has sufficient staff, systems and access to data to successfully monitor the market. Readiness will be achieved when the Readiness Team receives notification that the Market Monitor is capable of fulfilling its intended purpose. Market Monitor Asserts Readiness |  |  |  |
| Reporting Data Sources: Letter of Assurance from the Market Monitor |  |  |  |
| References | TP: N/A | TNP: 17.3 |  |

# Overall Readiness Metrics

### R1 - Nodal Readiness Declaration

| Reported By: ERCOT |  |  | EDS: N/A |
| --- | --- | --- | --- |
| Target Completion: Go Live less 30 days |  |  |  |
| Metric Description: ERCOT Declares the Texas Nodal Readiness State by assessing Program, ERCOT and Market Participant Readiness. |  |  |  |
| Background: The intent of this metric is to provide ERCOT stakeholders with a comprehensive statement of Market Readiness. |  |  |  |
| Criteria: ERCOT will confirm the state of Program Readiness through the PMO dashboard. ERCOT will confirm the state of ERCOT Readiness through assessment of the ERCOT related metrics. ERCOT will confirm the state of Market Participant Readiness through assessment of the MP related metrics. Readiness will be achieved when PMO state has been reported and ERCOT and MP related metric assessments have been completed. ERCOT Asserts Readiness |  |  |  |
| Reporting Data Sources: PMO Dashboard / Readiness Metric Report |  |  |  |
| References | TP: 6.3 | TNP: N/A |  |

### R2 - Develop Texas Nodal Market Launch Plan

| Reported By: ERCOT |  |  | EDS: N/A |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 90 days |  |  |  |
| Metric Description: Develop Texas Nodal Market Launch Plan. |  |  |  |
| Background: The intent of this metric is to ensure that a comprehensive market launch plan exists. The plan will address the activities ERCOT and Market Participants must perform in order to launch the integrated nodal market. |  |  |  |
| Criteria: The Readiness Team will review documentation indicating that the Texas Nodal Market Launch plan has been created and approved by the TAC. Readiness will be achieved when a approved Texas Nodal Market Launch Plan has been published. Texas Nodal Market Launch Plan is Posted |  |  |  |
| Reporting Data Sources: TN Market Launch Plan |  |  |  |
| References | TP: N/A | TNP: N/A |  |