## Slide 1: Texas Nodal Program Update Market Readiness Metrics Model Update
Tim Pare
PMO

## Slide 2: Goals & Characteristics of Readiness Metrics
Goals of Readiness Metrics
  Encourage early participation
  Minimize delinquency
  Inform market of readiness declarations
  Motivational tool for the market as a whole
Characteristics of Metrics
  Easy to understand (unambiguous) – linked to Transition Plan where possible
  Easy to calculate (reliable) – simple roll-up and grading rules
  Easy to communicate – red, amber, green
  Incorporates Market Participant self reporting & ERCOT Observability
Timing of Metrics
  Progressive measurement through the readiness sequence
  Forwarding looking, including lead indicators

## Slide 3: Overall View of Nodal Readiness Metrics model
Top-level view
ERCOT Summary grading rules
EDS Summary grading rules
MP Summary grading rules
EDS
1
EDS
2
EDS
3
EDS
4
ERCOT Roll-up
MP Roll-up
Dept C
Dept B
Dept A
QR ABC Inc.
ERCOT Model roll-up
EDS Model roll-up
MP Model roll-up
ERCOT scorecard & grading rules
MP scorecard & grading rules
EDS-unique metrics
ERCOT Readiness
EDS Readiness
MP Readiness
Dept. A
Dept. B
Dept. C
Dept. D
Dept. E
Dept. F
QSE +R
QSE
TSP/DSP
LSE
CRR
Dept. A
Dept. B
Dept. C
Dept. D
Dept. E
Dept. F
QSE +R
QSE
TSP/DSP
LSE
CRR
Metrics inventory (self-reported and ERCOT-observable metrics)
Reported to:
Nodal Steering Board
ERCOT managers
Reported to:
Nodal Steering Board
TPTF
TAC
BOD
Reported to:
Accountable Executives
1
2
3
6
5
7
4
5

## Slide 4: Top-level view of Readiness
Nodal Readiness – Top-Level View
ERCOT Readiness
EDS Readiness
Market Participant Readiness
Day-Ahead Administration
Price Verification
Congestion Management
Operations Planning & Analysis
Outage Coordination
Operations Support Engineering
Network Modelling
Dedicated Testing
Dedicated Training
Client Relations
QSE +R
QSE
TSP/DSP
LSE
CRR
The top-level gives a one-page view of where attention needs to be directed across all areas of market readiness
It will enable Nodal management and external stakeholders to have an up-to-date view of market readiness, in line with the program’s view of overall success
1

## Slide 5: Market Participant Self-Reporting Questionnaire – target deployment 6/1/2007
A self-reporting questionnaire will be released to Accountable Executives (Authorized Representative in absence of AE)
Initial focus:
  TSPs
  QSEs with Resources
  QSEs without Resources
The tool will enable MPs to attest to their level of readiness for the Nodal market
Overall readiness will be assessed by self-reporting and ERCOT observable metrics
Self-reporting questionnaire mock-up
2

## Slide 6: Questionnaire responses will inform separate metrics
Initiation status
Mobilization status
Delivery status
Metric grading rules:
  Report cycle 1 (June): Any "No" responses = Amber, else Green (no Red)
  Report cycle 2 (July) and beyond: Any "No" responses = Red, else Green (no Amber)
Metric grading rules:
  Report cycle 1 & 2 (June): Any "No" responses = Amber, else Green (no Red)
  Report cycle 3 (August) and beyond: Any "No" responses = Red, else Green (no Amber)
Metric grading rules:
  If Registration, Qualification OR Systems Available question is "No" = Red
  If all questions are "Yes" = Green
  All other permutations = Amber
2

## Slide 7: Self-reported and ERCOT-observable metrics will be combined into individual Market Participant and ERCOT departmental scorecards
Individual Market Readiness Scorecard
Self-reported metrics ERCOT Observable metrics
Initiation status
Mobilization status
Delivery status
Connectivity to Test Environment
Upload SCED offers to EDS
MP Test Digital Certificates Obtained
Overall readiness status:
Scorecard grading rules:
  Red – if any component is red
  Green – if all components are green
  Amber – all other permutations
2

## Slide 8: The first level of roll-up will provide aggregations of each metric by market participant role
Roll-up model:
  The roll-up will present a summarized view of MP readiness metrics by group (role)
  RAG (Red, Amber, Green) status will be determined by weighting each MP’s results by the % contribution (system generation, load, ancillary services) made to the Texas market for their role. Targets by role are:
    100% for QSEs with Resources and TSPs
    95% for other market participant types
3

## Slide 9: ERCOT roll-up will focus on the most affected departments
Market Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
Department Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
Market Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
Department Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
Market Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
Department Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
Market Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
Department Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
Market Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
Department Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
4
Roll-up model:
  The roll-up will present a summarized view of ERCOT readiness metrics by department.
  RAG status will reflect the ability of each department to hit readiness goals related to Training, Procedure Development, and Organization Design by the appropriate project milestones (typically correlated to EDS phases.)

## Slide 10: The top-level roll-up will provide a single summary for each market participant role and key ERCOT department
Overall readiness grading rules:
  Red – if any component is red
  Green – if all components are green
  Amber – all other permutations
ERCOT Readiness
Dept. A
Dept. B
Dept. C
Dept. D
Dept. E
Dept. F
MP Readiness
QSE +R
QSE
TDSP
LSE
CRR
5

## Slide 11: EDS Metric deployment dependent upon Early Delivery System Sequence Timeline
EDS metric grading rules:
  Not Measured – Metric not yet deployed
    White = Metric criteria is not evaluated
  In Measurement – under preliminary measurement
    Amber = Metric criteria is not met
    Green = Metric criteria is met
  Measured – under measurement
    Red = Metric criteria is not met
    Green = Metric criteria is met
Dept C
Dept B
Dept A
QR ABC Inc.
EDS-unique metrics
6

## Slide 12: Progressive measurement provides a temporal view of market readiness
EDS Readiness
Overall EDS readiness grading rules:
  Red – if any deployed component is red
  Green – if all deployed components are green
  Amber – all other permutations of deployed component metrics
  White – Metrics not yet deployed
7

## Slide 13: Next steps in Market Readiness – through 2007
MP Self Reporting deployment
  Distribution to respondents 6/1
  Target response 6/30
  Bi-monthly/quarterly thereafter (TBC)
ERCOT Departmental reporting deployment
  Organization Design beginning June 1st
  Internal procedures beginning August 1st
  Nodal Operating Guides beginning December 1st
  Training beginning October 1st
ERCOT-observable metrics deployment
  EDS 1 (ERCOT only) beginning June 1st
  EDS 2 beginning June 15th
  EDS 3 beginning November 1st
Reporting initiation
  July TPTF and TAC meetings