## Sheet1
TPTF Document Activity Matrix - The purpose of this spreadsheet is to show the status of documents and to help plan for upcoming reviews of documents. The most up-to-date version of this spreadsheet is posted the day before each TPTF meeting. Last Updated: May 4, 2007
Project | Requirements Documents | Approved | Current Status | Design Documents | Approved | Current Status | Other Deliverables | TPTF Action Taken | Current Status
PMO | [6 empty] | Nodal Transition Plan |  | Scheduled for review and a possible vote on May 23rd.
[7 empty] | Section 5.4.10 of Nodal Transistion Plan |  | Section 5.4.10 of the Nodal Transition Plan reviewed again next meeting, on May 21st. The rest of the Transition plan was approved at the 050707 TPTF meeting with the exclusion of this section, which still requires approval pending the development of an ERCOT plan for limiting Transmission Element Outages.
Integration and Design Authority (IDA) | [6 empty] | SoSA for Commercial Systems v1.0 | 2006-11-07
[7 empty] | SoSA for Market Information Systems v1.0 | 2006-11-07
[7 empty] | SoSA for Market Operations v1.0 | 2006-11-07
[7 empty] | SoSA for System Operations v1.0 | 2006-11-07
[7 empty] | Machine-to-Machine Interfaces Specification (Final) v0.95 |  | Review and possible vote TPTF May 21, 2007
[7 empty] | White Paper - Combined Cycle |  | Comments Due May 15 , Reviw May 23 TPTF
[7 empty] | White Paper - Joint Owned Unit Modeling |  | Comments Due May 15 - Review TPTF May 23 TPTF
Network Modeling Management System (NMMS) | NMMS Requirements Appendix v1.0 | 2006-03-01 |  | NMMS CSD v1.0 | 2007-01-24 |  | Transition NMT to Operations |  | Review at TPTF post 3/31/07
| NMMS Requirements v1.0 | 2006-03-01 |  | NMMS Detailed Design |  | 2007-06-01
Market Management System (MMS) | MMS SCED Business Requirements | 2007-01-10 |  | MMS CSD | 2007-01-24 |  | White Paper - AS Sched. and Deployment Telemetry | 2006-12-11
| Overall MMS Business Requirements | 2007-01-10 |  | Outage Scheduler CSD v0.06 | Approved 4/23/07 |  | White Paper - Base Point Above HASL Flags | 2006-12-11
| MMS RUC Business Requirements | 2007-01-10 |  | Asset Registration System CSD |  | TBD | White Paper - Coincidental Deployment of Up and Down Reg | 2006-12-11
| MMS DAM and SASM Business Requirements | 2007-01-15 |  | MMS Detailed Design |  | TBD | White Paper - Emergency Basepoint Calculation and Deployment | 2006-12-11
| MMS Constraint Competitive Test Business Requirements | 2007-01-15 |  | Outage Scheduler Detailed Design |  | TBD | White Paper - Generation Resource Responsive Reserve Deployment and Recall | 2007-01-03
| Requirements Specification for Outage Scheduler 1.1 | 2007-04-24 |  |  |  |  | White Paper - HDL and LDL During Start-up and AS Recall | 2006-12-11
[7 empty] | White Paper - Non-Spin Deployment Notification and Availability | 2007-01-03
[7 empty] | White Paper - SCED Base Point Dispatch | 2007-01-03
[7 empty] | White Paper - Remedial Switching Action | 2007-02-23
Energy Management System (EMS) | Data Models Requirements Specification v1.0 | 2006-03-01 |  | EMS CSD | TPTF provisionally approved the EMS CSD, v0.11. (May 7-8) |  | White Paper - AS Sched. and Deployment Telemetry | 2006-12-11
| Dynamic Ratings Requirements Specification v1.0 | 2006-03-01 |  | Wind Power Forecasting CSD |  | TPTF received updates on May 7-8 - review and possible vote TPTF May 22 | White Paper - Base Point Above HASL Flags | 2006-12-11
| Energy Management System Requirements Specification v1.0 | 2006-03-01 |  | EMS Detailed Design |  | TBD | White Paper - Coincidental Deployment of Up and Down Reg | 2006-12-11
| Forced Outage Detection Requirements Specification v1.0 | 2006-03-01 |  |  |  |  | White Paper - Emergency Basepoint Calculation and Deployment | 2006-12-11
| Generation Subsystem Requirements Specification v1.0 | 2007-02-28 |  |  |  |  | White Paper - Generation Resource Responsive Reserve Deployment and Recall | 2007-01-03
| Load Forecasting Requirements Specification v1.0 | 2006-03-01 |  |  |  |  | White Paper - HDL and LDL During Start-up and AS Recall | 2006-12-11
| Network Security and Stability Analysis Requirements Specification v1.0 | 2006-03-01 |  |  |  |  | White Paper - Non-Spin Deployment Notification and Availability | 2007-01-03
| Outage Evaluation Requirements Specification v1.0 | 2006-03-01 |  |  |  |  | White Paper - SCED Base Point Dispatch | 2007-01-03
| SCADA Requirements Specification v1.0 | 2007-02-28
| State Estimator Requirements Specification v1.0 | 2006-03-01
| Voltage Support Requirements Specification v1.0 | 2006-03-01
| Wind Power Forecasting Requirements Specification v1.0 | 2006-03-01
Congestion Revenue Rights (CRR) | Congestion Revenue Rights Business Requirements | 2006-10-10 |  | CRR Conceptual System Design | 2006-11-29
|  |  |  | Detail Design - Data Interface, Volume 1 |  | Pending Distribution
|  |  |  | Detail Design - Market User Interface (MUI), Volume 1 |  | Pending Distribution
|  |  |  | Detail Design - Calculation, Volume 1 |  | Pending Distribution
Commercial Systems (COMS) Includes: Settlements, Credit Monitoring, Disputes, Financial Transfer, Registration | Average Incremental Energy Cost (AIEC) Business Requirements | 2006-11-07 |  | AIEC CSD | 2007-01-24
| Real-Time Black-Start Settlement Business Requirements | 2006-09-29 |  | CRR Settlements CSD | 2007-01-24
| Credit Monitoring Business Requirements | 2006-10-25 |  | Credit Monitoring and Management System CSD | 2007-01-09
| CRR Auction Settlements and Revenue Disbursement | 2006-10-10 |  | Data Aggregation CSD | 2007-01-24
| CRR Balancing Account Settlement Business Reqts | 2006-10-10 |  | DAM Settlements CSD | 2007-01-24
| DAM AS Settlement Business Requirements | 2006-07-25 |  | Eligibility CSD | 2007-01-24
| DAM CRR Settlement Business Requirements | 2006-09-29 |  | Financial Transfer CSD | 2007-01-24
| DAM Energy Settlement Business Requirements | 2006-07-25 |  | Real-Time Settlements CSD | 2007-01-24
| DAM Make Whole Settlement Business Requirements | 2006-08-22 |  | RUC CSD | 2007-01-24
| Data Aggregation Business Requirements | 2006-11-07 |  | Statements and Invoices CSD | 2007-01-24
| Dispute Management Business Requirements | 2006-11-30 |  | Disputes CSD | 2007-01-24
| Eligibility Process for Settlements Business Requirements | 2006-11-30 |  | MP Registration System CSD | 2007-02-22
| Financial Transfer Settlements Business Requirements | 2006-10-25 |  | Credit Monitoring and Management System Detailed Design |  | April, 07
| Market Data Transparency (“Extracts”) Business Requirements | 2006-11-07 |  | Registration System Detailed Design |  | April, 07
| Real-Time AS Settlement Business Requirements | 2006-08-22 |  | Financial Transfer Detailed Design |  | May, 07
| Real-Time CRR Settlements Business Requirements | 2006-10-10 |  | COMS Settlements and Billing Detailed Design |  | June, 07
| Real-Time Emergency Operations Settlement Business Reqts | 2006-09-29 |  | Disputes Detailed Design |  | Sept., 07
| Real-Time Energy Settlements Business Requirements | 2006-09-29 |  | Settlements AIEC Conceptual System Design v1.1 |  | In review - Comments Due May 15
| Registration Business Requirements - | 2007-01-09 |  | Settlements CRR Conceptual System Design v1.1 |  | In review - Comments Due May 15
| RMR Settlements Business Requirements | 2006-10-10 |  | Settlements Day Ahead Conceptual System Design v1.1 |  | In review - Comments Due May 15
| RUC Settlement Business Requirements | 2006-08-22 |  | Settlements Eligibility Process Conceptual System Design v1.1 |  | In review - Comments Due June 4
| Settlement Invoice Business Requirements | 2006-10-25 |  | Financial Transfer Conceptual System Design v1.1 |  | In review - Comments Due June 4
| Settlement Statement Business Requirements | 2006-10-25 |  | Reliability Unit Commitment Conceptual System Design v1.1 |  | In review - Comments Due June 4
| Verifiable Costs Business Requirements | 2006-11-07 |  | Invoices Conceptual System Design v1.1 |  | In review - Comments Due June 4
| Miscellaneous Requirements v0.091 |  | Constantly under review by COPS will not go back to TPTF | Statements Conceptual System Design v1.1 |  | In review - Comments Due June 4
| Interface Requirements v0.10 |  | Constantly under review by COPS will not go back to TPTF | Registration System Conceptual Sustm Design v1.1 |  | In review - Comments Due June 4
| Real-Time Voltage Support Settlement Business Reqts | 2006-09-29
| AIEC Requirements v1.1 |  | To be voted on in TPTF May 23
| Black Start Services Real-Time Settlements v1.1 |  | To be voted on in TPTF May 23
| DAM AS Settlements Requirements v1.1 |  | To be voted on in TPTF May 23
| DAM Energy Settlements Requirements v1.1 |  | To be voted on in TPTF May 23
| DAM Make-Whole Settlements Requirements v1.1 |  | To be voted on in TPTF May 23
| Financial Transfer Requirements v1.1 |  | To be voted on in TPTF May 23
| Real-Time AS Settlements Requirements v1.1 |  | To be voted on in TPTF May 23
| Real-Time Emergency Ops Settlements Requirements v1.1 |  | To be voted on in TPTF May 23
| Real-Time Energy Requirements v1.1 |  | To be voted on in TPTF May 23
| Registration Requirements v1.1 |  | To be voted on in TPTF May 23
| RMR Services Real-Time Settlements Requirements v1.1 |  | To be voted on in TPTF May 23
| RUC Settlements Requirements v1.1 |  | To be voted on in TPTF May 23
| Settlements Invoice Requirements v1.1 |  | To be voted on in TPTF May 23
| Settlement Statement Requirements v1.1 |  | To be voted on in TPTF May 23
| Startup Eligibility Requirements v1.1 |  | To be voted on in TPTF May 23
| Voltage Support Real-Time Settlements Requirements v1.1 |  | To be voted on in TPTF May 23
| CRR Auction Revenue Disbursement Settlements Requirements v1.1 |  | In review - Comments Due June 4
| CRR Balancing Account Settlements Requirements v1.1 |  | In review - Comments Due June 4
| DAM CRR Settlement Requirements v1.1 |  | In review - Comments Due June 4
| Data Aggregation Requirements v1.1 |  | In review - Comments Due June 4
| Real-Time CRR Settlements Requirements v1.1 |  | In review - Comments Due June 4
| Disputes v1.1 – only after COPs has solidified changes to section 9 |  | – only after COPs has solidified changes to section 9
| CMM Requirements v1.1 |  | May 2007 based on revised detailed design, NPRR review
| Verifiable Cost Requirements |  | – May 2007
Market Engagement and Readiness (MER) Includes: Training and MIS | MIS Web Portal Requirements | 2006-10-11 |  | MIS Portal Conceptual System Design | 2007-01-10 |  | Nodal Training Course Curriculum Descriptions v2.0 | 2006-06-27
|  |  |  | MIS Detailed Design |  | 2007-04-01 | Nodal Training Audience Matrix v1.0 | 2006-06-27
[7 empty] | Market Participant Readiness Activity Matrix 1.0 | 6/?/2006
[7 empty] | Market Participant Training Readiness | 2006-11-06
[7 empty] | MIS Prototype 1 v2.0 | 2007-03-01
[7 empty] | MIS Prototype 2 v1.0 | 2007-03-01
[7 empty] | MIS Prototype 3 v1.0 |  | TBD
ERCOT Integrated Readiness and Transition (IRT) | none required |  |  | none required |  |  | Sandbox Overview v1.2 | 2007-01-31
[7 empty] | Java - Who Am I Web Service Client Package v1.0 | 2007-01-30
[7 empty] | .Net Who Am I Web Service Client Package v1.0 | 2007-03-05
[7 empty] | Java - Boomerang Web Service Client Package v1.0 | 2007-02-21
[7 empty] | .Net - Boomerang Web Service Client Package v1.0 | 2007-02-21
[7 empty] | Market Trials Approach v0.09 | 2007-02-05
[7 empty] | Qualification Approach for the Nodal Market v0.72 | 2007-02-05
[7 empty] | Three Part Offer POC v1.0 | 2007-03-23
[7 empty] | Metric Readiness Inventory |  | Reviewed at the upcoming meeting on May 23rd
[7 empty] | Service Level Agreement v0.91 - Nodal Sandbox Environment for Market Interface Testing | 2007-05-07
[7 empty] | Registration Approach v1.0 | 2007-04-02
[7 empty] | Readiness Criteria |  | Presented to TPTF Mar. 22 - Comments Received March 13
[7 empty] | MP Qualification and Qualification Guide v0.4 |  | Comments Due May 10, Review TPTF May 21-31
[7 empty] | ICCP Communication Handbook v0.21 |  | Review at TPTF May 22 possible approval
[7 empty] | EDS1 Approach v1 | 2007-03-22
[7 empty] | EDS2 Approach v.91 |  | Review begins the week of May 7. Review and possible vote at TPTF Mtg May 21-23
[7 empty] | EDS3 Detailed Plan (Approach) |  | Review at TPTF May 22 TPTF
[7 empty] | EDS4 Detailed Plan |  | Available May - July
[7 empty] | EDS3 Handbook |  | Available July
[7 empty] | EDS4 HandbookDetailed Plan |  | Available Sept
Infrastructure (INF) | none required |  |  | none required
Enterprise Data Warehouse (EDW) | Market Monitoring and Data Collection Requirements (Section 17) v1.0 | 2007-04-23 | In review - Comments Due April 20 | EDW Conceptual System Design v0.06 | Review TBD
| Performance Monitoring and Compliance Business Requirements (Section 8) |  | Review TBD
Integrated Testing (INT) | none required |  |  | none required
Nodal Program Office (NPO) | [6 empty] | Proposed Additions to TPTF Charter (with comments from TXU, Reliant, LCRA) TPTF Mtg (.doc |  | Scheduled to be discussed at May 7-8
[7 empty] | Proposed Revisions to the Nodal Transition Plan (with comments from ERCOT, LCRA) (. |  | Scheduled to be discussed at May 7-8
Currently in review (approval required) (red)
Currently in review (approval not required) (light red)
Approved (dark green)
Concurred (approval not applicable) (light green)
To be reviewed in future (approval required) (dark blue)
To be reviewed in future (approval not required) (light blue)
Color Legend