Texas Set Version 3.0

Implementation and Contingency Plan

DRAFT

V3.0 Market Coordination Team

Version 1.1

Revision History

| Date | Version | Description |
| --- | --- | --- |
| 04.12.2007 | 1.0 | First draft |
| 05.17.2007 | 1.1 | Additional Modifications for MCT 05/24 MCT meeting |

Table of Contents

Version 3.0 Implementation Schedule	4

ERCOT Contingency Plan	6

TDSP Contingency Plan	7

3.0 Transactions received by the TDSP	7

2.1 Transactions sent by the TDSP	7

CR Contingency Plan	9

3.0 Transactions received by the CR	9

2.1 Transactions sent by the CR	10

Additional Contingencies	10

# Version 3.0 Implementation Schedule

The following table provides an overview of the weekend schedule for the Texas SET Version 3.0 Implementation Plan.  These times were pulled from the implementation plan developed by the Texas SET Market Coordination Team.

Conference Call Number:  800-211-0633

Password:  844736

Press ‘6’ to mute/un-mute phone

| Tuesday, June 19, 2007 |  |  |  |
| --- | --- | --- | --- |
| Time | Task | Entity | Complete (Y or N) |
| 8:00 AM | CRs suspend sending 650_01 DNP Transactions - Pending DNPs will continue to be worked according to the DNP procedures | All CRs |  |
| Wednesday, June 20, 2007 |  |  |  |
| Time | Task | Entity |  |
| 5:00 PM | TDSPs (except ONCOR) will flush systems to cancel all pending 650 DNPs and send complete unexecutables to CRs | All TDSPs |  |
| Thursday, June 21, 2007 |  |  |  |
| Time | Task | Entity |  |
| 4:00 PM | 1st Market Conference Call - Confirm DNPs are suspended | All MPs |  |
| 5:00 PM | ONCOR will flush systems to cancel all pending 650 DNPs and send complete unexecutables to CRs | All TDSPs |  |
| Friday, June 22, 2007 |  |  |  |
| Time | Task | Entity |  |
| 12:00 PM | CRs suspend sending 814 transactions to ERCOT (both EDI and through TML) | All CRs |  |
|  | CRs begin using Safety Net process for submitting MVIs with a requested date of June 23 through June 26 | All CRs |  |
|  | ERCOT shuts down inbound processing of initiating transactions. Inbound response transactions will continue to be processed. ERCOT will continue to process outbound. | ERCOT |  |
|  | CRs suspend 814_PC transactions | All CRs |  |
|  | CRs suspend 650_01 transactions | All CRs |  |
|  | TDSPs suspend 650_04 transactions | All TDSPs |  |
|  | 997s sent for 810_02/03, 650_01/04, and 814_PC transactions | All MPs |  |
|  | TDSPs suspend 814_20 transactions | All TDSPs |  |
| Friday, June 22, 2007 |  |  |  |
| Time | Task | Entity |  |
| 1:00 PM | TDSPs suspend 867s and 814 responses | All TDSPs |  |
|  | CRs suspend 824 transactions | All CRs |  |
|  | TDSPs suspend 814_PD transactions | All TDSPs |  |
|  | TDSPs suspend 650_02 transactions | All TDSPs |  |
|  | CRs suspend 650_05 transactions | All CRs |  |
|  | 2nd MCC - ERCOT confirmation of transaction suspension. Update on transaction processing | All MPs |  |
| 2:00 PM | 997s suspended for 650_02/05, 814_PD, 824 transactions | All MPs |  |
| 5:00 PM | TDSPs suspend 810_02 (820_03MC) transactions | All TDSPs |  |
|  | CRs suspend 820_02 (810_03MC) transactions | All CRs |  |
|  | ERCOT Shuts down outbound processing | ERCOT |  |
|  | ERCOT sends out System Shutdown email to market | ERCOT |  |
| Saturday, June 23, 2007 |  |  |  |
| Time | Task | Entity |  |
| 6:00 PM | 3rd MCC - MP Migration Status - ERCOT Go/No Go Decision | All MPs |  |
| Sunday, June 24, 2007 |  |  |  |
| Time | Task | Entity |  |
| 10:00 AM | 4th MCC - MP Migration Status | All MPs |  |
| TBD | 5th MCC - Determine if additional CC necessary. Confirm Market Readiness. | All MPs |  |

# ERCOT Contingency Plan

Should ERCOT fail to successfully implement Texas SET Version 3.0 the Market will be notified on Saturday, June 23rd  at the 6:00 PM Market Participant Conference Call.  At that time the Market and ERCOT will identify the timeframe necessary to get all Market Participant and ERCOT systems back to Version 2.1 in time for normal business processing on Monday, June 25th .

# TDSP Contingency Plan

Should a TDSP fail to successfully implement Texas SET Version 3.0 the Market will be notified on Saturday,  June 23rd  at the 6:00 PM Market Participant Conference Call for AEP, TNMP, CNP, Sharyland, ONCOR, and Nueces.  The TDSP will coordinate a weekend migration to minimize any potential impact to the rest of the Market.

Upon notification, the TDSP will initiate the following Contingency Plan:

### 3.0 Transactions received by the TDSP

The following is a list of transactions that have changed as a result of Version 3.0 and could possibly be rejected by Version 2.1 code.  The TDSP acknowledges that these transactions will not be rejected if received but worked manually until the TDSP can implement Texas SET Version 3.0.

| Transaction | Transaction Type | Overall Market Operations Risk |
| --- | --- | --- |
| 650_01 | TDSP will not reject any 650_01 sent with one of the new Premium Disconnect codes CC2006-691, 2006-698, 2006-700 | L |
| 810_03 | MOU/EC TDSP: CC2006-699 |  |
| 814_PC | CC2006-691 |  |
| 814_03 | MOU/EC TDSP will not reject any 814_03 sent with the Membership ID CC2006-692, 2006-704 | L |
| 814_08 | CC2006-692, 2006-694, 2006-703 |  |
| 814_12 | CC2006-694 |  |
| 814_18 | MOU/EC TDSP will not reject any 814_18 sent with the Membership ID CC2006-694 | L |
| 814_24 | TDSP will not reject any 814_24 with new 2MR code CC2006-694 | M |
| 814_24 | MOU/EC TDSP will not reject any 814_24 sent with the Membership ID CC2006-694 | L |
| 814_26 | CC2006-694 |  |
| 820_02 | CC2006-691 |  |

### 2.1 Transactions sent by the TDSP

The following is a list of transactions that, if sent in Version 2.1, will fail at either ERCOT or the CR.  The TDSP acknowledges that these transactions will not be sent until the TDSP can produce the transaction in a Texas SET Version 3.0 format, or implement Texas SET Version 3.0 code.

| Transaction | Transaction Type | Overall Market Operations Risk |
| --- | --- | --- |
| 650_02 | CC2006-691, 2006-692, 2006-698 |  |
| 650_04 | CC2006-691, 2006-702 |  |
| 810_02 | CC2006-691, 2006-701 |  |
| 814_PC | CC2006-691 |  |
| 814_04 | CC2006-692, 2006-694, 2006-703 |  |
| 814_09 | CC2006-692, 2006-703 |  |
| 814_13 | CC2006-692 |  |
| 814_19 | MOU/EC TDSP: CC2005-687, 2006-692 |  |
| 814_20 | TDSP will not send any 814_20 Load Profile changes until successful migration of 2.1 CC2006-693, 2006-694, 2006-696 | M |
| 814_25 | CC2006-692 |  |
| 814_27 | CC2006-692 |  |
| 814_28 | CC2006-692, 2006-694 |  |
| 867_02 | CC2004-674 |  |
| 867_03 | CC2006-691 |  |
| 867_04 | CC2006-697 |  |

# CR Contingency Plan

Should a CR fail to successfully implement Texas SET Version 3.0 the Market will be notified on Saturday, June 23rd  at the 68:00 PM Market Participant Conference Call.  The CR will coordinate a weekend migration to minimize any potential impact to the rest of the Market.

Upon notification, the CR will initiate the following Contingency Plan:

### 3.0 Transactions received by the CR

The following is a list of transactions that have changed as a result of Version 3.0 and could possibly be rejected by Version 2.1 code.  The CR acknowledges that these transactions will not be rejected if received but worked manually until the CR can implement Texas SET Version 3.0

| Transaction | Transaction Type | Overall Market Operations Risk |
| --- | --- | --- |
| 650_02 | CRs will not reject any 650_02 received with the new complete unexecutable reasons CC2006-691, 2006-692, 2006-698 | L |
| 650_04 | CC2006-691, 2006-702 |  |
| 810_02 | CRs will not reject any 810_02 received with new codes related to billing determinants or tariff/charge off allowances CC2006-691, 2006-701 | H |
| 814_PC | CRs in MOU/EC Territory will not reject any 814_PC sent by an MOU/EC TDSP CC2006-691 | L |
| 814_02 | CC2006-692 |  |
| 814_05 | CC2006-695 |  |
| 814_08 | CC2006-692, 2006-694, 2006-703 |  |
| 814_11 | CC2006-692 |  |
| 814_12 | CC2006-694 |  |
| 814_14 | CC2006-692, 2006-703 |  |
| 814_17 | CC2006-692 |  |
| 814_19 | CC2005-687, 2006-692 |  |
| 814_20 | CC2006-693, 2006-694, 2006-696 |  |
| 814_22 | CC2004-678 |  |
| 814_25 | CC2006-692 |  |
| 814_27 | CC2006-692 |  |
| 814_28 | CRs will not reject any 814_28 received with the new complete unexecutable reasons CC2006-692, 2006-694 | L |
| 867_02 | CC2004-674 |  |
| 867_03 | CC2006-691 |  |
| 867_04 | CC2006-697 |  |

### 2.1 Transactions sent by the CR

The following is a list of transactions that, if sent in Version 2.1, will fail at either ERCOT or the TDSP.  The CR acknowledges that these transactions will not be sent until the CR can produce the transaction in a Texas SET Version 3.0 format, or implement Texas SET Version 3.0 code

| Transaction | Transaction Type | Overall Market Operations Risk |
| --- | --- | --- |
| 650_01 | CRs will not send an 650_01 transactions with the ‘N’ indicator in the Premium Disconnect YNQ segment CC2006-691, 2006-698, 2006-700 | L |
| 810_03 | To MOU/EC TDSP: CC2006-699 |  |
| 814_PC | CC2006-691 |  |
| 814_01 | CC2006-694 |  |
| 814_08 | CC2006-692, 2006-694, 2006-703 |  |
| 814_09 | CC2006-692, 2006-703 |  |
| 814_12 | CC2006-694 |  |
| 814_13 | CC2006-692 |  |
| 814_15 | CC2006-692, 2006-703 |  |
| 814_16 | CC2006-694 |  |
| 814_18 | CC2006-694 |  |
| 814_24 | CC2006-694 |  |
| 814_26 | CC2006-694 |  |
| 820_02 | CC2006-691 |  |

# Additional Contingencies

Potential Weather delay

First discussion of weather delay will take place on the Thursday 4:00 pm conference call.

- If delay is not called on Thursday 4:00 pm, last opportunity for discussion of weather delay will take place on Friday 1:00 pm conference call

- If delay is called, there are 2 possible results:

  - Weather does not cause a significant impact on any active MPs.  Delay is one week.

  - Weather causes a significant negative impact on one or more active MPs.  Delay may be more than one week.  Delay of greater than 1 week will cause July 1, 2007 PUCT mandated implementation date to not be met.  PUCT will need to be involved in contingency in this case.