## Jun_Jul
2007-06-01
Monday | Tuesday | Wednesday | Thursday | Friday | Sat/Sun
|  |  |  | 1 | 2/3
WebX
4 | 5 | 6 | 7 | 8 | 9/10
SCED HB Comments | SCED HB Comments | SCED HB Comments | WebX
11 | 12 | 13 | 14 | 15 | 16/17
TPTF EDS 3 Approach | SCED Phase 1 Comments | SCED Phase 1 Comments | WebX | SCED Phase 1 for TPTF Comments
18 | 19 | 20 | 21 | 22 | 23/24
SCED Phase 2 Comments | SCED Phase 2 Comments | SCED Phase 2 Comments | WebX | SCED HB Updated - Phase 2
25 | 26 | 27 | 28 | 29 | 30/1
TPTF SCED Phase 1 for Approval | TPTF | TPTF | Workshop SCED Phase 2
Key Activities
June 1 - Web X | Review 5/24 workshop Q&As, present tentative calendar, overview of Handbook updates.
June 7 - Web X | Review Handbook comments, discuss Phase 1 completion requirements, planning topics (TBD)
June 11 - TPTF | Present EDS 3 Approach for Approval
June 14 - Web X | Review SCED Phase 1 for TPTF Approval
June 15 | Post Handbook for TPTF comment on Phase 1
June 25-27 TPTF | Present SCED Phase 1 for TPTF Approval
June 28 - Workshop | Discuss SCED Phase 2 Scenarios, Offer Methodology, Data Requirements
2007-07-01
Monday | Tuesday | Wednesday | Thursday | Friday | Sat/Sun
30/1
2 | 3 | 4 | 5 | 6 | 7/8
SCED HB Phase 2
9 | 10 | 11 | 12 | 13 | 14/15
TPTF EDS 4 Approach | TPTF | Workshop Phase 2 - Concurrence |  | HB Update for TPTF
16 | 17 | 18 | 19 | 20 | 21/22
|  |  | WebX | SCED HB Phase 3
23 | 24 | 25 | 26 | 27 | 28/29
TPTF Phase 2 Approval | TPTF | TPTF | Workshop SCED Phase 3
30 | 31
Key Activities
July 9 - TPTF | EDS 4 Approach Presentation
July 11 - Workshop | Review Handbook comments, Review Phase 2 completion items, planning topics (TBD)
July 19 - Web X | Review Handbook Phase 2 for TPTF Approval
July 23 - TPTF | Present EDS 4 Approach Document for Approval
July 26 - Workshop | Review Handbook comments, discuss Phase 3 completion requirements, planning topics (TBD)