## EDS3_Workshop
# | Description | Type | Raised By | Comments | Status | Include in Handbook?
1 | What system capabilities will be available at what time and how many people need to be dedicated from each MP |  |  | The Market Participant Handbook will detail the activites to be performed during any given phase and timelines expected as well the frequency and the roles for Market Participants. Since each MPs solution may be different, ERCOT cannot provide resource requirements for MPs. MPs will have to estimate their resource needs based on the activities and timelines expected. | Open | Yes
2 | We need a timetable of how the SCED handbook will be built and delivered | Request | Bob Spangler | Draft Calendar for handbook development posted on 5/31, presented at 6/1 WebX. | Open | No
3 | What is the Registration information that you are using in July? Is it zonal. Do MPs have to do something and give any additional information other than what is already available? |  |  | We expect to use current Zonal data for Phase 1 of EDS 3. | Closed | Yes
4 | Need to see a flowchart of how things work. A technical representation that shows how data sent uploaded by MPs interacts with ERCOT systems and how responses are sent back. | Request |  | ERCOT will provide a conceptual diagram that will be including it in the SCED handbook. | Open | Yes
5 | We need to include technical deliverables and when they need to be there in the documentation. MPs technical roadmap needs to be created and included | Request |  | The MP Handbooks will define the technical deliverables required for each Phase of testing. | Open | Yes
6 | Offer some sample data of the inputs and outputs, with fictitious data | Request |  | The EDS team is researching this possibility and timeframe for delivery. | Open | TBD
7 | Add the type of MP who will need to use each type of External Webservice in the table that shows the web service implementation timeline. |  |  | QSEs will be the only type of MPs utilizing the Webservices listed in the SCED handbook | Open | Yes
8 | Why are we including COP during phase 1? |  | Floyd | The COP is required as part of the MMS validation rules. Reshmi Surendran to discuss with Floyd Trefny. Validation requirements to be reviewed. | Closed | No
9 | MPs need to see details around test scenarios for each phase. | Request | Bob Spangler | The EDS team is currently working on defining some test scenarios for each phase. Further development will be done with MP involvement during the planning workshops. | Open | Yes
10 | Will the TDSPs be notified if their involvement is required during EDS 3, if so how? |  |  | During EDS 3 TDSPs will be involved in EDS 2 activities in parallel and these data feeds will be utilized in EDS3 for SCED execution and LMP generation. | Closed | Yes?
11 | SCED Pre-Processor inputs such as Offer curves, Mitigated Offer Curves, Constraint List, Topology and Shift factors, Performance Metrics should be displayed and tested during the E-EDS. Even though these will be tested during iTEST, MPs still need proof |  | Bob Spangler | Under investigation with project team. Details will be communicated and provided in the Handbook. | Open | Yes
12 | When will basepoints be available through ICCP and at what frequency? |  |  | ICCP Output is targeted for Phase3 of SCED in November. Specific availability date will be clarified as we get closer. | Open | Yes
13 | We need to have disclaimers when we publishing outputs so that the market does not get confused. |  |  | EDS Output distribution will be limited to those MPs involved in EDS testing until general reasonability is determined. Disclaimers will be provided to clarify source data of distributed SCED results. | Open | No
14 | What if MPs cannot participate in the EDS before December |  |  | It is expected that all required MP will make their best effort to be ready by October. However, as the need arises ERCOT will work with individual MP where necessary. | Open | Yes?
15 | We need to drill down the details for phase 1. Need to publish a schedule for MP involvement in finishing the handbook |  |  | Draft Calendar for handbook development posted on 5/31, presented at 6/1 WebX. | Closed | No
16 | MPs want to know how we can transition from the draft to the detailed handbook |  |  | Draft Calendar for handbook development posted on 5/31, presented at 6/1 WebX. | Closed | No
17 | How do we ensure reasonable LMPs have been calculated? |  |  | Need to schedule a workshop with Market Participants for defning LMP reasonableness. | Open | No
18 | When will basepoints be available in GUI |  |  | Under investigation with project team to determine publish mechanisms and dates. | Open | Yes
19 | Swirl around security. Where do you get ceritificates, what is the mechanism. Etc. Include it in the handbook |  |  | The Handbook will include pre-requiste information for MP, including Security requirements. | Open | Yes
20 | Send out an email about eds3@ercot.com |  |  | A Market Notice will be sent. | Closed | No
21 | What all points need to be completed for eds 3? Is this covered within the scope of P2P , SE & Telemetry verification |  |  | The EDS team will provide more detail on the data requirements in the Handbook. | Open | Yes
22 | Will Mock Settlements statements be sent through API |  |  | Yes they will be. We need to include it in later handbooks | Open | Yes
23 | When is the MP training required to support EDS? |  |  | Training calendar will be published | Open | Yes
24 | Will Base points be sent through API |  |  | Not currently. MPs will need to raise an NPRR for this to happen | Closed | No
25 | As we are going though test phase, will errors reported by MPs be be covered during the weekly conference calls? |  |  | Yes, the EDS 3 team will maintain an open issue list with target resolution dates. | Open | Yes
26 | When will we have the first conference call be held? |  |  | Starting on Friday June 1st | Closed | No
27 | At what point can bilateral trades be tested? |  |  | EDS 4 | Closed | No