## Slide 1: Texas Nodal Program Update
Jerry Sullivan

## Slide 2: Agenda
Item | Who | Purpose
Nodal Program Status | Jerry Sullivan | For Information
Change Control | Jerry Sullivan | For Information
Market Readiness Metrics Model | Jerry Sullivan | For Information

## Slide 3: Program is still Amber - but is continually being assessed
Scope / Quality
Schedule
Cost
Legend
Summary
Amber
Latest monthly committed cost and forecasts are under by 4% of budget to date. Funding for Identity Management and change controls being defined.
Amber
Amber
Baseline 1 impact assessment nearing completion.
Still ensuring traceability of requirement to protocols.
Red
Amber
Green
Estimate at Complete = <$248m
Estimate at Complete = $248 - $263m
Estimate at Complete = >$263m
Go-live = 12/1/08
Go-live = <30 days+
Go-live = >30 days+
Program is aligned with current protocols
Program is aligned to previous version of protocols
Program is not wholly aligned to protocols
EDS 3 Market Participant planning event complete.
Working through issues on staffing.
Adjusting organization to respond to improve schedule.

## Slide 4: Current focus: clear the NPRR backlog and synchronize projects to a common baseline
To maintain overall system integrity – for Nodal to work as a whole – each project has to be synchronized on an explicit, current, common baseline
Baseline 0 May, 2006 Protocols
Baseline 1
NPRRs approved by March 31, 2007
NPRR “Backlog”
Nodal Projects
Pending Baseline
Current Baseline
Synchronization “deficit”
= Level of NPRR Incorporation

## Slide 5: We have agreed the next baseline for projects to synchronize on: “Baseline 1”…*
List of
63 baseline 1 items
including –
Approved NPRRs (31)
Draft NPRRs (13)
White Papers (15)
Change Items (4)
Baseline 1 (March 31, 2007)
The “Impact Categorization Matrix” helps triage the impacts for all the items across all the projects
23 of the 63 (36%) items have all projects with a
minimal or no impact
(category 3 or 4)
40 of the 63 (64%) items have at least 1 project with a high or a medium impact (category 1 or 2)
* Work in progress – counts may change

## Slide 6: Examples of the item types in a baseline group…
NPRR 48 - Revised Wording of Opportunity Outages for Transmission Facilities
The proposed Opportunity Outages rewording will allow ERCOT to grant a TSP permission to work on TSP-owned equipment that can only be maintained when a Resource is off-line for a Forced, Planned or Maintenance Outage.
White Paper 004 – Power Flow Consistency Requirements
In order that ERCOT achieve the objective of ensuring consistent results from the power flows supplied by the different vendors, it would be necessary to stipulate a consistent methodology, algorithm and tolerances to be used by all vendors. The remainder of this white paper focuses on that.
Change Item (CI) 57 – Move Resource Parameters from Registration to MMS
ERCOT had planned to implement all Resource parameters in the Registration system. Upon review by TPTF, the market participants observed that some parameters must be updated more frequently than the registration system accommodated. ERCOT revised the system design to allow a rapid change in some parameters through the MMS system.

## Slide 7: “Baseline 1” Status: Target completion of change requests – June 6th, 2007
The current cycle time suggests re-baselining at 90 day intervals
8 weeks from declaration of Baseline 1 scope
3/31/2007
Agree baseline scope

Complete impact categorization of finalized items

Group the items for implementation synergies/efficiencies

Technical Change Control Board conduct program-level architecture assessment & produce draft “Change Requests”

5/25/2007
Establish detailed project cost and schedule analysis

6/1/2007
Technical Change Control Board update schedule, budget and system architecture. Validate implementation timeframes.

6/6/2007
Submit to Change Control Board for approval

Presented Submittal

6/12/2007
Recommend Language and Impact Analysis for approval

## Slide 8: Baseline 1 will follow the following process for recommendation and approval…
Items to be approved
PRS/TPTF
June 12
TAC
June 28
BoD
(Mid-July)
Baseline 1
NPRRs*
Change Item*
White Papers*
Approved by BoD
Language approved by PRS
Language not approved by PRS
Recommend impact analysis (IA) for approval
Recommend language & IA for approval
Endorse impact analysis
Endorse impact analysis
Recommend impact analysis (IA) for approval
Recommend language & IA for approval
Endorse impact analysis
Endorse impact analysis
Approve protocol language and scope, timeline and cost impacts
PRS to endorse NPRRs and CIs, recommend white paper IA’s for approval.
Program Director to direct projects to begin baseline 1 implementation subject to BoD approval.
TAC to recommend language and impact analysis for approval.
Program Director to update directive if any revisions or rejections occur.
BoD to approve protocol language and scope, timeline and cost impacts.
Program Director update directive if any revisions or rejections occur.
*NPRR: New Protocol Revision Request e.g. MIS Posting for Area Trades (NPRR #22)
*Change Item: e.g Model Data Initial Load (Item #77)
Integration & Design Authority White Papers: e.g. State Estimator Rollover Maintenance (WPIDA008)
31
12
1
44
63
4
15
63
# of items
43
1
4
15

## Slide 9: The Change Control team has a clear roadmap for the next 3-4 weeks…
Send to TAC
Present to TAC
Send to BOD
Present to BOD
Projects review & approve IA Packages
Submit to CCB
PRS/TPTF dry run with PMs
Send IA data to PRS
Present at PRS /TPTF
Send slides to TAC
Present at TAC
Send slides to BOD
Present at BOD
June 5
June 6
June 7
June 7
June 12
June 18
June 28
July 6
July 17
May 31
June 7
June 8
June 19
Communicating the Process
Executing the Process
This planned approach ensures timely approvals from all external stakeholders

## Slide 10: Each of the 12 change requests will follow a common form…
Group No. |  |  |  | 2
Characteristics |  |  |  | 
No. of items | NPRR | 2 | Total $ impact | $TBD
 | Change Item | 3 | Critical path impact (weeks) | TBD
 | White Paper | 4 | EDS Test (1/2/3/4) | 2
Total |  | 9 |  | 
Detail |  |  |  | 
Item description: |  |  | Risks / Dependencies: | 
1 2 3 |  |  | 1 2 3 | 
ILLUSTRATIVE

## Slide 11: “Baseline 2” scope definition: target by June 22nd, 2007 …
Projects & Market participants to “finalize” their NPRRs or White Papers if they are to be considered for inclusion in Baseline 2
19 NPRRs
As of 5/12/2007, there are 28 items in Baseline 2…
9 IDA white papers and
other implementation and
design solutions not
impacting protocols
For inclusion of an NPRR in future pending baselines, it
must have PRS’s initial
review and recommendation
of approval (PRS 1)
Impact categorization continues for new items to get ahead for the next synchronization – work in progress
Work in progress

## Slide 12: Market Readiness

## Slide 13: Goals & Characteristics of Readiness Metrics
Goals of Readiness Metrics
  Encourage early participation
  Minimize delinquency
  Inform market of readiness declarations
  Motivational tool for the market as a whole
Characteristics of Metrics
  Easy to understand (unambiguous) – linked to Transition Plan where possible
  Easy to calculate (reliable) – simple roll-up and grading rules
  Easy to communicate – red, amber, green
  Incorporates Market Participant self reporting & ERCOT Observability
Timing of Metrics
  Progressive measurement through the readiness sequence
  Forwarding looking, including lead indicators

## Slide 14: Overall View of Nodal Readiness Metrics model
Top-level view
ERCOT Summary grading rules
EDS Summary grading rules
MP Summary grading rules
EDS
1
EDS
2
EDS
3
EDS
4
ERCOT Roll-up
MP Roll-up
Dept C
Dept B
Dept A
QR ABC Inc.
ERCOT Model roll-up
EDS Model roll-up
MP Model roll-up
ERCOT scorecard & grading rules
MP scorecard & grading rules
EDS-unique metrics
ERCOT Readiness
EDS Readiness
MP Readiness
Dept. A
Dept. B
Dept. C
Dept. D
Dept. E
Dept. F
QSE +R
QSE
TSP/DSP
LSE
CRR
Dept. A
Dept. B
Dept. C
Dept. D
Dept. E
Dept. F
QSE +R
QSE
TSP/DSP
LSE
CRR
Metrics inventory (self-reported and ERCOT-observable metrics)
Reported to:
Nodal Steering Board
ERCOT managers
Reported to:
Nodal Steering Board
TPTF
TAC
BOD
Reported to:
Accountable Executives
1
2
3
6
5
7
4
5

## Slide 15: Top-level view of Readiness
Nodal Readiness – Top-Level View
ERCOT Readiness
EDS Readiness
Market Participant Readiness
Day-Ahead Administration
Price Verification
Congestion Management
Operations Planning & Analysis
Outage Coordination
Operations Support Engineering
Network Modelling
Dedicated Testing
Dedicated Training
Client Relations
QSE +R
QSE
TSP/DSP
LSE
CRR
The top-level gives a one-page view of where attention needs to be directed across all areas of market readiness
It will enable Nodal management and external stakeholders to have an up-to-date view of market readiness, in line with the program’s view of overall success
1

## Slide 16: Market Participant Self-Reporting Questionnaire – deployment on 6/1/2007
A self-reporting questionnaire will be released to Accountable Executives (Authorized Representative in absence of AE)
Initial focus:
  TSPs
  QSEs with Resources
  QSEs without Resources
The tool will enable MPs to attest to their level of readiness for the Nodal market
Overall readiness will be assessed by self-reporting and ERCOT observable metrics
Self-reporting questionnaire mock-up
2

## Slide 17: Questionnaire responses will inform separate metrics
Initiation status
Mobilization status
Delivery status
Metric grading rules:
  Report cycle 1 (June): Any "No" responses = Amber, else Green (no Red)
  Report cycle 2 (July) and beyond: Any "No" responses = Red, else Green (no Amber)
Metric grading rules:
  Report cycle 1 & 2 (June): Any "No" responses = Amber, else Green (no Red)
  Report cycle 3 (August) and beyond: Any "No" responses = Red, else Green (no Amber)
Metric grading rules:
  If Registration, Qualification OR Systems Available question is "No" = Red
  If all questions are "Yes" = Green
  All other permutations = Amber
2

## Slide 18: Self-reported and ERCOT-observable metrics will be combined into individual Market Participant and ERCOT departmental scorecards
Individual Market Readiness Scorecard
Self-reported metrics ERCOT Observable metrics
Initiation status
Mobilization status
Delivery status
Connectivity to Test Environment
Upload SCED offers to EDS
MP Test Digital Certificates Obtained
Overall readiness status:
Scorecard grading rules:
  Red – if any component is red
  Green – if all components are green
  Amber – all other permutations
2

## Slide 19: The first level of roll-up will provide aggregations of each metric by market participant role
Roll-up model:
  The roll-up will present a summarized view of MP readiness metrics by group (role)
  RAG (Red, Amber, Green) status will be determined by weighting each MP’s results by the % contribution (system generation, load, ancillary services) made to the Texas market for their role. Targets by role are:
    100% for QSEs with Resources and TSPs
    95% for other market participant types
3

## Slide 20: ERCOT roll-up will focus on the most affected departments
Market Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
Department Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
Market Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
Department Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
Market Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
Department Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
Market Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
Department Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
Market Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
Department Readiness Scorecard
ERCOT Observable Metrics
Training
Amber
Procedure Development
Organization Design / Staffing
Overall Department readiness status:
4
Roll-up model:
  The roll-up will present a summarized view of ERCOT readiness metrics by department.
  RAG status will reflect the ability of each department to hit readiness goals related to Training, Procedure Development, and Organization Design by the appropriate project milestones (typically correlated to EDS phases.)

## Slide 21: The top-level roll-up will provide a single summary for each market participant role and key ERCOT department
Overall readiness grading rules:
  Red – if any component is red
  Green – if all components are green
  Amber – all other permutations
ERCOT Readiness
Dept. A
Dept. B
Dept. C
Dept. D
Dept. E
Dept. F
MP Readiness
QSE +R
QSE
TDSP
LSE
CRR
5

## Slide 22: EDS Metric deployment dependent upon Early Delivery System Sequence Timeline
EDS metric grading rules:
  Not Measured – Metric not yet deployed
    White = Metric criteria is not evaluated
  In Measurement – Under preliminary measurement
    Amber = Metric criteria is not met
    Green = Metric criteria is met
  Measured – Under measurement
    Red = Metric criteria is not met
    Green = Metric criteria is met
Dept C
Dept B
Dept A
QR ABC Inc.
EDS-unique metrics
6

## Slide 23: Progressive measurement provides a temporal view of market readiness
EDS Readiness
Overall EDS readiness grading rules:
  Red – if any deployed component is red
  Green – if all deployed components are green
  Amber – all other permutations of deployed component metrics
  White – Metrics not yet deployed
7

## Slide 24: Next steps in Market Readiness – through 2007
MP Self Reporting deployment
  Distribution to respondents 6/1
  Target response 6/30
  Bi-monthly/quarterly thereafter (TBC)
ERCOT Departmental reporting deployment
  Organization Design beginning June 1st
  Internal procedures beginning August 1st
  Nodal Operating Guides beginning December 1st
  Training beginning October 1st
ERCOT-observable metrics deployment
  EDS 1 (ERCOT only) beginning June 1st
  EDS 2 beginning June 15th
  EDS 3 beginning November 1st
Reporting initiation
  July TPTF and TAC meetings