EDS 3

Approach

Early Delivery System

Submitted By

EDS Project Team

Texas Nodal Project

June 2007

V0.91

Revision History

| Revision | Comments | Date | Author |
| --- | --- | --- | --- |
| V0.01 | Initial version for TPTF comment | April 19th, 2007 | EDS Team |
| V0.02 | Updated based on TPTF comments | May 3rd, 2007 | EDS Team |
| V0.91 | Updated based on TPTF comments | May 30th 2007 | EDS Team |

TABLE OF CONTENTS

1	EDS 3 – OVERVIEW	4

1.1	Introduction	4

1.2	Transition Plan Tasks	4

1.3	Early Delivery System Releases	5

1.4	EDS 3 Market Participant Involvement	5

1.5	EDS 3 Planning Workshops	6

1.6	EDS 3 High Level Timeline	7

2	Release 5 – Security Constrained Economic Dispatch	9

2.1	Description	9

2.2	SCED Testing Approach	10

2.3	Market Participant Readiness	14

2.4	Entry Criteria	15

2.5	Exit Criteria	15

3	Release 6 – Load Frequency Control	17

3.1	Description	17

3.2	LFC Testing Approach	17

3.3	Market Participant Readiness	22

3.4	Entry Criteria	22

3.5	Exit Criteria	23

4	Release 7 – Congestion Revenue Rights	23

4.1	Description	23

4.2	CRR Testing Approach	23

4.3	EDS 3 Market Participant Readiness	26

4.4	Entry Criteria	26

4.5	Exit Criteria	26

5	Mock Settlement Statements	26

6	Web Services / API	26

7	Quality Expectations and Staffing	27

7.1	Quality Expectations	27

7.2	EDS 3 Staffing	29

8	Protocol coverage and other test requirements	30

9	Appendix 1 – Protocol Coverage and testing requirements	31

10	Appendix 2 -  EDS Communication Activities	36

# EDS 3 – OVERVIEW

## Introduction

Each Early Delivery System (EDS) release is a deployment of new applications, hardware, functions and processes to satisfy the requirements as outlined in the ERCOT Nodal Transition Plan document. This document summarizes the approach and activities for EDS 3 and describes how each new release of system functionality will be tested to ensure ERCOT Nodal Transition Plan coverage.

## Transition Plan Tasks

The related transition plan tasks for EDS 3 are listed below:

SCED

- 5.1.4	As early as practical, ERCOT shall begin  posting of LMPs to Market  
                  Participants based on test Resource offer curves submitted to ERCOT by the 
                  QSEs to measure the accuracy and stability of the SCED.  The minimum time 
                  for this posting should be at least six months but may be longer as approved by 
                  the TPTF.

- 5.4.4 (1)	ERCOT, the IMM, and Market Participants shall, with the concurrence of the 
   		TPTF, develop a method for Market Participants to create and provide 
          	individual Resource offer curves to SCED.

- 5.4.4 (2)	To support trial operation of the SCED on the EDS to ensure that the pre- 
           	requisite component relationships are working, as well as to evaluate the quality 
 		of the LMPs produced, ERCOT shall implement the capability for QSEs to enter    
 		individual Resource offer curves to SCED.

- 5.4.4 (3)	Verify Base Points and associated LMPs calculated by SCED for reasonability 
                  and Post LMPs and other data available as required in the Nodal Protocols.

- Load Frequency Control

- 5.4.8(1)	Verify data requirements for LFC, for each QSE qualified to provide 
                  Reg-Up, Reg-Down or Response Reserve Services

- 5.4.8(2) 	Compare Area Control Error on EDS environment and existing control systems 
                  for seven days, for accuracy

- 5.4.8(3) 	Verify each QSEs ability to provide Regulation Control and Dispatch 
                  Instructions for Manual Emergency Energy Dispatch

CRR Allocation & Auction

- 5.4.5(1)  	Verify MP’s ability to submit test bids for CRRs on Transmission Elements

- 5.4.5(1)  	Execute Trial Auction for Monthly and Annual CRRs

- 5.4.5(1) 	Assign trial PCRRs / CRRs to MPs for DAM and RT Operations testing of
               	Settlement Systems during EDS4

## Early Delivery System Releases

The EDS 3 system functionality has been segmented into three distinct releases for the achievement of specific objectives.

- Release 5 – Security Constrained Economic Dispatch (SCED)

- Provide a SCED environment for Market Participant EDS Activities

- Verify QSE ability to submit 3 part offers, COP, and output schedules into SCED

- Verify the User Interface and Machine to Machine interfaces provide inputs for SCED

- Execute SCED to create test Base Points and LMPs

- Verify Base Points and associated LMPs for reasonability

- Verify QSE ability to receive test Generation Resource Base Points and test LMPs via ICCP

- Test LMPs can be posted to the MIS with other data available as required in the Nodal Protocols

- Release 6 – Load Frequency Control (LFC) testing and ACE calculation

- Validate completion of all communication system testing

- Verify proper operations of the LFC functions, including but not limited to:

  - Verify calculations of HASL, LASL, SURAMP, SDRAMP, HDL, LDL

  - Verify ability to deploy Responsive Reserve Capacity MW

  - Verify ability to deploy Non-Spin Capacity MW

  - Verify ability to calculate and issue Emergency Base Points to QSEs

- Compare Nodal ACE results with Zonal ACE results for accuracy

- Verify for each registered Reg Up and Reg Down Resource, the ability to provide      
 Regulation Control on Nodal Systems

- Release 7 – Congestion Revenue Rights Trial Allocation & Auction

- Provide a CRR test environment for Market Participant EDS Activities

- Verify Market Participant ability to provide CRR Allocation & Auction bids and offers

- Execute annual and monthly CRR trial auctions

- Distribute Allocation & Auction results to Market Participants

- Create test PCRRs / CRRs and assign for trial operation of DAM and settlements

## EDS 3 Market Participant Involvement

The EDS 3 SCED testing activities are focused on early testing of the SCED functionality initially in a stand alone mode then integrated with other Nodal systems before EDS 4 when the remainder of the Nodal functionality will be introduced. The sections below outline Market Participant involvement by type, EDS activities, and expectations.

SCED Testing

| Market Participant Type | Activities | Timeframe | Expectation |
| --- | --- | --- | --- |
| QSEs with Generation Resources planning to use External Web Services to interface with ERCOT | MP Development Connectivity Testing (Sandbox) | July - September | Strongly Recommended |
|  | MP Connectivity Testing (EDS Environment) | July - September | Strongly Recommended |
|  | MP Connectivity Testing (EDS Environment) | October | Mandatory * |
|  | MP Input Validation – SCED | Aug – September | Strongly Recommended |
|  | MP Input Validation – SCED | October | Mandatory * |
|  | MP Input using SCED User Interface | October | Recommended ** |
|  | MP Input for SCED Execution | October – December | Mandatory for designated EDS testing days |
|  | MP Input for 6 month LMP Period | January – June 2008 | Mandatory based on define scenarios and methodology |
| QSEs with Generation Resources who plan on using ERCOT’s provided User Interface to SCED | MP Input using SCED User Interface | July – September | Mandatory |
|  | MP Input for SCED Execution | October – December | Mandatory for designated EDS testing days |
|  | MP Input for 6 month LMP Period | January – June 2008 | Mandatory based on define scenarios and methodology |

* Starting in October Market Participant involvement is critical to begin producing “Reasonable” LMPs. During this period the Market Participants should have a EDS system in place to support the activities and functionality being demonstrated. The EDS team will provide workshops during this time to support Market Participants. Required Market Participants that are not able to participate will have to still perform these activities by requesting a ‘make-up’ workshop prior to involvement in later EDS activities. There will be limited opportunities for support due to focus on other EDS functionality.

** The EDS team recommends that all QSEs with resources schedule some time to get familiar with the SCED user interface even if they are planning on utilizing External Web Services in production. This will help ensure that Market Participants have a second method for accessing the EDS systems if their External Web Services are not functioning correctly.

## EDS 3 Planning Workshops

In order to get to the appropriate level of planning for execution of the EDS 3 activities ERCOT and the Market Participants need to work together to ensure that both ERCOT and the Market Participants can maximize the benefits of the EDS. The EDS team will schedule monthly EDS planning workshops and ongoing conference calls to complete the details required for EDS execution. The workshops will focus on: EDS 3 test preparations; questions and answers;  the use cases which will be tested; the detailed test procedures and schedule of the test sequences; test sequence planning at the QSE and Resource level; and a substantive list of specific exit criteria for each of the EDS 3 test sequences; and the final exit criteria that signifies the completion of all EDS 3 activities that support a declaration of readiness. The EDS planning workshops will provide input for the test plans and test scenarios to support the day-to-day testing activities.

The details for each Phase of EDS 3 testing will be documented in

a Market Participant handbook. – There will be a handbook for each EDS 3 Release covering SCED, LFC, and CRRs. These documents will be organized by EDS phases and will including testing activities, data management plans, staffing, detailed schedules, ERCOT and Market Participant activities, test scripts and use cases.

## EDS 3 High Level Timeline

EDS 3 activities start in July 2007 with the ability to upload three part offers into SCED for data validation.,  The environment will be upgraded with new functions and variance corrections as new software becomes available throughout the completion of EDS 3 testing .

The following diagram provides a high level representation of the Nodal program delivery with the EDS 3 releases outlined in the red box, showing incremental functionality and the timeline for each of the releases.

# Release 5 – Security Constrained Economic Dispatch

## Description

- The Security Constrained Economic Dispatch Release 5 will be the first introduction of the Nodal Market System to Market Participants. The focus of the release is to work with Participants to ensure that:

- QSEs can submit, modify, and retrieve SCED input data

- ERCOT can execute SCED and distribute Locational Marginal Prices (LMPs)

- SCED produced LMPs are reasonable against predetermined reasonability criteria

- QSE can receive Generation Resource Base Points and LMPs distributed via ICCP [note: the term Resource by itself includes Load Resources which can only offer into the DAM for Ancillary Services]

- MIS reporting for LMPs, Settlement Point Prices and other information meets posting requirements based on the Nodal Protocols, the Business Requirements and Nodal Transition Plan

- ERCOT can begin the 6 month LMP posting period as required by the Nodal Transition Plan

- Early system deliveries will initially provide QSEs the opportunity to submit, modify, cancel, and retrieve input data for SCED execution. During the phase the EDS environment will be further upgraded to provide the functionality for SCED execution using ERCOT and QSE test offers and to begin reporting on LMPs. This phase of SCED testing will  identify potential issues, provide crucial feedback for internal QA testing, and plan the LFC verification activity that will occur in Release 6.

## SCED Testing Approach

- The Nodal program has adopted an incremental approach for releasing functionality into the EDS environment to maximize the overall benefit of EDS by providing system functionality for Market Participants to begin testing as early as possible. The early deliveries provide Market Participants with tools to begin testing critical interfaces.

- During the EDS activities Market Participants will have the opportunity to sign up for support workshops, for their internal team and vendors, focused on the specific testing activities to address MP specific questions or issues. Based on issues identified and resolved during the workshops the EDS team will provide communications on general trends and technical issues that apply across Market Participants.

- EDS 3 - Upload SCED Input Data (Target July - September 2007)

- Starting in July, the EDS environment will be upgraded to include a stand alone SCED and the External Web Service infrastructure to support uploading offers into the SCED system. During this three month period, the specific priority 1 External Web Services outlined below will be incrementally deployed by groups into the EDS environment as the back-end integration and internal testing is complete.  All of the priority 1 Web Services will be available as stubs in the Nodal Sandbox environment by July.

- The details below outline the target functionality and timeframes for deployment into the EDS environment. The schedule of specific deployment dates will be maintained on the Nodal Readiness Center page.

- The EDS environment will support the following capabilities:

- SCED User Interface – Target Late July 07

- Web Service Interfaces (SCED Input) – Target Late July 07 – Early September 07

- Some of the required fields in the Web Services interface specifications may not apply to the early SCED testing, however, stub data will need to be used to ensure that the Web Services can be successfully submitted. These details will be worked out in the planning workshops and scripts. Details about the external web services are provided in Machine-to-Machine (External) Interface Specification v0.94

- The early testing of SCED inputs will provide the opportunity to validate a number of use case scenarios; however, until October when the system is integrated with EMS and all of the Market timing is in place some use case scenarios may not be supported by the system. As the details are worked out for each phase specific scenarios will be defined during the EDS planning workshops and included in the Market Participant Handbook.

EDS 3 - SCED Testing (Target October 2007)  The formal SCED testing period that requires full Market Participant involvement will begin in October 2007. The initial testing will focus on those MPs that were not able to complete connectivity and validation testing during the early release.  Once significant number of MPs have completed the SCED input validation testing the trail operation of SCED will begin.

To support SCED execution and external reporting, an integrated set of systems to provide real-time ICCP data into the EDS environment will require the EDS environment to be upgraded with the following applications and configuration:

- Registration System

- Network Model

- EMS (SCADA, SE, NSA, TCM, RLC)

- MIS (LMP and SPP Posting)

* Note: These systems will have had Functional Testing, Security, and initial Integration testing but will not be fully tested. During this period ERCOT internal quality control testing will continue to execute in parallel with EDS activities to improve quality and stability of the Nodal systems.

- The EDS environment will support the following capabilities:

- EMS Real Time ICCP Data Inputs

- MMS Market timing and proxy curve creation

- Execution of SCED utilizing Real-Time ICCP data

- Distribution of SCED Outputs through ICCP

- SCED External API Outputs

- SCED MIS Reporting (specific reports to be defined*)

- EDS 3 - 6 Month LMP Posting (Target January 2008) – The EDS 6 month posting phase will begin in January 2008.  After the completion of ERCOT internal quality control testing (FAT, Integration Testing, Business Process Testing) of all Release 5 systems, the EDS environment will be upgraded to begin six months of LMP posting as required by the Nodal Transition Plan.

- At the start of this phase, a number of activities from the previous two EDS 3 phases will have been completed resulting in significant improvement in the quality of the EDS results. These activities include:

- Participant training sufficient (SCED related)

- Participant EDS 3 market interfaces tested

- External Interface issues identified & critical issues fixed

- SCED issues identified & critical issues repaired

- Full Network Model and telemetry operational and tracking zonal systems

- Initial LMP evaluation complete

- During this period the Market Participants will be expected to provide SCED input data based on the requirements defined by ERCOT in a SCED Handbook with inputs from the IMM and Market Participants, and approved by TPTF. The handbook will be developed during the EDS planning workshops.

### Timeline

EDS 3 activities begin in July 2007 leading up to an integrated SCED system supporting full Market Participant involvement beginning October 2007. SCED output MIS reporting and ICCP will be introduced soon thereafter. The six month LMP posting period will begin in January 2008, after the ERCOT quality control process completes. The phases are outlined in the high level timeline below:

### Posting LMPs

ERCOT shall define a methodology to ensure LMPs are consistent with SCED inputs.

- The Nodal Transition Plan states:

– Once QSEs are providing sufficient information, ERCOT shall begin trial operation of SCED and calculation of Generation Resource Base Points.  The LMPs calculated by SCED shall be verified for reasonability by the EDS test Team with inputs from Market Participants.  Once reasonability has been achieved , ERCOT shall begin posting LMPs and other pricing data as required in Nodal Protocols, Section 6.3.2, Activities for Real-Time Operations.

- Reasonability will be assessed based on:

  - LMPs are consistent with the offers submitted by QSEs or from test offers created by ERCOT

  - LMPs reflect known system constraints and congestion areas

  - When needed, test offers for Generation Resources will be created by ERCOT using typical energy prices considering the fuel type and technology of the Resource

  - Some LMPs may be in error in given areas of the Transmission system, but the majority of LMPs appear correct. During the early EDS testing it is anticipated that some LMPs may be incorrect due to input data error.  These LMPs will be evaluated and corrected during the posting period.

- Other Data available for posting to MIS will include:

| LMP and Settlement Point Price at each Hub and Load Zone | November 2007 |
| --- | --- |
| Base Points from SCED to each MP on the certified area of MIS | October 2007 |
| Active binding transmission constraints by Transmission Element name (contingency /overloaded element pairs) | November 2007 |
| Settlement Point Prices for each Settlement Point immediately following the end of each Settlement Interval | November 2007 |

## Market Participant Readiness

Below are the key activities that are expected from each Market Participant before and during EDS Release 5:

- QSE EDS personnel have attended Nodal Training Courses to the extent such classes are available

- Provide new and updated Registration data to ERCOT as the full Registration system becomes available

- QSEs produce offer curves and are able to submit them to ERCOT (through either the UI or the Web Services API)

- QSEs have the ability to produce Output Schedules and submit them to ERCOT

- QSEs have the ability to produce COPs and submit them to ERCOT

- QSEs have completed APIs or are able to use the ERCOT provided User Interface including

  - Obtaining appropriate digital certificates

  - Connectivity and ID Authentication

  - Offer submissions capability demonstrated

- QSE Identification representative/point of contact identified to support EDS Activities

- Market Participant schedule time to support EDS

## Entry Criteria

ERCOT entry criteria for EDS 3 Release 5 SCED – October 2007

- EMS components (SE, SCADA, RLC, TCM) required to execute SCED successful FAT tested

- NMMS – EDS 1,2 components completed sufficiently to start SCED

- MMS – Three Part Offer Interfaces complete

- MMS – Output Schedule Interfaces complete

- MMS – COP Interfaces complete

- COMS – Registration functionality complete

MP Entry criteria

- MP early delivery system ready for SCED testing

- MP able to create and submit individual Generation Resource offer curves via the MIS or the API

- Successful completion of EDS 1 and 2 test sequences

- MP able to create  and submit individual Output Schedules

- MP able to create and submit COP

- MP able to access MIS portal

- MP able to query their data which are accepted by ERCOT (if using APIs)

- MP EDS 3 system development sufficient to start testing

- Certification by the Accountable Executive that sufficient MP Training has been completed to support EDS-3 testing

- MP Internal support in place to support EDS test activities

## Exit Criteria

The following Exit Criteria need to be further refined working with Market Participants to determine the specific measurement criteria. These activities will be completed during the planning workshops.

- QSE’s submission of Resource Output Schedules

- QSE’s submission of COP

- Resource Offer Curves, Output Schedules verified as correct inputs to SCED

- GTBD verified as correct input to SCED

- HASL, LASL, SURAMP, SDRAMP, HDL, LDL verified as correct inputs to SCED

- Proxy curves verified as correct inputs to SCED

- QSE’s ability to receive correct Resource Base Points and LMPs via ICCP

- Base Point and LMP calculation verified for Resources with Offer Curves

- Base Point and LMP calculation verified for Resources with Output Schedules

- LMPs verified for Reasonability and posted to MIS for Market Participant review

- Ideally, MPs can view via MIS their resources’ HASLs, LASLs, SURAMPs, SDRAMPs, HDLs, LDLs

- LMPs posted to MIS for Market Participant review

- Release 6 – Load Frequency Control

## Description

This release addresses the requirements of Section 5.4.8 of the Nodal Transition Plan (Load Frequency Control Testing).  This activity will test the QSEs and associated resources ability to respond to Load Frequency Control signals produced by the Nodal system. The EDS 3 team will work with the ERCOT operators and QSEs to carry out coordinated QSE-by-QSE testing.

## LFC Testing Approach

As quoted in the Registration approach Document: QSEs representing Resources providing Ancillary Services shall “self-certify” their Resources to provide Ancillary Services. Resources currently providing Ancillary Services in the zonal market may be qualified by a authorized representative of the QSE signing an attestation of self-certification for the nodal market.  Submission of the attestation must be complete prior to EDS 3 testing by the QSE.  Subsequently, ERCOT will monitor performance during the Load Frequency Control testing phases of EDS 3.  Resources may be disqualified during the LFC Testing if ERCOT deems the performance of the Resource does not meet the requirements of the Nodal Protocols and Operating Guides.

ERCOT seeks to obtain information related to Resource self-certification of Ancillary Services during the registration process in order to consolidate data entry into Siebel (ERCOT’s registration system) and allow the Ancillary Services data to be propagated into other downstream systems.

### Verification Steps for LFC Testing Stations

Currently ERCOT is evaluating two options for conducting LFC trials – by testing one unit at a time or by one QSE at a time. LFC must distribute regulation control signals based on each QSEs regulation participation factor.  QSE’s subsequently assign unit regulation response based on the unit participation factors provided in their COP.  The following steps describe the verification activity and instructions.

Preconditions:

All QSEs will have completed relevant EDS 1 and 2 activities successfully.  These pertain specifically to:

- ICCP and the Generation Subsystem (LFC and Resource Qualification Testing) will have passed FAT and completed acceptable portions of the ITEST.

- Certification by the Accountable Executive that communication for their Resources is functional and capable of supporting the EDS-3 Releases 6 test sequence.

- QSEs have the capability to obtain base points from the ERCOT Nodal system, and regulation instructions from either the ERCOT Zonal or Nodal system.

- Both ERCOT Zonal and Nodal system will have the capability to obtain system frequency simultaneously.

- If possible, QSE under test will keep feeding data to ERCOT Zonal system. If a particular QSE will not be able to do this, ERCOT will work with them on an alternate solution.  The Zonal system has failure mechanisms in place to minimize the effect of communication loss to a single QSE, so this is not expected to be a significant issue.

Test Preparations:

- QSEs with Resources capable of providing Reg-Up and Reg-Dn AS will be scheduled for the test. ERCOT will coordinate with each QSE to schedule time periods for the testing of the QSE’s Resources.  Prior to actual test initiation, ERCOT will give as much advanced notice as practical (and in general will be more than two days). ERCOT will select hours of the day where system load is relatively flat. Additionally, ERCOT should select times during which sufficient generation capacity is on-line to minimize the likelihood of an unacceptable excursion from frequency set-point.

- The QSE under test will be asked to submit Resource level base points to match its projected energy schedule for the test hour for the Generation Resource. The base points provided should be at 5 min intervals. (Further details need to be defined on how this will be done)

- The QSE under test will participate in Ancillary Services Market as usual. The ratio of the regulation obligation of the QSE under test to total ERCOT requirement will be one of the inputs to Nodal LFC during the following day’s testing. This ratio will be available after the Ancillary Service Market clears.  This step to be performed the day before the QSE’s specified test day.

- If the QSE chooses to participate in the Real Time Balancing Market during the test, a revised set of base points (5 min) will be provided to ERCOT. Alternatively, individual unit’s participation of the balancing energy, in the form of participation factors may be provided. The purpose is to provide enough information for ERCOT to calculate unit base points on which the regulation is based during the test.

Note for consideration: Alternatively, can the QSE under test send to ERCOT Nodal system the Resource Base Points calculated by the QSE’s EMS via ICCP?  The calculation of the Resource Base Points by the QSE EMS will be based on a value of GTBD = Base Power Schedule + Balancing Deployment.

- Just prior to the test initiation, the QSE under test will participate in Ancillary Services Market as usual. The regulation participation percentage of QSE under test for the test hour will be one of the inputs to Nodal LFC during the following day’s testing.

- Intervals during which this testing occurs will not be included in the test QSE SCE performance monitoring.

During the Test:

- At the scheduled hour, the test will start (or if system conditions do not permit, the QSE or ERCOT may abort the test). The QSE under test will temporarily switch its effected Resources to receive instructions from the QSE’s nodal systems.

- ERCOT will input into the Nodal system base points prepared beforehand for the QSE under test. Ideally, SCED may be used to pass the base points to LFC, treating those Resources as self-scheduled.  Due to non-production quality data be utilized in 6-month LMP testing, SCED will not be utilized to optimize the system or provide base points to be used in LFC testing.

- ERCOT will input the Ancillary Service Obligation of the QSE under test into the Nodal system. This will be based on the results from previous day’s cleared Zonal Ancillary Service Market

- The Nodal LFC will receive the system frequency, compute the required regulation using the base points previously submitted by QSE under test, and send them out via ICCP.

- The Zonal LFC will continue to receive the system frequency, compute the required regulation and send them out to all QSEs.  QSE under test is responsible to control which system it takes control from either nodal or zonal.  Thus, a QSE under nodal testing will not be acting on the Zonal signals, but will continue to receive the zonal signals from the zonal system for reference purposes.

- ERCOT will use the Resource Qualification Testing function of the EMS Generation System to capture and store the base points, regulation and Resource outputs for the test hour.

- At the end of the hour, the QSE under test will switch the control back to Zonal and conclude the test.

After the Test:

- The base points, regulation, and generating unit outputs will be compiled.

- ERCOT will develop criteria to gauge the readiness of the Nodal LFC in controlling system frequency.

- The data captured and stored during the test will be sent to the respective QSEs under test.

- In Zonal settlement, QSE under test will not be subject to uninstructed deviation charges.

Note: The testing described above focuses on individual unit response for LFC. Additional discussion will need to occur concerning potential full system control utilizing the Nodal systems.

### LFC Timeline

The Load Frequency Control testing will be conducted during the high level timeline below. Each QSE will be scheduled in advance to coordinate the testing effort.

### LFC Testing Development Tasks

| # | Description | Who |
| --- | --- | --- |
| 1 | Develop LFC Testing approach | EDS 3 Team |
| 2 | Communicate and agree plan with TPTF | EDS 3 Team, TPTF |
| 3 | Obtain contacts to schedule LFC Testing: For each QSE | EDS 3 Team, QSE |
| 4 | Create checklist for each QSE/station to be LFC Tested | EDS 3 Team |
| 5 | Provide station checklists to QSE contacts | EDS 3 Team |
| 6 | Confirm schedule and identify operators that will perform the verification | EDS 3 Team, ERCOT Operations, TSP/QSE Operators |
| 7 | Perform the LFC Testing | ERCOT Operations, TSP/QSE Operators |
| 8 | Record results and issues | ERCOT Operations, TSP/QSE Operators |
| 9 | Analyze and resolve issues | EDS 3 Team |
| 10 | Submit Service Requests to resolve issues if required | QSE |
| 11 | Process Service Requests | ERCOT Operations |

### ERCOT LFC Test Sequence

| Phase | Activities | Incremental System / Features |
| --- | --- | --- |
| Preliminary Testing | - Software and communications testing - Calculation of ACE & comparison with existing control system - Validate EMS - Ability of QSE to receive Regulation Signal - QSE internal system / processing validation | EMS System w/ LFC upgrade (Not integrated with SCED) |
| LFC Testing | - Complete communication and resource dispatch control response capability - Individual resource performance evaluation with AS-monitor - ACE calculations | EMS Integrated with SCED (verified during the ERCOT quality control process) |

## Market Participant Readiness

Below are the key activities that are expected from each Market Participant before and during EDS Release 6.

- QSE EMS/MMS Nodal system or test nodal system changes (required for EDS3) complete

- QSE Ancillary Service Qualification complete

### Release 6 System Design

The following diagram represents a logical view of systems and their linkages available after Release 6 has been installed to the EDS environment.

The above diagram shows the configuration of the EDS environment to be used for LFC Testing.  The EDS environment will be upgraded to include an integrated package of the following applications

- EMS (Generation subsystem including, LFC, RLC, AS Mon)

- SCED (for base points)

## Entry Criteria

Before EDS 3 – Release 6 can begin; the following entry criteria (dependencies) must be met:

- Checkout of LFC related ICCP functionality up to QSE EMS

- QSE demonstrates ability of QSE’s EMS control of it’s own individual Resources

- QSE completes functionality upgrades to comply with ERCOT ICCP specifications

- Functioning ICCP, RLC, A/S Monitoring, LFC  and SCED

- Functioning interface between SCED and LFC

- QSE completion of resource qualification for Regulation Up and Down Ancillary Service

## Exit Criteria

Upon completion of LFC testing activities the following the criteria should be met:

- All qualified and participating Compare Area Control Error on EDS environment and existing control systems for seven days for accuracy

- All qualified QSEs demonstrate responsiveness of its Resources to control from ERCOT Nodal LFC

# Release 7 – Congestion Revenue Rights

## Description

This release addresses Section 5.4.5 (Trial Operation of Congestion Revenue Rights Auction) of the Nodal Transition Plan by testing the CRR Allocation and Auctions processing.

The objectives of the EDS CRR Testing are to:

- Demonstrate the ERCOT PCRR (Pre-assigned Congestion Revenue Rights) Allocation process

- Provide MPs the opportunity to create test bids for CRRs on Transmission Elements

- Execute Trial Auction for Monthly and Annual CRRs

- Assign test PCRRs / CRRs to Account Holders for DAM and RT Operations testing of Settlement Systems

## CRR Testing Approach

- The CRR testing follows an incremental approach for releasing functionality into the EDS environment by providing system functionality for Market Participants to begin testing as early as possible. The early deliveries provide Market Participants with tools to begin testing critical interfaces.

- Stand Alone CRR System (Starting Jan 2008) - The EDS environment will be upgraded to include a stand alone CRR environment to support uploading bids into the CRR system. The objectives of this phase are

- Registration of QSEs as CRR Account Holders

- Validate MP CRR Digital Certificate rights

- Validate Account Holder to upload Bids

- The environment will include the following capabilities:

- CRR User Interface for uploading Bids

- CRR bids validation

- Integrated CRR system (Starting March 2008) – Once CRR is integrated with other ERCOT systems; the EDS environment will be upgraded to include an integrated CRR system.  The objectives of this phase are

- Conduct mock CRR auction

- Validate allocation methodology

- Issue test PCRRs and CRRs to MPs

- Publish Mock CRR Invoices

- This phase of CRR testing will have the following system capabilities

- Publishing of mock CRR auction results in CSV / XML format

- In addition, the CRR system will be integrated with other Nodal systems such as

- NMMS

- CMM

- Registration

- EDW

- MIS

- CRR EDS final release (Starting Apr 2008) – Once the CRR application has been sufficiently tested by ERCOT and the Market Participants, we plan to run the monthly and annual CRR auctions.  The objectives of this phase are to provide capability to

  - Account holders to enter monthly and annual bids

  - Conduct monthly and multi-month CRR auctions

  - Conduct bilateral trading

  - Account holders test bidding strategy

  - View CRRs

  - Trial Invoicing of CRRs

### System Design

The following diagram shows the configuration of the EDS environment to be used for CRR Trial Auction.  The EDS environment will be upgraded to include an integrated package of the following applications

- CRR

- NMMS

- Credit Monitoring and Management

- Registration

- MIS

- EDW

### Timeline

The CRR Testing will be conducted as a part of the EDS 3 to the timeline shown below.

## EDS 3 Market Participant Readiness

- CRR Digital Certificate access requested

- CRR Account Holder:  Completed Registration with ERCOT

- CRR Account Established Credit Limit

## Entry Criteria

- Before EDS 3 – Release 7 can begin; the following entry criteria (dependencies) must be met:

- ERCOT will provide MPs a detailed handbook that describes the testing and trial activities

- MPs have registered as CRR account holders using the Nodal Registration System

- MPs obtain CRR Digital Certificate access

- MPs establish a test CRR Account Credit Limit

## Exit Criteria

- Test PCRRs / CRRs assigned to MPs for EDS 4

- Successful allocation and sale of CRRs to account holders based on bids and offers for each auction.

# Mock Settlement Statements

ERCOT shall begin publishing mock Settlements statements during EDS 3 to enable Market Participants to familiarize themselves with the format of the Statements.  Mock data will be used for this phase until S&B is integrated with the upstream systems to provide real data (EDS 4). The purpose of this is to only provide the settlement statement or invoice format.

The initial release of the Settlement Statements is intended to provide Market Participants the ability to view the Nodal Statements online through the UI and manually download XML formatted statements. Participants are not required to have any tools in place but should be developing any required Settlement tools for the May EDS Settlements activities. The sample downloads will help Participants complete and test their systems, specifically the download and processing of the mock statements.

Settlement Statements and Invoices are rolled up summaries.  Shadow Settlements and billing determinants are provided when EDW becomes available.

# Web Services / API

In support of the EDS development activities, ERCOT is making the external web services available to enable Market Participant development teams to test connectivity with ERCOT systems. The web services will be released on a parallel track prior to the EDS testing activities requiring connectivity. These tools will not be linked to the back-end systems for business rule validation until EDS.

The web services provide another critical tool for Market Participants to ensure EDS readiness.

The following shows the web services and the approximate release dates. The availability of web services will be communicated to MPs when available.

# Quality Expectations and Staffing

## Quality Expectations

ERCOT will employ a process of Quality Control Gates to build confidence in the quality of the available systems.  The process is displayed below:

- During the ERCOT quality control process, early software versions will be used for EDS testing that have not completed ERCOT's full quality control cycle

  - EDS Software versions will have known defects and additional defects discovered during EDS that will be incorporated into the internal release management schedule for prioritization and correction.

  - Potential for periods of reduced service level due to unexpected circumstances such as server failures.

- These systems will be available to the market for testing the processes required to run SCED, LFC and CRR.

- The EDS environment will be upgraded incrementally with new functionality coordinated with the internal release management schedule. Market Participants will be notified in advance of system upgrades and new functionality.

- System availability, quality of LMPs and other data and support responses will improve over time but may not likely meet production standards at the initial start.

## EDS 3 Staffing

The following organization chart illustrates the EDS 3 team structure and the interaction between EDS 3 team members and the QSEs:

Application Support Team – The application support team comprises members of the application development teams of EMS, MMS, NMMS, MIS & EDW. Their function is to support the application during SCED testing and to coordinate any vendor corrective action required.

EDS Execution Team – This team will handle the day to day management of the EDS activities and contact with the market participants.

- Issue Analysis and Resolution Team – This team will analyze and report on the outputs from the applications and coordinate any corrective actions when required.

Estimate of staff required for running LMPs include:

- Dispatch Operations staff to maintain continuous operation of Nodal Network Security Analysis and Transmission Constraint Management

- Staff to run SCED = 2 Operators from Dispatching and 1 SO engineer part time on call.

- Other SO & MP staff to cycle through to understand new environment and processes

- Development and project staff available to handle bug fixes and re-release of the application

The team is working on identifying the specific resources that be supporting the early EDS 3 activities. Some of the resources will be involved from the Nodal project teams and ERCOT business on a rotating basis. As the specific testing approaches a support and resource plan will be put in place.

# Protocol coverage and other test requirements

ERCOT shall demonstrate compliance to Nodal Protocols section 6.5.7 & 6.5.9 prior to the completion of EDS 3. As shown in Appendix 1.

# Appendix 1 – Protocol Coverage and testing requirements

| # | Protocol Ref # | Protocol Requirement | Testing Approach |
| --- | --- | --- | --- |
| 1 | 6.4.2 (3) | The entry of an Energy Offer Curve for a Resource automatically nullifies the Output Schedule for that Resource and prohibits entry of future Output Schedules for that Resource for the time during which the Energy Offer Curve is in effect | Validated during Project FAT Confirm during EDS |
| 2 | 6.4.2.3 (2) | ERCOT must reject an Output Schedule for a Resource if an Energy Offer Curve corresponding to any period in the Output Schedule exists | Validated during Project FAT Confirm during EDS |
| 3 | 6.5.7.1.11 | ERCOT shall develop a policy for setting maximum Shadow Prices for approval through the PRR process | Will be completed before the 168 hour test. |
| 4 | 6.5.7.1.12 | The following Generation Resource limits are calculated by ERCOT and used as inputs by the SCED process: - High Ancillary Service Limit (HASL) - Low Ancillary Service Limit (LASL) - Normal Ramp Rate by using the curve submitted by the QSE and the Resource’s MW telemetry - Emergency Ramp Rate by using the curve submitted by the QSE and the Resource’s MW telemetry - SCED Up Ramp Rate (SURAMP) - SCED Down Ramp Rate (SDRAMP) - High Dispatch Limit (HDL) (the Resource’s Real-Time generation plus the product of the Normal Ramp Rate at that Real-Time output level multiplied by five), restricted by HASL - Low Dispatch Limit (LDL) (the Resource’s Real-Time generation minus the product of the Normal Ramp Rate at that Real-Time output level multiplied by five), restricted by LASL | This will be delivered by the Project Team, but may need to be re-validated in the EDS environment to ensure that all pieces are available and working correctly. |
| 5 | 6.5.7.1.13 | Inputs: The following information must be provided as inputs to the Real-Time Sequence and SCED. ERCOT may require additional information as required, including - The calculated SCED Up Ramp Rate and SCED Down Ramp Rate are each greater than or equal to zero | This will be delivered by the Project Team, but may need to be re-validated in the EDS environment to ensure that all pieces are available and working correctly. |
| 6 | 6.5.7.2 (1) | Resource Limit Calculator: ERCOT shall calculate the HASL, LASL, SCED Up Ramp Rate (SURAMP), SCED Down Ramp Rate (SDRAMP), HDL and LDL within 4 seconds after a change of the Resource-specific attributes provided as part of the QSE’s SCADA telemetry under Section 6.5.5.2, Operational Data Requirements. | Will be validated to ensure this is working properly before starting EDS, to ensure SCED results |
| 7 | 6.5.7.3 (2) | The SCED solution must monitor cumulative deployment of Regulation Services and ensure that Regulation Services deployment is minimized over time | Will be verified before the 168 hour test. |
| 8 | 6.5.7.3 (3) | For use as SCED inputs, ERCOT shall use the available capacity of all committed Generation Resources by creating proxy Energy Offer Curves for certain Resources as follows: - Non-wind-powered Generation and Dynamically Scheduled Resources without Energy Offer Curves - Dynamically Scheduled Resources with Energy Offer Curves - Output Schedules - Non-wind-powered Generation Resources without full-range Energy Offer Curves - Wind-powered Generation Resource | ERCOT will create a test sequence and process to ensure this is working properly. Will need a number of Use Cases to test potential scenarios (limit raise  extend curve, Need to test Output Schedules for DSRs. |
| 9 | 6.5.7.3 (5) | The two-step SCED methodology is: - The first step is to execute the SCED process to determine Reference LMPs. In this step ERCOT executes SCED using the full Network Operations Model while only observing limits of Competitive Constraints. Energy Offer Curves for all On-Line Generation Resources, whether submitted by QSEs or created by ERCOT under this section is used in the SCED to determine “Reference LMPs.” - The second step is to execute the SCED process to produce Base Points, Shadow Prices, and LMPs, subject to security constraints (including Competitive and Non-Competitive Constraints) and other Resource constraints. - ERCOT shall archive information and provide monthly summaries of security violations and any binding transmission constraints (B4 168 hour) identified in Step 2 of the SCED process. | The Project team is determining the methodology for testing competitive constraints. |
| 10 | 6.5.7.4 | Base Points | Base points will be tested and published after LMP publishing begins. |
| 11 | 6.5.7.5 | Ancillary Services Capacity Monitor | This will be tested by the project team and will also be verified during the early phase of EDS 3 with live MP inputs. |
| 12 | 6.5.7.6.2.2 | Deployment of Responsive Reserve Service | Validated during Project FAT Confirm during EDS. |
| 13 | 6.5.7.6.2.3 | Non-Spinning Reserve Service Deployment | These dispatching procedures to be tested during the LFC testing phase. Currently assessing the impact of the NPRR & White Paper. |
| 14 | 6.5.7.8 (1) | Dispatch Procedures – - ONTEST | These dispatching procedures to be tested during the LFC testing phase. |
| 15 | 6.5.7.8 (8) | ERCOT shall record and file all electronic Dispatch Instructions and acknowledgements as soon as practicable after the issuance of the Dispatch Instruction. | Validated during LFC release. |
| 16 | 6.5.9 | Emergency Operations – - ERCOT, based on ERCOT System reliability needs, may issue a Dispatch Instruction requiring a Resource to move to a specific output level (“Emergency Base Point”). | Project teams will FAT test these test scenarios. In addition these emergency conditions will be tested with the MPs during EDS 3. A methodology white paper will be developed for EECP operation and testing. |
| 17 | 6.5.9.1 | Emergency and Short Supply Operation |  |
| 18 | 6.5.9.2 (2) | Failure of the SCED Process - For intervals that the SCED process fails to reach a solution, then the LMPs for the interval for which no solution was reached are equal to the LMPs in the most recently solved interval. |  |
| 19 | 6.5.9.2 (3) | Once ERCOT declares an Emergency Condition for a SCED process failure, ERCOT may use any of the following measures - ERCOT may direct the SCED process to relax the active transmission constraints - ERCOT may issue Emergency Base Points for Resources a. 5-min Emergency base point (MW) b. 5-min Emergency base point INDICATOR (STATUS) |  |
| 20 | 6.5.9.3.1 | Communication under Emergency Conditions – - operating conditions notices. The OCN is the first of four possible levels of communication issued by ERCOT in anticipation of a possible Emergency Condition. - Advisory - Alert - Emergency Notice |  |
| 21 | 6.5.9.4.1 | Emergency Energy Curtailment Plan - Maintain 2,300 MW of reserves |  |
| 22 | 6.5.9.4.2 | ERCOT shall continue EECP until sufficient offers are received and deployed by ERCOT to eliminate the conditions requiring the EECP and normal SCED operations are restored. Intermittent solutions of SCED do not set new LMPs until ERCOT declares that the EECP is no longer needed. |  |
| 23 | 3.18 | Resource Limits in Providing Ancillary Service (1) The HSL must be greater than or equal to the LSL and the sum of the Resource-specific designation of capacity to provide Responsive Reserve, Reg-Up and Non-Spin; (2) For Reg-Up, the amount of Reg-Up provided must be less than or equal to the HSL for Generation Resources and LPC for Load Resources minus the LSL for Generation Resources and MPC for Load Resources; (3) For Reg-Down, the amount of Reg-Down provided must be less than or equal to the HSL for Generation Resources and LPC for Load Resources of the unit minus the LSL for Generation Resources and MPC for Load Resources; and (4) For Non-Spin, the amount of Non-Spin provided must be less than or equal to the HSL for Generation Resources and LPC minus MPC for Load Resources; and (5) For Responsive Reserve Service: (a) The amount of RRS provided from a Generation Resource must be less than or equal to 20% of thermal unit HSL for an Ancillary Service Offer and must be less than or equal to 10 times the Emergency Ramp Rate; (b) Hydro-powered Resources operating in the synchronous condenser fast-response mode may provide RRS up to the Resource’s proved 20-second response (which may be 100% of the HSL); (c) For any hydro-powered Resource with a five percent droop setting operating as a generator, the amount of RRS provided may never be more than 20% of the HSL; and (d) The amount of RRS provided from a Load Resource must be less than or equal to the LPC minus the MPC. | This will be delivered by the Project Team, but may need to be re-validated in the EDS environment to ensure that all pieces are available and working correctly. |
| 24 | NA | Validation of additional input data to SCED other than resource limits - not the same as EDS1 or EDS2: a. Regulation deployment signal b. Responsive deployment signal c. Non-Spin deployment signal | Validated during Project FAT Confirm during EDS. |
| 25 | NA | Validation of SCED solutions - for QSE - not algorithmic since only ERCOT and their consultants can do it: a. Mapping from Resource Node (Settlement point) to resource b. Received 5-min LMP c. Received 5-min BP d. Relationship between LMP vs BP (for resources with output schedule/offer curve/RMR – or proxy curve) e. Combined Cycle – valid LMP and BP | To be tested during EDS 3 after LMP posting has commenced in November 2007. |
| 26 | NA | Validation of LFC 4-sec base point a. ramp from BP (t) to BP (t+1) b. Ramp rate validation c. Stop ramp validation (BP = actual gen) d. Operating Limit checks | To be tested by the project teams, and validated in the EDS environment after LFC and SCED are integrated. |

# Appendix 2 -  EDS Communication Activities