## Slide 1: COMS Nodal Commercial Systems Project Update
COPs Meeting
June 2007
Bill Barnes

## Slide 2: Agenda
Item | Purpose | Presentor
Deliverables Update | For Information | Bill Barnes
Delivery Schedule Update | For Information | Justin Rasberry
Questions | For Information | Bill and Justin

## Slide 3: COMS Requirements Update
ERCOT is currently syncing all projects to the March 2007 Protocols and a number of NPRRs and whitepapers (termed Baseline 1).
The baseline sync is needed to make sure all projects can communicate data appropriately with one another
Baseline 2 synchronization will start in July 2007. Activities around baseline 2 should conclude by August 2007
ERCOT is anticipating at least 3 baselines before Go Live
All associated documentation (use cases, CSDs, test cases, etc) will be updated as Baselines approved
New document naming convention will in place for all baseline 1 and future baseline versions.
COPs personnel should stay abreast with COMS requirements.

## Slide 4: COMS Requirements Update
The following COMS Requirements are approved by TPTF as version 1.1:
  AIEC
  DAM, 3 documents -- Energy, AS, and Make Whole
  RUC
  Eligibility
  Statements and Invoices, 2 documents
  Financial Transfer
  Real Time Operations, 6 documents – AS, Energy, Voltage, Emergency Operations, RMR, and Black Start
  Registration
The following COMS requirements version 1.1 were submitted at May 23 TPTF
  CRR Requirements – 4 documents
  Data Aggregation Requirements
The following COMS requirements version 1.1 will be submitted at the June 11 TPTF meeting
  CMM Requirements and CSD
All documents are going through the TPTF approval cycle and should be updated by July 2007

## Slide 5: COMS CSD Update
The following COMS Conceptual System Designs (CSDs) were being submitted to TPTF as version 1.1 on May 23:
  Registration
  AIEC
  CRR
  DAM
  Eligibility
  Financial Transfer
  Statements
  Invoices
  RUC
The following COMS Conceptual System Design (CSDs) were being submitted to TPTF as version 1.1 on May 23:
  CMM

## Slide 6: COMS Use Case and Mini Market Examples Update
ERCOT has not received any comments on Use Cases
  Has anyone reviewed them
  Any feedback ??
  Are groups having difficulty understanding them
Nodal Settlements Mini Market Examples - in progress
  Published end of June
  Dedicated SDAWG meeting for review Mid July

## Slide 7: Development Update
Detailed Design on task
  Should have drafts of Detailed Design documents by 2Q2007
  Functional Decompositions completed in April 2007 on base coding
Lodestar version 4.7 successfully delivered in April 2007
  Code base which will be used to build Nodal
  Have had a number of defects and working Lodestar to correct
Lodestar metadata changes version 1 submitted April 2007
  Significant number of new tables and columns submitted to support Nodal
  Metadata changes have been delivered to ERCOT and applied to Lodestar 4.7 schema
Should have Statements and Invoice mock displays ready for COPs/TPTF by July 2007
Plan to start unit testing as early as Summer 2007 to meet EDS timeline
  Initial testing at the Modular level and will “build up” to batch

## Slide 8: Development Update
Most build packages consists of multiple modules
  Modules aligned into business functional components (i.e. DAM Energy, DAM AS, CRR, etc.)
Target FAT completion by mid 4th quarter 2007
Target SAT completion by early 1st quarter 2008
Currently, Lodestar S&B slated for EDS 3 & 4
  Statements and Invoice format for EDS 3
  Shadow Settlements EDS 4 (requires Extracts)
Settlements Go Live with 1st CRR auction

## Slide 9: Question ??