## Qualification
| Document Name: | Response to TN EDW ComplianceRequirementsSpecification v0.06.doc
| Issuing Entity | Page Number | Description | Accepted / Rejected | Reviewer | Reason
1 | Center Point | p.1 | 1. All of the compliance requirements are very lacking in specifics. | Accepted | S. Privette | The process for defining the content of each report or extract is breifly described below: 1.) Get approval of the requirement. 2.) ERCOT Business representative will be responsible for working with TPTF to define content/metrics of report or extract. 3.) The Nodal PMO/IDA function will ensure that each compliance report or extract is accepted as a requirement of the Nodal team which is delivering the source system. 4.) Nodal Project teams will contract with EDW team for creation and/or delivery of report or extract to MIS. 5.) The EDW project or source system delivery team will convey delivery dates for each line item listed in the Section 8 Requirements to include all in Appendix A.
2 | Center Point | p.1 | 2. CNP highly recommends that ERCOT work with market participants directly impacted by a metric as they are being developed. Stakeholder meetings (live and via WebEx) would be beneficial in the detailed development. | Accepted | S. Privette | The process for defining the content of each report or extract is breifly described below: 1.) Get approval of the requirement. 2.) ERCOT Business representative will be responsible for working with TPTF to define content/metrics of report or extract. 3.) The Nodal PMO/IDA function will ensure that each compliance report or extract is accepted as a requirement of the Nodal team which is delivering the source system. 4.) Nodal Project teams will contract with EDW team for creation and/or delivery of report or extract to MIS. 5.) The EDW project or source system delivery team will convey delivery dates for each line item listed in the Section 8 Requirements to include all in Appendix A.
3 | Center Point | p.1 | 3. The date each metric is going to become effective should be listed in this document and the implementation dates must be in compliance with new Zonal Protocol section 21.12 Process for Transition to Nodal Market Protocol Provisions and Nodal Protocol section 1.1 (2)(b) Summary of ERCOT Protocols Document. | Accepted | S. Privette | The metrics identified in the process listed above will become effective at market GO-LIVE.
4 | Center Point | p.1 | 4. Only Protocol sections 8.1 QSE/Resource Performance Monitoring and Compliance and 8.3 TSP Performance Monitoring and Compliance metrics are listed. Protocol section 8.2 ERCOT Performance Monitoring and Compliance metrics are missing. Will they be added later? | Accepted | S. Privette | Section 8.2 requirements are listed individually in Appendix A (starting on page 57), and have been identified as being approved in MIS and EMS requirements docuuments.
5 | Center Point | p.1 | 5. Section 5 Protocol Coverage – the FR-C numbers are skewed. TSP metrics are listed as FR-C39 through 48, but they should be FR-C35 through 44. | Accepted | S. Privette | Problem is the row alignment. In section 5 Protocol Coverage the items referencing Nodal Protocol Section 8.3 have been changed to TSP Performance Monitoring and Compliance Section 8.5.1.2 have been changed to Reporting Section 8.5.2 have been changed to Primary Frequency Control Measurements.
6 | TXU | p.1 | This document appears to identify the Section 8 performance requirements; however, many of the table entries are “Description not available”. | Accepted | S. Privette | The process for defining the content of each report or extract is breifly described below: 1.) Get approval of the requirement. 2.) ERCOT Business representative will be responsible for working with TPTF to define content/metrics of report or extract. 3.) The Nodal PMO/IDA function will ensure that each compliance report or extract is accepted as a requirement of the Nodal team which is delivering the source system. 4.) Nodal Project teams will contract with EDW team for creation and/or delivery of report or extract to MIS. 5.) The EDW project or source system delivery team will convey delivery dates for each line item listed in the Section 8 Requirements to include all in Appendix A.
6 | TXU | p.1 | 1. the assurance that the EMS and MMS teams are aware of the need to support the performance monitoring requirement in their system designs and that the required data elements are either calculated and the results captured or component data elements are captured for use in after-the-fact performance calculations. An example of the detail needed is the COMS Business Requirements in which the data elements that are the responsibility of a source system are identified; and 2. the need in this requirement to clearly identify each system’s (EMS, MMS, EDW) responsibility assignments. | Accepted | S. Privette | The process for defining the content of each report or extract is breifly described below: 1.) Get approval of the requirement. 2.) ERCOT Business representative will be responsible for working with TPTF to define content/metrics of report or extract. 3.) The Nodal PMO/IDA function will ensure that each compliance report or extract is accepted as a requirement of the Nodal team which is delivering the source system. 4.) Nodal Project teams will contract with EDW team for creation and/or delivery of report or extract to MIS. 5.) The EDW project or source system delivery team will convey delivery dates for each line item listed in the Section 8 Requirements to include all in Appendix A.
7 | TXU | p.1 | Finally, TPTF needs to decide whether approval of the document can be made when so much of the detail remains to be determined. It would be helpful, in this regard, to understand the timeline and project needs for EDW in the context of the overall nodal project timeline. | Accepted | S. Privette | The EDW CSD has listed the timelines associated with the delivery of source system components. The EDW Project will provide an overall project deliverables timeline to the TPTF for the compliance items that are generated from the EIS systems or stored in the Market Information Repository for distribution through the MIS portal.