## Slide 1: Texas SET Version 3.0 Production Implementation Plan

## Slide 2: Table of Contents
Shutdown Procedure
Use of Reconnects for Non-payment and Option 1 Outage Request
Use of Safety Net
Consolidated Transaction Shutdown Timeline (chart)
All CRs Shutdown Tasks
All TDSPs Shutdown Tasks
ERCOT Shutdown Tasks
Market Conference Calls
<number>

## Slide 3: Shutdown Procedure
The shutdown times listed will be strictly adhered to
All MPs should submit transactions well in advance of the shutdown time so that large transaction volumes are not experienced just prior to shutdown
  (i.e. if you run batch jobs, schedule them throughout the day)
All MPs shall call-in to each conference call, on-time, during the implementation.
All times listed are Central Prevailing Time
<number>

## Slide 4: Use of Reconnect for Non-Payment & Option 1 Outage Request
For Reconnects for Non-Payment during Version 3.0 conversion weekend, CRs shall use the appropriate Emergency Reconnect for Non-Payment Procedures as outlined for each TDSP in the Retail Market Guide (Emergency Reconnect Section 7.6.5.1). Link: http://www.ercot.com/mktrules/guides/retail/2007/04/07/07-040107.doc#_Toc157581304
If the TDSP’s Emergency Reconnect for Non-Payment Procedures instructs the CR to use the Emergency Reconnect Request Spreadsheet (Retail Market Guide Appendix C2) and the CR cannot include the actual BGN02 then the BGN02 must be provided in the following format (cannot exceed 30 characters):
  First 3 spaces= V30
  Next 3 spaces= Abbreviated CR name
  Then followed by a unique number for each transaction.
    NOTE: CenterPoint Energy will not accept Priority Reconnects for Non-Payment until after Version 3.0 is implemented that would include the Emergency Reconnect Request spreadsheet during conversion weekend.
As of Monday, June 25th at 8:00 AM or as soon as Version 3.0 transactions begin to flow, TDSPs will no longer support Emergency Reconnect for Non-Payment Spreadsheets in lieu of a 650_01 Reconnect for Non-Payment TX SET transaction.
Option 1 CRs for Outages are not affected by this version release, therefore Outage Option 1 CRs will continue to send outage transactions/notifications to the TDSPs as normal throughout conversion weekend.
<number>

## Slide 5: Use of Safety Net
Beginning Friday, June 22nd at 12:00 pm, the CR will utilize the approved Safety Net process during implementation with a default BGN02 value to request Move-Ins with requested dates during migration period. If the REP cannot include the actual BGN02, the BGN02 must use the following format (cannot exceed 30 characters):
  First 3 spaces= V30
  Next 3 spaces= Abbreviated CR name
  Then followed by a unique number for each transaction
CRs will be required to follow up with the corrected BGN02 on a Safety Net correction to the TDSP once their actual BGN02 is available.
The TDSPs will no longer accept default BGN values on Monday, June 25th at 8:00 am or as soon as Version 3.0 transactions begin to flow.
<number>

## Slide 6: Use of Safety Net
CRs must send Priority Safety Net MVI spreadsheets at least every 2 hours during system downtime.
  NOTE: CenterPoint Energy only will not accept Priority MVIs until after Version 3.0 is implemented that would include Priority Safety Net spreadsheets during conversion weekend.
CRs must send Standard Safety Net MVI spreadsheets by noon and 4:00 pm CPT each day
After Version 3.0’s Implementation, if CRs send Standard 814_16 MVI transaction with requested MVI date of 6/25 or 6/26 “scooching” will be in effect. If the CR is requesting a Move-In date of Monday 6/25/2007 or Tuesday 6/26/2007 they will need to send the 814_16 MVI transaction as a Priority MVI.
<number>

## Slide 7: Consolidated Transaction Shut-Down Timeline
<number>

## Slide 8: Consolidated Transaction Shut-Down Timeline
<number>

## Slide 9: Consolidated Transaction Shut-Down Timeline
<number>

## Slide 10: Consolidated Transaction Shut-Down Timeline
<number>

## Slide 11: All CRs Tasks & Shut-down Timeline
8:00 AM CPT - Tuesday, June 19, 2007
  CRs will stop sending 650_01 Disconnect for Non-Payment (DNP) Transactions
12:00 PM CPT – Friday, June 22, 2007
  CRs suspend sending the following transactions:
    814 transactions to ERCOT (both EDI and through TML)
    814_PC transactions
    650_01 transactions (650_01 Disconnects for Non-Payment (DNP) should have already been suspended as of 8:00 AM Tuesday, June 19.)
  CRs begin using Safety Net process for submitting MVIs with a requested date of June 23 through June 26
<number>

## Slide 12: All CRs Tasks & Shut-down Timeline
1:00 PM CPT - Friday, June 22, 2007
  CRs suspend sending 997s for 650_04 transactions
  CRs suspend the following transactions:
    650_05
    824
5:00 PM CPT – Friday, June 22, 2007
  CRs suspend sending 997s for 810_02/03 transactions
  CRs suspend 820_02 (810_03MC) transactions
<number>

## Slide 13: All TDSPs Tasks & Shut-down Timeline
5:00 PM - Wednesday, June 20, 2007
  TDSPs (except ONCOR) will flush systems to cancel all pending 650 DNPs and send complete unexecutables to CRs
5:00 PM - Thursday, June 21, 2007
  ONCOR will flush systems to cancel all pending 650 DNPs and send complete unexecutables to CRs
<number>

## Slide 14: All TDSPs Tasks & Shut-down Timeline
12:00 PM CPT – Friday, June 22, 2007
  TDSPs suspend sending the following transactions:
    650_04 Transactions
    814_20 Transactions
1:00 PM CPT – Friday, June 22, 2007
  CRs suspend sending 997s for 650_01, 814_PC transactions
  TDSPs suspend sending the following transactions:
    867s and 814 responses
    814_PD Transactions
    650_02 Responses to CRs this includes 650_02 Reconnect for Non-Payment Responses
2:00 PM CPT – Friday, June 22, 2007
  TDSPs suspend sending 997s for 650_02/05, 814_PD, 824 transactions
5:00 PM CPT – Friday, June 22, 2007
  TDSPs will stop sending 810_02 (820_03MC) Transactions
<number>

## Slide 15: ERCOT’s Tasks & Shut-down Timeline
12:00 PM CPT - Friday, June 22, 2007
  ERCOT will shut down inbound processing of initiating transactions. Inbound response transactions will continue to be processed. ERCOT will continue to process outbound transactions.
5:00 PM CPT – Friday, June 22, 2007
  ERCOT will shut down outbound processing
  ERCOT sends out system shutdown email to market (Note: this email notice will be sent out as soon as outbound transactions have completed processing). Retail systems to be shutdown will include MarkeTrak, API, Report Explorer, and TML.
<number>

## Slide 16: Conference Call Times
Conference Call Information
  800-211-0633 password: 844736
  Press ‘*6’ to mute/un-mute phone
Thursday June 21st 4:00pm
  ERCOT transaction processing update
      “in queue”
      “in process”
      Overall system health
  CRs and TDSPs to provide status (state of systems and processing)
  Confirm DNPs are suspended
<number>

## Slide 17: Conference Call Times
Friday June 22nd 1:00pm
  ERCOT confirmation of initiating transactions suspension
  Confirm Safety Net Spreadsheet is being utilized for MVI Request
  Update on transaction processing
  ERCOT transaction processing update
      “in queue”
      “in process”
      Overall system health
<number>

## Slide 18: Conference Call Times
Saturday June 23rd 6:00 pm –(This may be moved to Sunday based on the code migration duration times)
  Market Participants provide migration status
  Go/No Go Decision from Market Participants and ERCOT, % complete of production verification
<number>

## Slide 19: Conference Call Times
Sunday June 24th 10:00 am
  Market Participants provide migration status
Sunday June 24th Time TBD
  ERCOT provides time at which ERCOT will begin accepting V3.0 transactions
  CRs and TDSPs provide migration status
  If a Market Participant is not ready will use this time to establish the next conference call
<number>