Texas Set Version 3.0

Implementation and Contingency Plan

FINAL

V3.0 Market Coordination Team

Version 1.3

Revision History

| Date | Version | Description |
| --- | --- | --- |
| 04.12.2007 | 1.0 | First draft |
| 05.24.2007 | 1.1 | Modifications made at 05/24 MCT meeting |
| 06.05.2007 | 1.2 | Modifications from MCT Conference Call |
| 06.07.2007 | 1.3 | FINALIZED |

Table of Contents

Version 3.0 Implementation Schedule	3

ERCOT and TDSP Contingency Plan	6

CR Contingency Plan	7

# Version 3.0 Implementation Schedule

The following table provides an overview of the weekend schedule for the Texas SET Version 3.0 Implementation Plan.  These times were pulled from the implementation plan developed by the Texas SET Market Coordination Team.

In the event of force majeure (e.g. fire, hurricane, tornado, etc.), the market will consider rescheduling Texas SET 3.0 implementation for the contingency weekend of June 30 – July 1.

Conference Call Number:  800-211-0633

Password:  844736

Press ‘*6’ to mute/un-mute phone

| Tuesday, June 19, 2007 |  |  |  |
| --- | --- | --- | --- |
| Time | Task | Entity | Complete (Y or N) |
| 8:00 AM | CRs suspend sending 650_01 DNP Transactions - Pending DNPs will continue to be worked according to the DNP procedures | All CRs |  |
| Wednesday, June 20, 2007 |  |  |  |
| Time | Task | Entity |  |
| 5:00 PM | TDSPs (except ONCOR) will flush systems to cancel all pending 650 DNPs and send complete unexecutables to CRs | All TDSPs |  |
| Thursday, June 21, 2007 |  |  |  |
| Time | Task | Entity |  |
| 4:00 PM | 1st Market Conference Call - Confirm DNPs are suspended | All MPs |  |
| 5:00 PM | ONCOR will flush systems to cancel all pending 650 DNPs and send complete unexecutables to CRs | All TDSPs |  |
| Friday, June 22, 2007 |  |  |  |
| Time | Task | Entity |  |
| 12:00 PM | CRs suspend sending 814 transactions to ERCOT (both EDI and through TML) | All CRs |  |
|  | CRs begin using Safety Net process for submitting MVIs with a requested date of June 23 through June 26 | All CRs |  |
|  | ERCOT shuts down inbound processing of initiating transactions. Inbound response transactions will continue to be processed. ERCOT will continue to process outbound. | ERCOT |  |
|  | CRs suspend 814_PC transactions | All CRs |  |
|  | CRs suspend 650_01 transactions | All CRs |  |
|  | TDSPs suspend 650_04 transactions | All TDSPs |  |
|  | TDSPs suspend 814_20 transactions | All TDSPs |  |
| Friday, June 22, 2007 |  |  |  |
| Time | Task | Entity |  |
| 1:00 PM | 997s suspended for 650_01/04, and 814_PC transactions | All MPs |  |
|  | TDSPs suspend 867s and 814 responses | All TDSPs |  |
|  | CRs suspend 824 transactions | All CRs |  |
|  | TDSPs suspend 814_PD transactions | All TDSPs |  |
|  | TDSPs suspend 650_02 transactions | All TDSPs |  |
|  | CRs suspend 650_05 transactions | All CRs |  |
|  | 2nd MCC - ERCOT confirmation of transaction suspension. Update on transaction processing | All MPs |  |
| 2:00 PM | 997s suspended for 650_02/05, 814_PD, 824 transactions | All MPs |  |
| 5:00 PM | TDSPs suspend 810_02 (820_03MC) transactions | All TDSPs |  |
|  | 997s suspended for 810_02/03 transactions | All MPs |  |
|  | CRs suspend 820_02 (810_03MC) transactions | All CRs |  |
|  | ERCOT Shuts down outbound processing | ERCOT |  |
|  | ERCOT sends out System Shutdown email to market. Retail systems to be shutdown will include MarkeTrak, API, Report Explorer, and TML. | ERCOT |  |
| Saturday, June 23, 2007 |  |  |  |
| Time | Task | Entity |  |
| 6:00 PM | 3rd MCC - MP Migration Status - ERCOT Go/No Go Decision | All MPs |  |
| Sunday, June 24, 2007 |  |  |  |
| Time | Task | Entity |  |
| 10:00 AM | 4th MCC - MP Migration Status | All MPs |  |
| TBD | 5th MCC - Determine if additional CC necessary. Confirm Market Readiness. | All MPs |  |

# ERCOT and TDSP Contingency Plan

Should ERCOT or a TDSP fail to successfully implement Texas SET Version 3.0 the Market will be notified on Saturday, June 23rd on the 6:00 PM Market Participant Conference Call.  ERCOT and TDSPs will indicate on the 6:00 PM Market Participant Conference Call whether they need additional time for code migration.  In this event, another Market Participant Conference Call will be scheduled for a later time on Saturday evening for a migration status update.  If ERCOT or a TDSP is unable to migrate to Version 3.0, ERCOT or the TDSP will not reject Version 3.0 transactions and will hold them or work them manually until they can implement Texas SET Version 3.0.

# CR Contingency Plan

Should a CR fail to successfully implement Texas SET Version 3.0, the Market will be notified on a Market Participant Conference Call.  The CR will coordinate a migration to minimize any potential impact to the rest of the Market.  The CR will not reject Version 3.0 transactions and will hold them or work them manually until the CR can implement Texas SET Version 3.0.