## -- RO --
Proposed 2008 RO Project Prioritization - PUCT, Market and ERCOT Projects
From CBA (work in progress)
Source | Committee | Prog Area | Source Doc | Project | Project No. | Current Status | Project Manager | 2008 Priority | 2008 Rank | 2008 Budget | 2008 Running Total | 2009 Budget | 2007 Priority | 2007 Rank | Original 2007 Budget Range | 2007 Running Range | 2006 Priority | 2006 Rank | 2006 Budget Range | Nodal Impact | Nodal Impact Comments | Priority Approval | 2005 Priority | 2005 Rank | CBA Score | Net Benefit | ERCOT Cost | ERCOT Benefit | Market Cost | Market Benefit | Summary Description | Benefit Summary | Market comments_05232007 Mtg. | ERCOT COMMENTS
PUCT | RMS | RO | PUCT Project 24462 | Performance Measures Reporting Requirements (changes to Project 24462) | 60007_01 | Not Started |  | 0 - Previously Approved | 0.1 | $500k-$1M | $0 - $1M |  | 2 - High | 9.5 | $1M-$3M | $6M-$7M | 1.1 | 9 | [6 empty] | 18 | -1000000 |  |  |  |  | Expected project needed to enhance reporting systems as a result of T&Cs requirements effecting PUCT Performance Measures Project 24462 | TBD
ERCOT | RO | RO |  | Registration Data Model Enhancement | 60015_01 | Initiation | Parrish | 0 - Previously Approved | 0.2 | $100k-$250k | $1M - $2M |  | 0 - Carryover | 3 | $100k-$250k | $0 - $1M | 1.1 | 23 | [6 empty] | 18 | 890000 |  |  |  |  | Normalize type of data associated to business objects. Multiple business objects are using the same tables which are growing large causing performance and scalability issues. | Increased efficiences in development and integration time as well as end user interaction (approximately 12 hours per day) |  | Project Name change from ESIID Account Table Split to Registration Data Model Enhancement approved at 05/24 CART-
ERCOT | RO | RO |  | Data Research and Reporting | 50088_01 | Planning | Day | 0 - Previously Approved | 0.3 | $500k-$1M | $1M - $2M |  | 0 - Carryover | 5 | $500k-$1M | $1M - $2M | 1.1 | 29 |  |  |  |  | 2.3 | 106 | 21 | 1200000 |  |  |  |  | Transition of ETS reporting from Data Archive to Enterprise Data Warehouse | Improved reporting and analysis efficiency (7 hours per workday); Improved development efficiencies (16 hours per workday) |  | Project Name change from ETS Transition to EDW to Data Research and Reporting approved at 05/24 CART
ERCOT | RO | RO |  | EDW EAI Transition (inc. PaperFree & NAESB) | 50061_02 | Planning | Day | 0 - Previously Approved | 0.4 | $100k-$250k | $1M - $2M |  | 0 - Carryover | 6 | $250k-$500k | $1M - $2M | 1.1 | 28 |  |  |  |  | 2.1 | 72 | 23 | 740000 |  |  |  |  | Transition of EAI reporting from Data Archive to Enterprise Data Warehouse | Fewer ad hoc data requests (4 hours per workday), less production support of data archive (4 hours per workday), improved daily research of Siebel service order changes (8 hours per workday) |  | Project Number Approved from 50061_01 to 50061_02 at 05/24 CART for split of project deliveries between 2007 and 2008
Market | RMS | RO | PRR672 PRR707 | Terms and Conditions requirements, not limited to Texas SET changes | 60008_01 | Initiation | Parrish | 0 - Previously Approved | 0.5 | $250k-$500k | $1M - $2M |  | 2 - High | 8.5 | $250k-$500k | $2M - $3M | [14 empty] | Proctocol Timing changes not Covered by TX SET 3.0 (PRR672, 693, 707)
Market | RMS | RO | SCR749 | MarkeTrak Enhancements (Workflow & Reporting) | 70007_01 | Initiation | Parrish | 0 - Previously Approved | 0.6 | $500k-$1M | $2M - $3M |  | 2 - High | 9 | $500k-$1M | $3M - $4M | N/A | N/A | [6 empty] | 16 | 740000 |  |  |  |  | Enhancements to the functionality of MarkeTrak | Reduce manual workarounds for efficient use of Retail Customer Choice resources, improve reporting capabilities, enhance workflows and improve validations for ERCOT and Market Participants.
ERCOT | RO | RO |  | Exception Reporting / Monitoring Enhancements | 70008_01 | Not Started |  | 0 - Previously Approved | 0.7 | $100k-$250k | $2M - $3M |  | 2 - High | 10 | $250k-$500k | $3M - $4M | N/A | N/A | [6 empty] | 9 | 400000 |  |  |  |  | Automate current exception reporting to monitor protocol compliance for processing exceptions. Create new exception reports using new data available from RBP and/or EDW projects. | Exception reporting in Retail Customer Choice has been very manual. There are protocol requirements that may not be met due to the lack of logging after the processing occurs.
ERCOT | RO | RO |  | Systematic Exception Reprocessing Functionality | 70009_01 | Not Started |  | 0 - Previously Approved | 0.8 | $250k-$500k | $3M - $4M |  | 2 - High | 11 | $500k-$1M | $4M - $5M | N/A | N/A | [6 empty] | 8 | 40000 |  |  |  |  | Automate current exception processing to meet protocol. Create reporting features after processing occurs. | Exception processing in Retail Customer Choice has been very manual. There are protocol requirements that may not be met due to the manual efforts.
Market | RMS | RO |  | Advanced Metering - RMWG/TX SET | New | Not Started |  | 1 - Critical | 1 | $250k-$500k | $3M - $4M |  | NA | [17 empty] | TX SET changes related to Advanced Metering |  |  | If it is relegated to PaperFree/TX SET mapping changes only that would be a good swag. If there is change in business logic in other systems, add a lot of SAS70 verifications or add additional external reporting then budget would go up. Requirements are needed to determine this.
Market | RMS | RO |  | Small renewables - RMWG | New | Not Started |  | 1 - Critical | 1 | $250k-$500k | $4M - $5M |  | NA | [17 empty] | TX SET changes related to small renewables |  |  | If it is relegated to PaperFree/TX SET mapping changes only that would be a good swag. If there is change in business logic in other systems, add a lot of SAS70 verifications or add additional external reporting then budget would go up. Requirements are needed to determine this.
ERCOT | RO | RO |  | Enrollment Postcard Notification Process | New | Not Started |  | 2 - High | 2 | $100k-$250k | $4M - $5M |  | NA | [17 empty] | Re-Write the enrollment postcard/notification process internally at ERCOt for Efficiency Reliability and stability to mitigate current compliance issues occurring today. | Enhancements to enrollment postcard/notification process. Concise documentation of business requirements • Improved testing abilities • Improved production support (including the creation of a Service Level Agreement) • Improved exception handling • Education of new team members Process portability Bringing the process into compliance with recent technology changes (RBP) | Market request to provide the benefits to aide in prioritizing with others. | Updated Name as requested
ERCOT | RO | RO |  | EDI Transaction logging | 60062_01 | Not Started |  | 2 - High | 3 | $100k-$250k | $4M - $5M |  | 3 - High / Medium | 17 | $100k-$250k | $9M-$10M | 2.2 | 128 | [6 empty] | 14 | 75000 |  |  |  |  | Change the Paper Free application system to log all ANSI records to TRLOG and to log all TXSET records to a new table which will better support current and future business needs. | Improve performance and accessibility of data. The suggested changes in the logging details will allow users to access the data without needing a cross-reference sheet telling them what the columns are in TRLOG and what data (per transaction type) is being logged to them. | recommended to prioritize above xml portal rewrite.
ERCOT | RO | RO |  | 814 inbound XML rewrite (impacts input from portal only) | 60043_01 | Not Started |  | 2 - High | 4 | $100k-$250k | $4M - $5M |  | 3 - High / Medium | 16 | $100k-$250k | $8M-$9M | 1.3 | 92 | [6 empty] | 13 | 440000 |  |  |  |  | Re-Write of Inbound 814 XML maps to Increase Efficiency, Reliability and Stability of ERCOT transaction data processing. | Our experience with splitting the inbound 814 X12 maps has shown that reducing the complexity of the map (by implementing clean flowing logic) can reap significant performance gains. The time to analyze and correct any logic errors has been decreased by as much as 10 times the original completion times with the original logic. In addition the overall number of defects that are/were created from attempts to correct logic or implement enhancements has also been greatly reduced.
ERCOT | RO | RO |  | Commercial Apps - Calendar Consolidation | 60033_01 | Not Started |  | 2 - High | 5 | $250k-$500k | $4M - $5M |  | 3 - High / Medium | 20 | $250k-$500k | $10M - $11M | 1.2 | 69 |  |  | - |  |  |  | 23 | 740000 |  |  |  |  | Develop single business calendar for use by all retail applications | Reduced rework for both market and ERCOT by eliminating possibility of out of sync conditions between multiple business calendars (50 hours per year of data repair activity for CRs and TDSPs)
ERCOT | RO | RO |  | Name to DUNS conversion | 60059_01 | Not Started |  | 2 - High | 6 | $100k-$250k | $4M - $5M |  | 4 - Medium | 21 | $100k-$250k | $11M - $12M | 2.1 | 120 | [6 empty] | 14 | 14000 |  |  |  |  | Change the Paper Free application system to utilize DUNS numbers as opposed to Market Participant company names. | Consistent naming standards within Paperfree system.
ERCOT | RO | RO |  | MP configuration Table | 60060_01 | Not Started |  | 2 - High | 7 | $100k-$250k | $5M - $6M |  | 4 - Medium | 22 | $100k-$250k | $12M - $12 | 2.1 | 122 | [6 empty] | 18 | -300 |  |  |  |  | Remove all of the MPDB.conf files in the MB/PF systems and consolidate all of the configurations into a single table. The complexity of adding new MP to the system must be reduced in order to remove the number of errors that are encountered when adding / modifying MP information. | The complexity of adding new MP to the system must be reduced in order to remove the number of errors that are encountered when adding / modifying MP information.
ERCOT | RO | RO |  | MarkeTrak phase 3 | New | Not Started |  | 2 - High | 8 | $100k-$250k | $5M - $6M |  | NA | [17 empty] | Expand capabilities and efficiencies of the MarkeTrak Retail Issue Resolution System. ERCOT wants to leverage upgrades from Serena.
ERCOT | RO | RO |  | Retail application upgrades | New | Not Started |  | 2 - High | 9 | $500k-$1M | $6M - $7M |  | NA | [17 empty] | Application upgrades not covered within other projects on the PPL IE: Oracle 10g, PFREE, Siebel, TIBCO, etc.
2008 Resource Capability Line - $6.1M
Market | RMS | RO |  | TEXAS SET 3.0 (mandatory fixes) - TX SET | New | CANCEL |  | DELETE | Pending Removal | NA |  |  | NA | [17 empty] | Mandatory oversite from 3.0 |  |  | Recommended for Cancel to mitigate "place holder" projects. Need to be able to quantify anything other than Parking Lot to determine capabilities. Rulings should be available. MP agreed to cancel 5/30 RMS Agenda Planning Call.
Market | RMS | RO |  | Other legislative impacts/PUCT - All | New | CANCEL |  | DELETE | Pending Removal | NA |  |  | NA | [17 empty] | TBD |  |  | Recommended for Cancel to mitigate "place holder" projects. Need to be able to quantify anything other than Parking Lot to determine capabilities. Rulings should be available. Any urgent items that come up will be re-ranked and prioritized throughout the year. MP agreed to cancel on05/30 RMS Agenda Planning Call.
ERCOT | RO | RO |  | 867 inbound map rewrite | 60042_01 | CANCEL |  | DELETE | Pending Removal | NA |  |  | 3 - High / Medium | 14 | $100k-$250k | $7M-$8M | 1.3 | 89 | [6 empty] | 11 | 6900 |  |  |  |  | Re-Write of Inbound 867 maps to Increase Efficiency, Reliability and Stability of ERCOT transaction data processing | Development Costs will be reduced for enhancements and maintenance of this code following the re-write as overall analysis time will be reduced, maintenance coding and re-coding time reduced, enhancement coding time reduced, and overall errors resulting from changes made to code reduced. | possible combine with advanced metering? | Moved effort to MO Project ERCOT System Throughput for IDR
Market | RMS | RO |  | Training for IAGs | CANCEL | Not Started |  | DELETE | Pending Removal | NA | [22 empty] | recommended to include in 101 and other training efforts. Training is generally nt considered project capital effort.
Market | RMS | RO | SCR745 | ERCOT Outage Evaluation and Resolution (TDTWG)--Phase III | 60006_02 | Not Started |  | 9 - Parking Lot |  | $1M-$3M |  |  | 9 - Parking Lot |  | $1M-$3M | $12M - $13M | 1.2 | 58.5 |  |  |  | BoD 12/13/05 |  |  | 24 | 25000000 | 1500000 |  |  |  | Identify market facing servers without redundancy. Implement new code and hardware when possible to eliminate single points of failure. This will include clustering market facing servers and implementing code which will be able to switch from one system to the other without an outage. This project may be addressed in SCR-745 | Savings based on cost estimates of data cleanup due to outages: 4 large incidents per year at $25k each; 20 small incidents per year at $5k each. | recommended to discuss with architecture to confirm f this is covered by other efforts (nodal/AIX) | recommended by ERCOT to assign parking lot until AIX stabilization. Will re-evaluate the validity of this project in q407.
Market | RMS | RO |  | NAESB Failover - TDTWG | New | Not Started |  | 9 - Parking Lot |  | TBD | [22 empty] | TDTWG workshop to be scheduled. Recommended to followo up with chair and possibly not enough info to place on 2008 RO.
Market |  | RO |  | Create Retail XML Transaction Format to MPs - set the national standard | 60065_01 | Not Started |  | 9 - Parking Lot |  | TBD | [22 empty] | Blake will follow up
Market | RMS | RO | SCR737 | Estimated Meter Read Data | 50091_01 |  |  | 9 - Parking Lot |  | $100k-$250k | [20 empty] | Create a calendar month, summary report to be presented at RMS that will provide Market Participants with estimated meter reading information broken-down by TDSP territory and indicating customer class. This report will also indicate the degree to which meter reads occur consecutively across two or more months and the degree to which estimates may straddle Move-Ins and Move-In/Forced Outs. | In its Resolution to RMS, TITF requested that NIDR estimated meter read data be provided to the market in order to monitor the number of estimates being submitted on a market-wide basis.