## Slide 1: Market Coordination Team Update Retail Market Subcommittee June 13, 2007 Susan Munson Retail Market Liaison/MODPO

## Slide 2: Risks / Issues
Issue | Mitigation | Owner
PUCT Mandate of 07/01/2007 poses tight timeline (Med) | Schedule and resource management Milestone completion | All
AIX Server Consolidation (Low) | AIX and TX SET Project Teams working closely together on dates. All servers used by TX SET have been scheduled for after 07/01/2007. | ERCOT
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 3: Project Schedule
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 4
PR40038_01 Status
Status:
  On target for schedule, budget, and scope
Project Phases:
  Initiation – Completed
  Planning – Completed
  Execution – Mandated completion date July 1, 2007; Go-Live 06/24/2007
  Closing – Target completion is post go-live
Recent Activity as of June 6, 2007:
  Continue ETS, Reprocessing, UAT (on track for completion 06/15/2007)
  Finalizing Migration Planning at ERCOT
Next Steps for ERCOT as of May 1, 2007:
  Finalize Production Migration Tasks = 06/15/2007
  Complete all testing = 06/15/2007
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 5
PR40038_01 Status
Recent Activity for MCT/TX SET:
  Finalized Production Implementation Plan
  Drafted and finalized Production Implementation Contingency Plan
  Recommended Texas SET Emergency Change Control 2007-708 for RMS vote to clarify a requirement
Next Steps for MCT:
  Production Implementation!
  Lessons Learned
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 6: Clarifications to Market Requirements
At May 24 MCT meeting
  Naming convention of Customer Billing Contact Information file per RMGRR052
  Use of the ‘TS’ code in cancelling transactions involved in a Mass Transition
From June 4 TX SET Change Control Call
  REF~5I segment will not be sent on 867_03 Finals with estimated meter reads (Ts & Cs Requirement 4)
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 7: Production Implementation Plan - FINAL
Finalized Production Implementation Plan for Texas SET 3.0
  Minor modifications made at May 24 MCT meeting
    997 schedule alignment
    ERCOT send system shutdown email
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 8: Production Contingency Plan - FINAL
Finalized Production Contingency Plan for Texas SET 3.0
  In the event of force majeure (e.g. fire, hurricane, tornado, etc.), the market will consider rescheduling Texas SET 3.0 implementation for the contingency weekend of June 30 – July 1.
  ERCOT and TDSP Contingency Plan
    Should ERCOT or a TDSP fail to successfully implement Texas SET Version 3.0 the Market will be notified on Saturday, June 23rd on the 6:00 PM Market Participant Conference Call. ERCOT and TDSPs will indicate on the 6:00 PM Market Participant Conference Call whether they need additional time for code migration. In this event, another Market Participant Conference Call will be scheduled for a later time on Saturday evening for a migration status update. If ERCOT or a TDSP is unable to migrate to Version 3.0, ERCOT or the TDSP will not reject Version 3.0 transactions and will hold them or work them manually until they can implement Texas SET Version 3.0.
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 9: Production Contingency Plan - FINAL
Finalized Production Contingency Plan for Texas SET 3.0
  CR Contingency Plan
    Should a CR fail to successfully implement Texas SET Version 3.0, the Market will be notified on a Market Participant Conference Call. The CR will coordinate a migration to minimize any potential impact to the rest of the Market. The CR will not reject Version 3.0 transactions and will hold them or work them manually until the CR can implement Texas SET Version 3.0.
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 10: Texas SET Emergency Change Control 2007-708
TX SET Approved and recommended for RMS vote on June 4 Texas SET Change Control Call
  Issue: Per Terms and Conditions Task Force, modify the 867_03 Monthly Usage transaction to include a new REF segment (REF~5I) that also provides data elements to communicate the reason for denial of access, where the reason for estimating only applies to the monthly usage (867_03) and not the 867_03 Final. However, ERCOT and some CRs coded that the REF~5I will always be sent on all 867_03s with estimated meter reads based on the following statement in the gray box on the REF~5I segment in the 867_03 Implementation Guide: “Required when usage has been estimated, otherwise not used.”
  Resolution: Clarification is needed in the gray box of the REF~5I segment in the 867_03 Implementation Guide to note specifically when this segment is required.
RMS Approved TX SET Change Control 2007-708 by email vote
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 11: Reminder: Where are Texas SET 3.0 Key Documents Kept?
  MCT page – ERCOT.com
  http://www.ercot.com/committees/board/tac/rms/mct/index.html
  And what is there?
  Texas SET Version 3.0 Requirements Final Version 1.13
  Texas SET 3.0 - MCT Issues & FAQs Log
  Texas SET Version 3.0 Change Controls
  Texas SET Guides Version 3.0
  Texas SET Version 3.0 Implementation Plan FINAL
  Texas SET Contingency Plan FINAL
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 12
Meeting Dates and Locations 2007
  June 25 – Emergency MCT Conference Call (only if needed)
  June 28 – MCT and TX SET Conference Call
  July 20 – AEP, Corpus Christi
  August 29 (Lessons Learned) – ERCOT Met Center
(Note: all meetings are held in conjunction with TX SET meetings)
Future Meetings/Market Communications
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 13: ERCOT Contacts
ERCOT Project Manager ERCOT SR. Business Analyst
Hope Parrish Jennifer Frederick
hparrish@ercot.com jfrederick@ercot.com
512-248-6522 (w) 512-248-6733 (w)
512-771-9582 (c) 512-413-0815 (c)
ERCOT Market Liaison
Susan Munson
smunson@ercot.com
512-248-3881 (w)
512-826-0564 (c)
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO

## Slide 14: Questions?
Project: PR40038_01 Current Phase: Execution
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $1-$3 MM Program Area: RO