## TPTF Comments & Responses
FollowUp | Document Name: | [5 empty] | Texas Nodal EDS3 SCED Handbook Phase 1 Comments Review, Version 0.01
| S.No. | Issuing Entity (Name) | Page Number | Section | Req./Table /Fig. | No., Pg, Sec., Req. | Description | Response Type | Reason / Comment
| 1 | D.S. Mai (NRG) | Various |  |  |  | General Edits & Additions | Accepted
| 2 | D.S. Mai (NRG) | 8 | Phase 3 |  |  | • Simulated inputs for each Generation Resource to support calculation of LASL, LDL, HDL, HASL (using Zonal AS awards spread out to individual units?), SURAMP, SDRAMP – Note: should this be in phase 2, as part of SCED execution testing? | Clarification Provided* | Adjusting document to remove Zonal reference and AS clarification.
| 3 | D.S. Mai (NRG) | 8 | Phase 3 |  |  | • Review SCED produced Base Points and LMPs for reasonability, including the LMPs for Hubs and Load Zones | Accepted | LMPs for Hub and Load Zones will not be available until Phase 3.
| 4 | D.S. Mai (NRG) | 14 | Phase 1 |  |  | Note: if QSEs submits data using Web Services, can QSEs view what was submitted via SCED UI? | Clarification Provided* | Yes, updated Document to ensure clarity.
| 5 | D.S. Mai (NRG) |  |  |  |  | • Reject COP with corresponding error message(s) if at least one of the following conditions is not met: o Resource name must be a valid registered resource name o Generation Resource Status must be a valid Generation Resource status code o Load Resource Status must be a valid Load Resource status code o HSL must be less than or equal to High Reasonability Limit o LSL must be greater than or equal to Low Reasonability Limit o HEL must be greater than or equal to HSL o LEL must be less than or equal to LSL o HSL must be greater than or equal to the sum of (Reg Up Responsibility + Responsive Reserve Responsibility + Non-Spin Responsibility + Reg Down Responsibility+LSL) o COP is submitted for an invalid time period (e.g. in the past) • Issue corresponding warning(s) if at least one of the following conditions is not met: o A Resource with a Resource Status of ONTEST must have a corresponding valid Output Schedule o For combined-cycle Resources, the COP data items must be submitted for each registered configuration •Rejection of COP due to out of HSL/LSL range - (HSL/LSL submitted is out of the high/low reasonability limit range) [I think the MMS team intends to change this to just a warning and not a rejection. Check with Resemi] Rejection of COP due to submitting for an invalid time period (i.e. in the past) Validate the Reg Up and Reg Down vs. Resource Status Validate the HSL/LSL vs. Reasonability Limit Parameters • Validate the Resource RRS vs. HSL-LSL | Pending | Working with Project Team to review. Will have update by TPTF meeting.
x | 6 | D.S. Mai (NRG) | 17 | Phase 1 |  |  | Note: there may be more reasons to either reject COP, or accept COP while issuing warnings to QSE. It may be worth describing in a document what COP is used for (e.g. validation of Output Schedules, Forced Outage Detection, RUC, study mode network analysis, etc.), and conditions under which COP is rejected, or accepted with warming messages. There is a document – “Texas Nodal MMS Explanation of Market Submission Items” – that describes certain COP validation, acceptance, and rejection steps, but it does not describe all steps. | Pending | Working with Project Team to ensure the referenced document is updated.Will have update by TPTF meeting.
| 7 | D.S. Mai (NRG) | 17 | Phase 1 |  |  | • Rejection due to violation of SCED Up/Down ramp rates Note: which source of data is used to calculate the SCED Up/Ddown ramp rates for this purpose, i.e. is COP the source of data? | Pending | Working with Project SMEs to clarify. Will have update by TPTF meeting.
x | 8 | D.S. Mai (NRG) | 24 | Phase 1 |  |  | Note: how will SCED model JOU in this phase? | Pending | Working with Project SMEs to determine JOU clarify.
| 9 | D.S. Mai (NRG) | 25 | Phase 1 |  |  | note: when will the SCED UI Manual be distributed?. | Clarification Provided | This document is posted on the Readiness Center (Nodal Website). Link to be provided.
x | 10 | [6 empty] | Clarification Provided
| 11 | [6 empty] | Clarification Provided

## Punch List
Document Name:
Punch List # | Punch List Description | Related TPTF Comment

## Data Entry Lists
Response | Description
Accepted | Comment accepted and requirements document updated as per the comment.
Clarification Provided* | Clarification provided and requirements document updated to clarify
Clarification Provided | Clarification provided and no updates made to the requirements document.
Pending | Issue is not resolved yet. All pending issues will be dispositioned to a punch list and resolved later. These issues need more time and coordination across multiple Nodal projects.
Rejected | Comment rejected as it does not comply with Nodal Protocols.