## Sheet1
Document Name: Texas Nodal Market Readiness Metric Inventory Version 0.14
S.No. | Issuing Entity (Name) | Pg. Sec., Req. | Description | Response | Reviewer | Reason / Comment | IDA Punch List
| GP&L-Ronnie H. | CO1 | CO1 - Settle Market for 7 Days and provide appropriate extracts: There should be a metric for the API’s to access the COM’s data under the Commercial Operations Metrics section | Pending | Grendel | There are currently no APIs in scope for settlement transactions. Settlement invoices and statements will be posted by ERCOT for download by MPs.
| GP&L-Ronnie H. | CO1 | CO1 - Settle Market for 7 Days and provide appropriate extracts; Should be Posted DAM Statements; Add Posted RT Statements along with RT invoices; On RT, what about 7 initials, 7 finals, and 7 True-ups (please detail) | Accepted | Barnes | Details on settlement and invoices statements added to criteria.
| LCRA - Naomi Richard | General Comment | 1. The difference between CRR2 and CRR4 is unclear. It seems like if you create the plan in CRR2, it can also be "implemented" in that same metric. Just a thought. | Rejected | Grendel | To maintain the clarity between the development of the TCR to CRR transition plan and the successful execution of the approved plan ERCOT suggests these metrics remain separate.
| LCRA - Naomi Richard | General Comment | 2. The difference between IMM1 and E7 is unclear. | Question | Grendel | E7 verifies ERCOT’s EDW is functional and accessible from the WEMM’s perspective. E7 is a metric on ERCOT’s EDW capability. IMM1 verifies the WEMM is ready to perform their market monitoring function from a staffing, systems and data access perspective and is a measurement on the WEMM’s readiness.
| LCRA - Naomi Richard | General Comment | 3. Should IMM1 have a signoff from the WEMM and the PUC since both are shown? | Accepted | Grendel | IMM1 will be edited as suggested.
| LCRA - Naomi Richard | General Comment | 4. How will planning documents be evaluated in MP1? For example, is the mere submission of a document titled a "Training Plan" sufficient? What about test plans - what type of detail will satisfy this requirement? Will documents submitted need to conform to a certain template or PMI standard? | Question | Grendel | MP1 does not require that documents be submitted to ERCOT. It only requires the accountable executive to attest that such a document exists and that the documentation meets the companies readiness and project needs.
| LCRA - Naomi Richard | General Comment | 5. Will the next publication of the Metric Report solve outstanding TBD's? | Accepted | Grendel | TBDs will be replaced as specific dates are identified.
| LCRA - Naomi Richard | General Comment | 6. CRR1 specifies that a CRR Test Plan will be developed. Should there be an equivalent for Commercial Operations, Enterprise Data Warehouse, etc.? | Question | Grendel | The ERCOT Nodal Transition Plan specifically requires test plans for the following: Trial Operation of the CRR Auction, Trial Operation of the DAM and Trial Operation of RUC. Each of these will be detailed in the EDS handbook. At this point in time ERCOT has only identified the CRR Auction test plan as a stand alone metric.
| LCRA - Naomi Richard | General Comment | 7. The document references a Dashboard and a Scorecard. Where will the metrics appear in general? | Question | Grendel | In general, Readiness Metric status will be communicated by the ERCOT Nodal PMO on a monthly basis.
| TXU - Bob Spangler | General Comment | 1. Better coordiantion between this document and the EDS Handbooks that describe the EDS test sequences is required. For example, with regard to the Market Participant Section – TXU recommends that the MP Metrics be grouped by early delivery system (i.e. EDS 1, 2, 3 and 4), where applicable, leaving those that apply across all of the EDS or are strictly contingent on market open as a final category. | Pending | Grendel | The Market Readiness team is working closely with the EDS teams to coordinate metrics and EDS test sequences. Linkages to EDS test sequences will be inserted as the EDS handbooks are developed.
| TXU - Bob Spangler | General Comment | 2. When grouping within the EDS test sequence, the metric should be specific to the EDS test handbook test functions that are designated for inclsion in the EDS releases. Criteria should be based on: the population of Market Particpants that are affected, the number of MP actually particpating, and the number that have successfully completed the testing (i.e. the idea here is that all participating MP have achieved the requested performance by the end date of the test). The function of the readiness project is to report these numbers - strict pass/fail percentages are not required for the MP metrics. Value judgements regarding the each metric by ERCOT, TPTF, TAC and the Board (as required by the Transition Plan ) are sufficient. Perhaps a check‑off box for each entity making the value judgement is a good approach. These same comment applies, as appropriate, to the other ot general category of MP metrics. | Rejected | Pare | ERCOT has described the metrics model including roll-up and grading rules that interpret underlying measures into simple red, amber, green metrics at various levels of abstraction. These rules are fundamentally judgments, and the model can be adjusted in the light of practical experience. Ultimately, the self-reporting concept can be utilized to require each entity to attest to their individual readiness in the light of their latest scorecard.
| TXU - Bob Spangler | General Comment | 3. Reporting Data Sources should be expanded to include the responsible ERCOT group that will make any determination (i.e. the EDS Test Team, ERCOT Compliance, etc.). | Accepted | Grendel | The responsible ERCOT group will be added to the document.
| TXU - Bob Spangler | General Comment | 4. The only time the term Market Particpant should be used in the name of a criteria is when the readiness criteria applies to all market particpants. Otherwise, the name should explicitly reference the target MP. For example, it may be appropriate to use MP in the name of MP1 but not in MP3 which is specific to QSEs with Resources. This is a general comment that should be applied throughout the document. TXU’s suggested changes in this regard are not meant to be all inclusive but, rather are examples. | Accepted | Grendel | The term “Market Participant” will be replace throughout the document with the specific MP type that is impacted by each metric. Version 0.19 have been updated for all MP metrics. The remainder will be updated in a subsequent version.
| TXU - Bob Spangler | General Comment | 5. Target Completion dates need clarification – if you continue to use the milestone reference +/- x days, please also include a reference date xx/xx/xx based on the current project schedule. | Accepted | Grendel | A table with reference dates from the current project schedule will be added to the document
| TXU - Bob Spangler | General Comment | 6. The following reflects detailed markups in the MP section of the document. The genral comments identified above are meant to apply to all sections of the document and the lack of detailed comment does not represent the acceptability of the presentation or acceptability of the metric. It mey be useful to have workshops that envolve TPTF and the PMO office before going final with this document. As a first priority, the project We should at least finalize the metrics that relate to EDS 1 and 2. The remaining metrics can follow later. | Accepted | Grendel | Metrics will be discussed and reviewed by EDS in a chronological fashion. Metric workshops will be scheduled as necessary with TPTF.
| TXU - Bob Spangler | MP1 | The target items deleted are internal business processes for the market particpants and are confidential information. There is no need for ERCOT to track internal MP Business Processes. ERCOT’s scope of readiness monitoring extends only to its interfaces with MP for commmunications and inforamtion that MP are requried to provide to ERCOT in accordance with approved protocols. | Pending | Tim Pare | The intent of this metric is to ensure that Market Participants are engaged in Nodal preparations. ERCOT does not plan to review details associated with MP budgeting or project management activities. We do want assurances from the accountable executives that the necessary steps are being taken to ready their organizations for December 1st, 2008 nodal go live target.
| TXU - Bob Spangler | MP1 | Recommended Criteria: Aggregation - % MP >= 95% | Pending | Tim Pare | The roll up aggregation for this metric is currently “Aggregation - % of Load and Generation >= 95%”. ERCOT has set the target for overall market readiness at 95% of generation MWs “ready” and 95% of load MWs “ready”.
| TXU - Bob Spangler | MP2 | MP2 – QSE with Resources Connectivity to ERCOT Reported By: QSE with Resources & ERCOT EDS: 3 Target Completion: 6-month LMP posting major milestone less 45 days Metric Description: QSEs with resources have confirmed their ability to connect to the MIS and/or an External Web Service in the early Early Delivery System 1, 2 and 3 environments. Background: The intent of this metric is to ensure that QSEs with Resources can successfully connect to ERCOT. Criteria: The Readiness Team will review documentation providing connectivity statistics by Market Participant. Readiness will be met when the QSE successfully submits a transaction (at least one? At least one of each of a list of transaction types?) that is logged in the Enterprise Integration Framework (EIF) transaction database as successfully passing the proxy server. EIF entry per MP >=1 Connectivity is too broad a criterion. Connectivity involves links over ICCP, the MIS Portal and the external Web Service API. All QSEs, with or without physical resources, CRR Account Holders, and TSPs may use any or all of the connectivity links identified above. If you desire to split all of the connectivity into individual metrics, then the metric names need to reflect the connectivity being tested. | Pending | Steve Grendel | The connectivity criterion has been tightened as follows: Readiness will be met when the MP successfully submits a three part offer, incremental/decremental offer, current operating plan or a output schedule via either web services or the MIS that is logged in the Enterprise Integration Framework (EIF) transaction database as successfully passing the proxy server. Only a single transaction is required to verify connectivity.
| TXU - Bob Spangler | MP3 | MP3 – QSE with Resources Upload of SCED Offers to ERCOT Reported By: QSE with Resources & ERCOT EDS: 3 Target Completion: 6-month LMP posting major milestone less 45 days see genral note 1 Metric Description: QSEs with Resources shall demonstrate their ability to successfully submit energy offer curves within a three part offer context to the MIS and/or an External Web Service in the Early Delivery System (EDS) environment. Background: The intent of this metric is to ensure that QSEs with Resources can successfully submit a 3-part offer (output schedule?) to the ERCOT. Criteria: The Readiness Team will review documentation providing transaction statistics by Market Participant. Readiness will be met when the MP successfully submits a request that is logged in the Enterprise Integration Framework (EIF) transaction database. (same comments as for MP2 Criteria) EIF entry with transaction status of Passed per MP >=1 Reporting Data Sources: EIF log table entry in EDS References TP: N/A TNP: N/A | Pending | Grendel | Comments incorporated.
| TXU - Bob Spangler | MP4 | Target Completion: 6-month LMP posting major milestone less 60 days – This completion date seems late – will test digital certificates be needed earlier in the EDS 3 test sequence? | Pending | Hall | At this point in time MPs will use their current zonal production certificates for all EDS 3 activities. MP4 is no longer necessary. If this approach changes this metric will be reinstated and adjusted as required.
| TXU - Bob Spangler | MP4 | Background: The intent of this metric is to ensure that Market Participants have digital certificates for the Nodal Testing environment {What about the production environment?} | Pending | Hall | At this point in time MPs will use their current zonal production certificates for all EDS 3 activities. MP4 is no longer necessary. If this approach changes this metric will be reinstated and adjusted as required.
| TXU - Bob Spangler | MP4 | Criteria: Readiness Team will review documentation reporting upon the issuance of digital certificates to Market Participants. Readiness will be met when a Nodal test environment digital certificate has been mailed to a registered / qualified MP. Which ERCOT organization is responsible for this activity and is there a concurrent ERCOT readiness criterion? | Pending | Hall | At this point in time MPs will use their current zonal production certificates for all EDS 3 activities. MP4 is no longer necessary. If this approach changes this metric will be reinstated and adjusted as required.
| TXU - Bob Spangler | MP5 | Criteria: The Readiness Team will review documentation ( what documentation and whose documentation?) that verifies the accuracy of telemetry points mapping, values and status within an acceptable scan rate. Readiness will be achieved when TSPs, QSEs and ERCOT have mapped all required points to meet Nodal Protocols, Point to Point Verification has occurred, and all Telemetry issues have been documented and communicated to MPs, when ERCOT has ICCP database under change control and service requests needed to resolve ICCP issues have been submitted. See general comment 2. | Question | Hall | Documentation generated by the EDS 1 team will be utilized to verify the criteria related to MP5. Specifically, the weekly posted “EDS 1 Status MMDDYYYY.xls” will be utilized to verify the status of MP5
| TXU - Bob Spangler | MP5 | MP5 – What do these mean? Server Fail Over >=5 Minutes Com Link Failover >= 30 Seconds Com link availability >= 85% of data for 98% of the time Critical Telemetry Data >= 95% of data for 90% of the time All Telemetry Data >= 98% of data for 80% of the time | Question | Webb | These targets come from the TAC approved telemetry standards.
| TXU - Bob Spangler | MP6 | MP6 – QSE and TSP Telemetry/ICCP System Availability Reported By: QSE and TSP & ERCOT EDS: 1,2 Target Completion: EDS 2 – Release 3 plus 14 days Metric Description: Verify that all MP telemetry availability criteria are met. Background: The intent of this metric is to ensure that MP telemetry systems are stable in a redundant state and meet TAC approved telemetry data standards. Criteria: The Readiness Team will verify that telemetry failover thresholds and data availability standards are met by MPs. Readiness will be achieved when the MPs have passed a simulated failover test and proven data availability. What do these mean? Also see general comment 2. | Pending |  | These targets come from the TAC approved telemetry standards.
| TXU - Bob Spangler | MP7 | MP7 - MP Use of MIS Reported By: MP & ERCOT EDS: 3,4 Target Completion: EDS-4 Release 9 Complete Metric Description: This metric will measure Market Participant hits to the Nodal MIS of specified functions as part of the QSE qualification activities, limited to MIS Secure Area and MIS Certified Area.{This seems pointless – MIS comes in two flavors, it can be used to flow information to ERCOT (i.e. 3-part offers) and to retrive information from ERCOT (i.e. LMPs ). The EDS test sequences should validate each of these functionalities. QSE use of the MIS portlets to provide information to ERCOT should be validated in each EDS test sequence. On the other hand, ERCOT can validate that the MIS portlets include all of the inforamtion described in the MIS spec. It is up to the MP to assure its own ability to retrive information from MIS. No rediness criteria for inforamation retrival by MP is necessary.} Background: It is the intent of this metric to ensure that an adequate volume of transactions has passed through the MIS on through to the MMS to adequately represent market conditions as confirmation of unit testing. If this is desired then a specific test should be accomplished by ERCOT to stress the volumetric capacity of the MIS and associated broadband communications channels to meet the MIS specification for market information submission and retrival. Criteria: The Readiness Team will review documentation that verifies that an adequate number of market participants have sent and received information through the MIS during EDS activities. Readiness will be met when an adequate number of transactions occurs. T In other words you want at least 75% of the MPs to each submit 100 transactions? In what time period? This criterion needs better definition. Also see general comment 2. | Pending | Hall | MP7 will be removed from the metrics list. The intent of the metric was to verify the ERCOT system could function under full volume conditions. This will be achieved during the 168 hour test and therefore this metric is not necessary.
| TXU - Bob Spangler | MP8 | MP8 - QSE AP & RTM Transactions Reported By: QSEs & ERCOT EDS: 3,4 Target Completion: EDS-4 Release – 24*7 Operations Metric Description: ERCOT shall verify the ability of QSE to send transactions associated with the Adjustment Period (AP) and Real Time Market (RTM). Note in the AP and Real time QSEs will exchange data with ERCOt via ICCP and the messenging system which presumably will be accomplished by ICCP and a web service. Is this criteria addressing both ICCP and the web service? Background: The intent of this metric is to ensure that QSEs have the ability to participate in the real time market. Criteria: The Readiness Team will review documentation that verifies that market participants can and have successfully sent test real time transactions. Readiness will be met when ERCOT has observed Market Participants successfully sending test real time transactions. MP Transactions Sent = MP Transactions Received at ERCOT What does this criterion mean? In each of the EDSD test sequences there needs to be a milestone that address this criteria. This milestone should be sufficiently far into the test sequence such that errors that occur early in the test sequence are identified, corrected and retested. Is the successful completion of the test sequence the culminating event that determines acceptance? We believe that all QSEs who are to do business in the nodal market must agree to their capability to perform. | Pending | Kasparian | This metric is specific to MIS and Web Service transactions. ICCP transactions will be considered under MP5 and MP6. This metric will be measured during the first week of "7 by 24 full nodal operation" starting on July 1st, 2008. Specific details on required transactions will be provided in the appropriate EDS handbook and consistent with protocol requirements.
| TXU - Bob Spangler | MP9 | MP9 - QSE DAM Transactions Reported By: QSE & ERCOT EDS: 4 Target Completion: EDS-4 Release 9 – 24*7 Operations Metric Description: ERCOT shall verify the ability of QSE to submit transactions associated with the Day Ahead Market. Is this a sufficient description? What is if interest may be that QSEs are capable of submitting all information requried by the Nodal Protocols that is necessary for the successful functioning of DAM optimization engine. Will the EDS test sequence demonstrate this on a QSE by QSE basis? Background: The intent of this metric is to ensure that QSEs have the ability to participate in the Day Ahead Market. Criteria: The Readiness Team will review documentation that verifies that the market participants can and have successfully sent test DA Transactions. Readiness will be met when ERCOT has observed Market Participants successfully sending test DA transactions. MP Transactions Sent = MP Transactions Received at ERCOT See comment under Criteria in MP8 above. | Pending | Kasparian | This metric is specific to MIS and Web Service transactions. ICCP transactions will be considered under MP5 and MP6. This metric will be measured during the first week of "7 by 24 full nodal operation" starting on July 1st, 2008. Specific details on required transactions will be provided in the appropriate EDS handbook and consistent with protocol requirements.
| TXU - Bob Spangler | MP10 | MP10 - Mapping of Resources to Resource Nodes and Resources to Revenue Quality Meters is Complete Reported By: MP & ERCOT This is an ERCOT driven activity EDS: Registration | Pending | Mereness | This is an ERCOT driven activity? Yes, this will be driven by ERCOT.
| TXU - Bob Spangler | MP12 | MP12 - MP Completes EDS-3 Related Training; Criteria: ERCOT Training will dashboard MP training progress against the commitments provided by each Accountable Executive. Progress will be reported to the Accountable Executive and the readiness evaluators (TPTF, TAC, and the ERCOT Board). | Accepted | Hailu | Comments Accepted.
| TXU - Bob Spangler | MP13 | MP 13 - Same comment as above | Accepted | Hailu | Comments Accepted.
| TXU - Bob Spangler | MP14,MP15,MP16,MP17 | MP14,MP15,MP16,MP17 - General Comment 2: When grouping within the EDS test sequence, the metric should be specific to the EDS test handbook test functions that are designated for inclsion in the EDS releases. Criteria should be based on: the population of Market Particpants that are affected, the number of MP actually particpating, and the number that have successfully completed the testing (i.e. the idea here is that all participating MP have achieved the requested performance by the end date of the test). The function of the readiness project is to report these numbers - strict pass/fail percentages are not required for the MP metrics. Value judgements regarding the each metric by ERCOT, TPTF, TAC and the Board (as required by the Transition Plan ) are sufficient. Perhaps a check‑off box for each entity making the value judgement is a good approach. These same comment applies, as appropriate, to the other ot general category of MP metrics. | Pending | Pare | Accepted with the following comments: Metrics will be linked to specific EDS test handbook test functions as the handbooks are drafted. It seems appropriate to establish the targets so that we can "raise" the flag if we are falling behind in any area. At some point in time the percentage targets will be necessary to establish an opinion of readiness.
| TXU - Bob Spangler | MP15 | MP 15: Criteria: The Readiness Team will review documentation that an adequate number of MPs by market segment have submitted output schedules and three-part supply offer curves, have participated in the CRR auction (? Is this an EDS 3 activity?) and have participated in LFC Testing. | Question | Grendel | Yes, the CRR auction is an EDS 3 activity.
| TXU - Bob Spangler | CO2 | CO2 - Does this mean that ERCOT will request each MP submit a dispute? | Pending | Mereness | This metric does ask each QSE and CRR account holder to submit a dispute.
| TXU - Bob Spangler | CO9 | CO9 - If a QSE in the zonal market is responding with the transfer of funds, what more is needed? Does this apply to CRR auction settlement? | Pending |  | Review with Cheryl Yager or Sylvia S.
| TXU - Bob Spangler | CO10 | CO10 - The issue of credit and credit worthiness should be handled internally at ERCOT and is the responsibility of the ERCOT organizations responsible for this activity in today’s zonal market. These groups should be required to provide a dashboard that shows progress in establishing a credit relationship with new market participants (e.g. CRR Account Holders) and, if necessary in their opinion, existing market participants. | Pending | Grendel | This Market Readiness Criteria is called out specifically in the Nodal Transition Plan.
| Reliant - Marguerite Wagner | General Comment | From a formatting perspective, it would be helpful to increase the size of the text used to define the metrics | Accepted
| Reliant - Marguerite Wagner | MP1 | This is a useful metric, but may want to consider a focus on training, registration and EDS participation and striking things about budgeting, project management, and business impact. The latter are internal business decisions. Recommend keeping focus on the interface between MPs and ERCOT—and away from internal MP activities. | Rejected | Pare | ERCOT has described the metrics model including roll-up and grading rules that interpret underlying measures into simple red, amber, green metrics at various levels of abstraction. These rules are fundamentally judgments, and the model can be adjusted in the light of practical experience. Ultimately, the self-reporting concept can be utilized to require each entity to attest to their individual readiness in the light of their latest scorecard.
| Reliant - Marguerite Wagner | MP2 | QSEs with resources have demonstrated their ability to connect to the MIS and/or an External Web Service in the early Early Delivery System (EDS) environment and that they can submit 3 part offers and, if applicable, dynamic output schedules. | Accepted | Grendel | MP2 is focused on connectivity. MP3 will be updated to reflect these comments.
| Reliant - Marguerite Wagner | MP2 | The Readiness Team will review documentation providing connectivity statistics and status of data submitted through the nodal sandbox environment by Market Participant. Readiness will be met when the MP successfully submits a transaction that is logged in the Enterprise Integration Framework (EIF) transaction database as successfully passing the proxy server. [Reliant: shouldn’t it also have to pass validation with the MMS system?] | Pending | Grendel | MP2 focuses only on connectivity. Data validation is addressed in MP3.
| Reliant - Marguerite Wagner | MP2 | Reliant: is this only for QSEs with Resources? If so the measurement below requires revision. EIF entry per MP >=1 | Accepted | Grendel | MP2 only applies to QSEs with resources.
| Reliant - Marguerite Wagner | MP3 | Reliant: the clarifications we provided in previous metric are also applicable here | Accepted | Grendel
| Reliant - Marguerite Wagner | MP5 | Is EDS1 looking at scan rates? Was under the impression that this was solely a manual interface to data on both sides wherein ERCOT or MP changed status and the other party was to see it. The scan rate might be a good metric, but am not sure that it is consistent with what is being done in EDS1 | Question | Grendel | EDS1 does look at scan rate as required by the ERCOT Transition Plan (5.4.1 (2k) - Verify telemetry meets Protocol 3.10.7.4 (failover, scan rates)) Nodal Protocol Reference: “The telemetry provided to ERCOT by each TSP must be updated at a 10 second or less scan rate and be provided to ERCOT at the same rate “
| Reliant - Marguerite Wagner | MP5 | not all nodal points are being tested in EDS1—so this likely is not verifiable in EDS1. The nodal submission points should be verified somewhere else, though | Rejected | Grendel | It is the intent of ERCOT to verify all nodal points during the execution of EDS 1.
| Reliant - Marguerite Wagner | MP5 | not all nodal points are bing checked. May want to change this to be a statistic against the NMMS—how about points in the NMMS are consistent on both sides | Rejected | Grendel | It is the intent of ERCOT to verify all nodal points during the execution of EDS 1.
| Reliant - Marguerite Wagner | MP6 | Verify that all MP telemetry availability criteria are met. [Reliant: is there a parallel requirement on the ERCOT side—for failover and other metrics?] | Question | Grendel | Yes there is. ERCOT’s contingency operation metrics are addressed in C1 through C10.
| ERCOT - CRR Team | R1 | Target Completion: Go Live less 60 days [If this is assumed as Dec 1, 2008, then the declaration needs to be earlier. CRR will be holding its first Monthly auction 30 days prior to RT market go-live, with PCRR and MCFRI allocations completed ~ 3 weeks prior to the start of te auction.] | Accepted | Grendel | Metric R1 updated with earlier start date. Go live less 60 days adopted in metric.
| ERCOT - CRR Team | CRR2 | Target Completion: August 2007 [The transition plan will address the contents of the 2008 Annual TCR (zonal) auction, which will be held in December 2007, with info posted 20 days prior, and PCR requests and allocations completed prior to auction posting. CRR expects to develop early version in August 07, and subsequently refine the plan for 08 activities. The 'final' transition plan should be baked 180 days prior to the first monthly CRR auction.] | Accepted | Grendel | Metric CRR2 updated with final transition plan complete180 days prior to the first monthly CRR auction.