| Flight Schedule for Version 3.0 Flights in 2008 | 0108 |
| --- | --- |
| Activity | Calendar Date |
| Notice from ERCOT Retail Client Services of the next flight for Retail Market Testing sent to ERCOT lists.ercot.com distribution | Nov. 07, 07 |
| TTPT to finalize scripts | Nov. 28, 07 |
| Testing Worksheets are unlocked | Dec. 05, 07 |
| FLIGHT DEADLINE The following 4 steps must be completed by 5PM CPT. on the deadline: CR must have submitted ERCOT LSE Application and Application Fee CR must have filed for PUCT REP Certification TW updated on ERCOT Retail Testing Website Send an e-mail of intent to test to ERCOT at: RetailMarketTesting@ercot.com The following steps must be completed by 5PM CPT. on the deadline for current MPs: TW updated on ERCOT Retail Testing Website Send an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com Testing Worksheets are locked at 5PM CPT. | Dec. 12, 07 |
| ERCOT Retail Client Services verifies that each new Testing Participant has completed Registration testing requirements with ERCOT | Dec. 14, 07 |
| Verification and communication from PUCT Staff that Testing Participants intending to test have applied for REP Certification | Dec. 14, 07 |
| Communication from ERCOT Flight Administrator of Testing Participants to each TDSP | Dec. 14, 07 |
| MPs to start scheduling connectivity | Dec. 17, 07 |
| Communication of Test Certificates from ERCOT Retail Client Services to all Testing Participants | Dec. 17, 07 |
| TDSPs and ERCOT have completed communication of connectivity testing schedule to each Trading Partner | Dec. 17, 07 |
| Connectivity Testing kick-off Conference Call - Mandatory for all Testing Participants (black-out ends) | Dec. 18, 07 |
| Connectivity Testing begins for all Testing Participants | Dec. 18, 07 |
| Penny Test (CON52) & ACK55/56 (FA Scripts) begins for all New Testing Participants | Dec. 18, 07 |
| TDSPs communicate test bed load to Trading Partners and ERCOT | Jan. 07, 08 |
| Flight Kick off Conference Calls - Mandatory for all Testing Participants | Jan. 11, 08 |
| Daily Conference Calls begin – Day 1 Transactions flow | Jan. 14, 08 |
| Flight tentatively scheduled to conclude | Feb. 26, 08 |
| Contingency Testing scheduled to conclude for Flight (black-out starts) | March 14, 08 |

| Flight Schedule for Version 3.0 Flights in 2008 | 0408 |
| --- | --- |
| Activity | Calendar Date |
| Notice from ERCOT Retail Client Services of the next flight for Retail Market Testing sent to ERCOT lists.ercot.com distribution | Feb. 06, 08 |
| TTPT to finalize scripts | Feb. 27, 08 |
| Testing Worksheets are unlocked | March 05, 08 |
| FLIGHT DEADLINE The following 4 steps must be completed by 5PM CPT. on the deadline: CR must have submitted ERCOT LSE Application and Application Fee CR must have filed for PUCT REP Certification TW updated on ERCOT Retail Testing Website Send an e-mail of intent to test to ERCOT at: RetailMarketTesting@ercot.com The following steps must be completed by 5PM CPT. on the deadline for current MPs: TW updated on ERCOT Retail Testing Website Send an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com Testing Worksheets are locked at 5PM CPT. | March 12, 08 |
| ERCOT Retail Client Services verifies that each new Testing Participant has completed Registration testing requirements with ERCOT | March 14, 08 |
| Verification and communication from PUCT Staff that Testing Participants intending to test have applied for REP Certification | March 14, 08 |
| Communication from ERCOT Flight Administrator of Testing Participants to each TDSP | March 14, 08 |
| MPs to start scheduling connectivity | March 17, 08 |
| Communication of Test Certificates from ERCOT Retail Client Services to all Testing Participants | March 17, 08 |
| TDSPs and ERCOT have completed communication of connectivity testing schedule to each Trading Partner | March 17, 08 |
| Connectivity Testing kick-off Conference Call - Mandatory for all Testing Participants (black-out ends) | March 18, 08 |
| Connectivity Testing begins for all Testing Participants | March 18, 08 |
| Penny Test (CON52) & ACK55/56 (FA Scripts) begins for all New Testing Participants | March 18, 08 |
| TDSPs communicate test bed load to Trading Partners and ERCOT | April 07, 08 |
| Flight Kick off Conference Calls - Mandatory for all Testing Participants | April 11, 08 |
| Daily Conference Calls begin – Day 1 Transactions flow | April 14, 08 |
| Flight tentatively scheduled to conclude | May 27, 08 |
| Contingency Testing scheduled to conclude for Flight (black-out starts) | June 17, 08 |
| Flight Schedule for Version 3.0 Flights in 2008 | 0708 |
| Activity | Calendar Date |
| Notice from ERCOT Retail Client Services of the next flight for Retail Market Testing sent to ERCOT lists.ercot.com distribution | May 14, 08 |
| TTPT to finalize scripts | June 4, 08 |
| Testing Worksheets are unlocked | June 11, 08 |
| FLIGHT DEADLINE The following 4 steps must be completed by 5PM CPT. on the deadline: CR must have submitted ERCOT LSE Application and Application Fee CR must have filed for PUCT REP Certification TW updated on ERCOT Retail Testing Website Send an e-mail of intent to test to ERCOT at: RetailMarketTesting@ercot.com The following steps must be completed by 5PM CPT. on the deadline for current MPs: TW updated on ERCOT Retail Testing Website Send an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com Testing Worksheets are locked at 5PM CPT. | June 18, 08 |
| ERCOT Retail Client Services verifies that each new Testing Participant has completed Registration testing requirements with ERCOT | June 20, 08 |
| Verification and communication from PUCT Staff that Testing Participants intending to test have applied for REP Certification | June 20, 08 |
| Communication from ERCOT Flight Administrator of Testing Participants to each TDSP | June 20, 08 |
| MPs to start scheduling connectivity | June 23, 08 |
| Communication of Test Certificates from ERCOT Retail Client Services to all Testing Participants | June 23, 08 |
| TDSPs and ERCOT have completed communication of connectivity testing schedule to each Trading Partner | June 23, 08 |
| Connectivity Testing kick-off Conference Call - Mandatory for all Testing Participants (black-out ends) | June 24, 08 |
| Connectivity Testing begins for all Testing Participants | June 24, 08 |
| Penny Test (CON52) & ACK55/56 (FA Scripts) begins for all New Testing Participants | June 24, 08 |
| TDSPs communicate test bed load to Trading Partners and ERCOT | June 30, 08 |
| Flight Kick off Conference Calls - Mandatory for all Testing Participants | July 7, 08 |
| Daily Conference Calls begin – Day 1 Transactions flow | July 7, 08 |
| Flight tentatively scheduled to conclude | Aug.19, 08 |
| Contingency Testing scheduled to conclude for Flight (black-out starts) | Sept. 9, 08 |
| Flight Schedule for Version 3.0 Flights in 2008 | 1008 |
| Activity | Calendar Date |
| Notice from ERCOT Retail Client Services of the next flight for Retail Market Testing sent to ERCOT lists.ercot.com distribution | Aug. 13, 08 |
| TTPT to finalize scripts | Sept. 3, 08 |
| Testing Worksheets are unlocked | Sept. 10, 08 |
| FLIGHT DEADLINE The following 4 steps must be completed by 5PM CPT. on the deadline: CR must have submitted ERCOT LSE Application and Application Fee CR must have filed for PUCT REP Certification TW updated on ERCOT Retail Testing Website Send an e-mail of intent to test to ERCOT at: RetailMarketTesting@ercot.com The following steps must be completed by 5PM CPT. on the deadline for current MPs: TW updated on ERCOT Retail Testing Website Send an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com Testing Worksheets are locked at 5PM CPT. | Sept. 17, 08 |
| ERCOT Retail Client Services verifies that each new Testing Participant has completed Registration testing requirements with ERCOT | Sept. 19, 08 |
| Verification and communication from PUCT Staff that Testing Participants intending to test have applied for REP Certification | Sept. 19, 08 |
| Communication from ERCOT Flight Administrator of Testing Participants to each TDSP | Sept. 19, 08 |
| MPs to start scheduling connectivity | Sept. 22, 08 |
| Communication of Test Certificates from ERCOT Retail Client Services to all Testing Participants | Sept. 22, 08 |
| TDSPs and ERCOT have completed communication of connectivity testing schedule to each Trading Partner | Sept. 22, 08 |
| Connectivity Testing kick-off Conference Call - Mandatory for all Testing Participants (black-out ends) | Sept. 23, 08 |
| Connectivity Testing begins for all Testing Participants | Sept. 23, 08 |
| Penny Test (CON52) & ACK55/56 (FA Scripts) begins for all New Testing Participants | Sept 23, 08 |
| TDSPs communicate test bed load to Trading Partners and ERCOT | Sept. 29, 08 |
| Flight Kick off Conference Calls - Mandatory for all Testing Participants | Oct. 3, 08 |
| Daily Conference Calls begin – Day 1 Transactions flow | Oct. 6, 08 |
| Flight tentatively scheduled to conclude | Nov. 18, 08 |
| Contingency Testing scheduled to conclude for Flight (black-out starts) | Dec. 9, 08 |